## Slide 1
CPAG – Energy Cluster
Rajasthan RE Projects
Monthly Report for Aug-26

## Slide 2
Agenda
Executive Summary
Project Wise Update (Bandha-II 500 MW, Baiya 600 MW)
            Project Information & Salient Features
            Project Plot Plant
            Overall S Curve
            Engineering Progress
            Three Month Rolling Plan for Material Supply
            Detailed Progress Update (Activity Wise)
            Major Milestone- Next 3 Months
            Manpower Deployment Plan vs Actual
2

## Slide 3
Rajasthan Projects Executive Summary
SN | Location | Project Name | Project Capacity (MW) | FY 27 Initial Plan (MW) | FY 27 Current Forecast (MW) | COD |  | Overall Progress % |  | Remarks
 |  |  |  |  |  | Baseline Plan | Achieved/ Expected | Plan | Actual | 
1 | RJ | MLP T1 TN – 500 MW Bandha II | 500 | 362.5 | 362.5 | 31-Jan-27 | 22-May-27 | 82 | 76 | 137.5 MW – Commissioned in Mar’26 Commissioning of balance 362.5 MW by May-27 based on LTA elements readiness.
2 | RJ | NHPC BOO 600 MW, Baiya | 600 | 349 | 349 | 31-Jan-27 | 23-Mar-27 | 83 | 79 | 251 MW – Commissioned in Mar’26 Commissioning of balance 349 MW is planned by Mar-27 considering court ruling in favour of AGEL by 17-Sep-26 and Piling work start by 4th week of Sep-26.
Total |  |  | 1,100 | 711.5 | 711.5 |  |  |  |  | 

## Slide 4: MLP T1 TN 500 MW Bandha Solar Project
4

## Slide 5: 500 MW Bandha: Salient Project Features
Project | 500 MW Bandha
Project Scope/ Capacity | 500 MW (695 MWdc)
Owner/ Developer | Adani Green Energy Twenty-Five B Limited
Location | Village – Bandha, Tehsil – Jaisalmer, Dist. Jaisalmer, Rajasthan
Concessionaire, If applicable | -
EPC, If applicable | NA
Land Area | 1853.25 Acre
Approved Budget (INR Cr.) (date: 01-Apr-25) | INR 2019.3 Cr
Revised Budget (INR Cr.) | NA
Project Start Date | Aug-24
Schedule COD | LTA operationalization + 60 days (Forecast LTA operationalization – Dec’26)
Revised COD, if any | -
Expected COD | 19-Feb-27 (137.5 MW Commissioned in Mar’26, 212.5 MW by Jan’27, 150 MW by Feb’27)
Other Comments | 
5

## Slide 6: 500 MW Bandha: Project Plot Plan
Description | Bandha II | 
Type of MMS | No. of Blocks | MW
Fixed Tilt | 40 | 500
Total | 40 | 500
Type of Land | Acres
Govt. | 1853.25
Pvt. | -
Total | 1853.25
6

## Slide 7: 500 MW Bandha: Overall S Curve
7
Gap Analysis |  |  |  |  | 
Progress Parameter | Weightage | Cumm. Plan | Cumm. Actual | Variance | Remarks for Variance
Land & Statutory | 7% | 98% | 63% | 35% | Land Sub Lease Pending
Engineering+ System Study | 13% | 100% | 100% | 0% | 
Procurement | 30% | 89% | 83% | 6% | 
Construction | 50% | 71% | 68% | 4% | 
Overall | 100% | 82% | 76% | 6% | 
Chart: Bandha_500 MW
| Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27
Overall Plan | 0.0044444 | 0.014444 | 0.0027876 | 0.0059725 | 0.0049333 | 0.0075231 | 0.018973 | 0.02824 | 0.088064 | 0.048278 | 0.063631 | 0.069858 | 0.061918 | 0.071897 | 0.048041 | 0.041431 | 0.038132 | 0.03902 | 0.04018 | 0.031418 | 0.0040089 | 0.032791 | 0.035668 | 0.017355 | 0.0047664 | 0.0059497 | 0.035693 | 0.03794 | 0.052402 | 0.030334 | 0.012697
Overall Actual | 0.0044444 | 0.014444 | 0.0027876 | 0.0059725 | 0.0049333 | 0.0075231 | 0.018973 | 0.02824 | 0.088064 | 0.048278 | 0.063631 | 0.069858 | 0.061918 | 0.071897 | 0.048041 | 0.041431 | 0.038132 | 0.03902 | 0.04018 | 0.031418 | 0.0040089 | 0.011139 | 0.0096321 | 0.0075874 | -0.0019206 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Engineering Plan
Engineering Actual
Procurement Plan
Procurement Actual
Construction Plan
Construction Actual
Land Plan
Land Actual
Overall Cummulative Plan | 0.0044444 | 0.018889 | 0.021677 | 0.027649 | 0.032582 | 0.040105 | 0.059078 | 0.087318 | 0.17538 | 0.22366 | 0.28729 | 0.35715 | 0.41907 | 0.49096 | 0.539 | 0.58044 | 0.61857 | 0.65759 | 0.69777 | 0.72919 | 0.73319 | 0.76599 | 0.80165 | 0.81901 | 0.82377 | 0.82972 | 0.86542 | 0.90336 | 0.95576 | 0.98609 | 0.99879
Overall Cummulative Actual | 0.0044444 | 0.018889 | 0.021677 | 0.027649 | 0.032582 | 0.040105 | 0.059078 | 0.087318 | 0.17538 | 0.22366 | 0.28729 | 0.35715 | 0.41907 | 0.49096 | 0.539 | 0.58044 | 0.61857 | 0.65759 | 0.69777 | 0.72919 | 0.73319 | 0.74433 | 0.75397 | 0.76155 | 0.75963 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 8
500 MW Bandha: Engineering Progress
Sr. No | Description | No. of Drawings | %
A (B+C) | Total | 272 | 100%
B (RFC+b1+b2+b3) | Approved | 272 | 100%
RFC | RFC | 241 | 
b1 | A1-Category | 23 | 
b2 | A2-Category | 0 | 
b3 | I-Category | 8 | 
C | Pending | 0 | 
A1-Category: Approved
A2-Category: Approved with Comments
I-Category: Information
8

## Slide 9: 500 MW Bandha: Procurement & 3 month rolling plan for Supply Status
S.No. | Packages | UOM | Scope | Ordering Completed | Balance Ordering | Delivered at Site up to Aug’26 | Forecast delivery schedule |  | 
 |  |  |  |  |  |  | Sep-26 | Oct-26 | Nov-26
1 | Module | MWp | 695 | 198 | 497 | 198 | - | - | -
2 | MMS - FT | MW | 500 | 500 | - | 500 | - | - | -
3 | IDT | Nos. | 41 | 41 | - | 41 | - | - | -
4 | Inverter | Nos. | 1937 | 1937 | - | 1937 | - | - | -
5 | HT Panel | Nos. | 40 | 40 | - | 40 | - | - | -
6 | LT Panel | Nos. | 654 | 654 | - | 654 | - | - | -
7 | HT Cable | km | 298 | 298 | - | 298 | - | - | -
8 | LT Cable | km | 457 | 457 | - | 457 | - | - | -
9 | Control Cable | km | 29 | 29 | - | 29 | - | - | -
10 | DC Cable | km | 3742 | 3742 | - | 3742 | - | - | -
11 | Robotic Module Cleaning System | Nos. | 1034 | 1034 | - | 1034 | - | - | -
9

## Slide 10: 500 MW Bandha: Construction Progress Update
10
Description | UOM | Scope | Completed upto Aug’26 | Balance as on Aug’26 | For the Month Aug'26 |  | Next 3 Month Rolling Plan |  |  | Completion Target
 |  |  |  |  | Plan | Actual | Sep-26 | Oct-26 | Nov-26 | 
Piling | Nos | 2,47,030 | 2,47,030 | - | - | - | - | - | - | 29-Dec-25
MMS - FT | Tables | 20,180 | 18,678 | 1,502 | - | - | 587 | 915 | - | 27-Oct-26
IDT Foundation | Blocks | 40 | 40 | - | - | - | - | - | - | 02-Oct-25
HT & LT Slab | Blocks | 40 | 40 | - | - | - | - | - | - | 13-Oct-25
HT & LT Canopy | Blocks | 40 | 40 | - | - | - | - | - | - | 12-Feb-26
IDT Erection | Blocks | 40 | 40 | - | - | - | - | - | - | 31-Jan-26
HT Panel Erection | Blocks | 40 | 40 | - | - | - | - | - | - | 25-Dec-25
LT Panel Erection | Nos. | 640 | 640 | - | 24 | 24 | - | - | - | 31-Aug-26
Inverter Erection | Nos. | 1,918 | 1,918 | - | - | - | - | - | - | 25-Jul-26
LT Cabling Works | Kms | 430 | 430 | - | - | - | - | - | - | 30-Jul-26
HT Cabling Works | Kms | 298 | 298 | - | - | - | - | - | - | 22-Jun-26
Module [Erection] | MWdc | 695 | 191 | 504 | - | - | - | - | - | 03-May-27
MC4 & VOC | MWdc | 695 | 191 | 504 | - | - | - | - | - | 08-May-27
CEA Inspection & Approval | MW | 500 | 137.5 | 363 | - | - | - | - | - | 10-May-27
Commissioning & Trial Run | MW | 500 | 137.5 | 363 | - | - | - | - | - | 22-May-27

## Slide 11: 500 MW Bandha: Major Milestone – Next 3 months
Oct’26
Milestone: 100% MMS Erection to be done. Status: ~93% MMS Erection already completed, balance is in progress.
11

## Slide 12
500 MW Bandha: Manpower Deployment Plan vs Actual
12
Chart: 
| Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27
Piling | 0 | 8 | 125.1333 | 206.0968 | 55.8333 | 32.5333 | 21.1852 | 32.6333 | 8.7333 | 5
MMS+Robot | 0 | 0 | 0 | 48.9032 | 150.3333 | 144.3 | 93.069 | 88.1 | 132.5484 | 131 | 120 | 19 | 19 | 133.7037 | 44 | 139.7491 | 15 | 30 | 23 | 9 | 9 | 5 | 5 | 30 | 30 | 10 | 5
Module | 0 | 0 | 0 | 0 | 0 | 0 | 93.069 | 46 | 91.0323 | 74 | 92 | 33 | 33 | 0 | 29 | 0 | 14 | 0 | 11 | 0 | 5 | 0 | 0 | 70 | 270 | 270 | 70
IDT Area | 0 | 0 | 17.8148 | 53.4194 | 68.9333 | 63.3 | 18.7857 | 12.3448 | 14.7097 | 16 | 19 | 4 | 4 | 10 | 9 | 10 | 4 | 10 | 7 | 10 | 2 | 10
AC DC | 0 | 0 | 19.3 | 62.0645 | 58.3667 | 102.7667 | 45.3929 | 46.8667 | 50.0323 | 67 | 88 | 34 | 34 | 20 | 24 | 20 | 42 | 80 | 32 | 25 | 19 | 20 | 20 | 80 | 100 | 100 | 80
Total Planned | 90 | 163.7037 | 169.7491 | 120 | 44 | 35 | 25 | 180 | 400 | 380 | 155 | 0
Total Actual | 0 | 8 | 162 | 370 | 333 | 343 | 272 | 226 | 297 | 293 | 319 | 90 | 106 | 75 | 73 | 35
Total Forecast | 50 | 30 | 121.7563 | 405.914 | 410.3226 | 340.5 | 110

## Slide 13: NHPC BOO 600 MW Baiya Solar Project
13

## Slide 14: 600 MW Baiya: Salient Project Features
Project | NHPC BOO – Baiya
Project Scope/ Capacity | 600 MW (816 MWdc)
Owner/ Developer | Adani Solar Energy Barmer One Private Limited
Location | Village – Baiya, Tehsil – Fatehgarh, Dist. Jaisalmer, Rajasthan
Concessionaire, If applicable | -
EPC, If applicable | NA
Land Area | 2290 Acre
Approved Budget (INR Cr.) (date: 23-Jul-24) | INR 2773 Cr
Revised Budget (INR Cr.) | NA
Project Start Date | 11-Aug-23
Schedule COD | 09-Mar-22. Extension received up to 31-Mar-26 for 320 MW (MP) & 30-Jun-26 for 280 MW (J&K)
Revised COD, if any | 320 MW PPA (M&P): 31-Mar-26 (LD as per PPA shall be apply to any capacity commissioned between 31-Mar-26 to 30-Sep-26) 280 MW PPA (J&K): SCD 30-Jun-26.
Expected COD | 16-Mar-27 (251 MW Commissioned in Mar’26, 139 MW by Dec’26, 90 MW by Jan’27 & 120 MW by Mar’27)
Other Comments | 
14

## Slide 15: 600 MW Baiya: Project Plot Plan
Description | Baiya | 
Type of MMS | No. of Blocks | MW
Fixed Tilt | 51 | 600
Total | 51 | 600
Type of Land | Acres
Govt. | 2133.43
Pvt. | 156.9
Total | 2290.33
15

## Slide 16: 600 MW Baiya: Overall S Curve
Gap Analysis |  |  |  |  | 
Progress Parameter | Weightage | Cumm. Plan | Cumm. Actual | Variance | Remarks for Variance
Land & Statutory | 7% | 100% | 99% | 1% | 
Engineering+ System Study | 13% | 100% | 100% | 0% | 
Procurement | 30% | 100% | 100% | 0% | 
Construction | 50% | 65% | 59% | 2% | Delayed on account of unavailability of bush cutting permission
Overall | 100% | 83% | 79% | 2% | 
16
Chart: Baiya_600 MW
| Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Overall Plan | 0.0036046 | 0.0055136 | 0.010886 | 0.012584 | 0.025926 | 0.012262 | 0.00431 | 0.0049896 | 0.0072885 | 0.0075582 | 0.01066 | 0.0058006 | 0.011343 | 0.0061429 | 0.016522 | 0.012706 | 0.0085437 | 0.019675 | 0.03389 | 0.027779 | 0.054877 | 0.043664 | 0.045575 | 0.036579 | 0.046563 | 0.04685 | 0.028531 | 0.038123 | 0.036765 | 0.040115 | 0.049693 | 0.058269 | 0.011631 | 0.0079485 | 0.0093301 | 0.003872 | 0.020707 | 0.036179 | 0.03721 | 0.028932 | 0.038694 | 0.018449
Overall Actual | 0.0036046 | 0.0055136 | 0.010886 | 0.012584 | 0.025926 | 0.012262 | 0.00431 | 0.0049896 | 0.0072885 | 0.0075582 | 0.01066 | 0.0058006 | 0.011343 | 0.0061429 | 0.016522 | 0.012706 | 0.0085437 | 0.019675 | 0.03389 | 0.027779 | 0.054877 | 0.043664 | 0.045575 | 0.036579 | 0.046563 | 0.04685 | 0.028531 | 0.038123 | 0.036765 | 0.040115 | 0.049693 | 0.058269 | 0.011631 | 0.0050554 | 5.4609e-05 | 0.0040499 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A
Engineering Plan
Engineering Actual
Procurement Plan
Procurement Actual
Construction Plan
Construction Actual
Land Plan
Land Actual
Overall Cummulative Plan | 0.0036046 | 0.0091182 | 0.020004 | 0.032588 | 0.058514 | 0.070776 | 0.075086 | 0.080075 | 0.087364 | 0.094922 | 0.10558 | 0.11138 | 0.12273 | 0.12887 | 0.14539 | 0.1581 | 0.16664 | 0.18631 | 0.2202 | 0.24798 | 0.30286 | 0.34652 | 0.3921 | 0.42868 | 0.47524 | 0.52209 | 0.55062 | 0.58875 | 0.62551 | 0.66563 | 0.71532 | 0.77359 | 0.78522 | 0.79317 | 0.8025 | 0.80637 | 0.82708 | 0.86326 | 0.90047 | 0.9294 | 0.96809 | 1
Overall Cummulative Actual | 0.0036046 | 0.0091182 | 0.020004 | 0.032588 | 0.058514 | 0.070776 | 0.075086 | 0.080075 | 0.087364 | 0.094922 | 0.10558 | 0.11138 | 0.12273 | 0.12887 | 0.14539 | 0.1581 | 0.16664 | 0.18631 | 0.2202 | 0.24798 | 0.30286 | 0.34652 | 0.3921 | 0.42868 | 0.47524 | 0.52209 | 0.55062 | 0.58875 | 0.62551 | 0.66563 | 0.71532 | 0.77359 | 0.78522 | 0.79027 | 0.79053 | 0.79418 | 0.79418 | #N/A | #N/A | #N/A | #N/A | #N/A

## Slide 17
600 MW Baiya: Engineering Progress
Sr. No | Description | No. of Drawings | %
A (B+C) | Total | 468 | 
B (RFC+b1+b2+b3) | Approved | 468 | 100%
RFC | RFC | 329 | 
b1 | A1-Category | 115 | 
b2 | A2-Category | 3 | 
b3 | I-Category | 21 | 
C | Pending | 0 | 
A1-Category: Approved
A2-Category: Approved with Comments
I-Category: Information
17

## Slide 18: 600 MW Baiya: Procurement & 3 month rolling plan for Supply Status
S.No. | Packages | UOM | Scope | Ordering Completed | Balance Ordering | Delivered at Site up to Aug’26 | Forecast delivery schedule |  | 
 |  |  |  |  |  |  | Sep-26 | Oct-26 | Nov-26
1 | Module | MWp | 816 | 816 | - | 816 | - | - | -
2 | MMS - FT | MW | 600 | 600 | - | 600 | - | - | -
3 | IDT | Nos. | 52 | 52 | - | 52 | - | - | -
4 | Inverter | Nos. | 2142 | 2142 | - | 2142 | - | - | -
5 | HT Panel | Nos. | 51 | 51 | - | 51 | - | - | -
6 | LT Panel | Nos. | 816 | 816 | - | 816 | - | - | -
7 | HT Cable | km | 255 | 255 | - | 255 | - | - | -
8 | LT Cable | km | 729 | 729 | - | 729 | - | - | -
9 | Control Cable | km | 25 | 25 | - | 25 | - | - | -
10 | DC Cable | km | 4808 | 4808 | - | 4808 | - | - | -
11 | Robotic Module Cleaning System | Nos. | 2268 | 2268 | - | 2268 | - | - | -
18

## Slide 19: 600 MW Baiya: Construction Progress Update
19
Description | UOM | Scope | Completed upto Aug’26 | Balance as on Aug’26 | For the Month Aug'26 |  | Next 3 Month Rolling Plan |  |  | Completion Target
 |  |  |  |  | Plan | Actual | Sep-26 | Oct-26 | Nov-26 | 
Piling | Nos | 3,01,798 | 1,79,613 | 1,22,185 | - | - | 5,507 | 38,564 | 27,545 | 10-Feb-27
MMS - FT | Tables | 24,582 | 13,232 | 11,350 | - | - | 170 | 2,485 | 2,174 | 20-Feb-27
IDT Foundation | Blocks | 52 | 45 | 7 | - | - | 2 | 4 |  | 24-Oct-26
HT & LT Slab | Blocks | 52 | 44 | 8 | - | - | 2 | 5 |  | 24-Oct-26
HT & LT Canopy | Blocks | 52 | 38 | 14 | - | - | 7 | 6 | 1 | 24-Nov-26
IDT Erection | Blocks | 52 | 37 | 15 | - | - | 7 | 5 | 2 | 18-Nov-26
HT Panel Erection | Blocks | 52 | 33 | 19 | - | - | 10 | 1 | 7 | 25-Nov-26
LT Panel Erection | Nos. | 832 | 500 | 332 | 148 | - | 188 | 8 | 120 | 30-Nov-26
Inverter Erection | Nos. | 2,130 | 1,262 | 868 | - | - | 3 | 220 | 100 | 28-Jan-27
LT Cabling Works | Kms | 521 | 303 | 218 | - | - |  | 80 | 36 | 28-Jan-27
HT Cabling Works | Kms | 231 | 207 | 24 | - | - | 5 | 7 |  | 26-Oct-26
Module [Erection] | MWdc | 834 | 409 | 425 | - | - | 1 | 66 | 76 | 03-Mar-27
MC4 & VOC | MWdc | 834 | 372 | 462 | - | - | - | - |  | 04-Mar-27
CEA Inspection & Approval | MW | 600 | 251 | 349 | - | - | - | - |  | 05-Mar-27
Commissioning & Trial Run | MW | 600 | 251 | 349 | - | - | - | - |  | 23-Mar-27

## Slide 20: 600 MW Baiya: Major Milestone – Next 3 months
20
Oct’26
Milestone: Start of Piling work for Phase-III (90 MW) & Phase-IV (120 MW). Status: Bush cutting permission required to progress further work. Hearing on 20-Aug-26 conducted, next hearing is scheduled on 18-Sep-26.

## Slide 21
600 MW Baiya: Manpower Deployment Plan vs Actual
21
Chart: 
| Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Piling | 0 | 24 | 201 | 126.4839 | 7.9 | 2.5 | 6.9091 | 7.4667 | 6 | 1 | 1 | 1 | 0 | 0 | 57 | 1 | 57 | 3 | 57 | 1 | 57 | 0 | 57 | 0 | 57 | 0 | 55 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MMS+Robot | 0 | 0 | 45 | 154.6774 | 237.6 | 136.4 | 142.6667 | 82.7419 | 36 | 41 | 18 | 18 | 30 | 1 | 125 | 6 | 139 | 0 | 139 | 1 | 139 | 0 | 139 | 0 | 139 | 0 | 139 | 0 | 139 | 0 | 69 | 0 | 0 | 0 | 0 | 0
Module | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 399 | 89 | 89 | 0 | 82 | 0 | 28 | 0 | 1 | 97 | 1 | 97 | 0 | 97 | 0 | 97 | 0 | 97 | 0 | 97 | 0 | 97 | 0 | 0 | 0 | 0 | 0
IDT Area | 0 | 6 | 53.125 | 87.8333 | 62.3667 | 33.25 | 34.3448 | 23.76 | 11 | 16 | 1 | 1 | 35 | 1 | 7 | 1 | 43 | 6 | 43 | 3 | 45 | 0 | 45 | 0 | 23 | 0 | 14 | 0 | 2 | 0 | 0 | 0 | 18 | 0 | 10 | 0
AC DC | 0 | 0 | 14.25 | 43.7097 | 95.6333 | 85.2069 | 71.4667 | 55.8065 | 54 | 99 | 25 | 25 | 60 | 7 | 12 | 17 | 54 | 5 | 69 | 5 | 128 | 2 | 128 | 0 | 101 | 0 | 94 | 0 | 64 | 0 | 56 | 0 | 35 | 0 | 25 | 0
Total Planned | 134 | 125 | 201 | 293 | 405 | 466 | 466 | 417 | 399 | 357 | 222 | 53 | 35
Total Actual | 0 | 30 | 313 | 413 | 404 | 257 | 255 | 170 | 149 | 556 | 134 | 91 | 53 | 15 | 11
Total Forecast | 192.5714 | 402.1111 | 453.3226 | 513 | 433.0645 | 235.0258 | 153 | 35

## Slide 22: Thank You