1. Executive Leadership Dashboard (CEO, CXO, CDO)

This dashboard provides a high-level strategic overview of the entire portfolio, focusing on financial health, major risks, and overall progress.

| Source Document | KPI |
| --- | --- |
| Projects | MW at Risk of Delay (Next 30/60/90 Days) |
| Projects | Capex Overrun (%) vs Approved NFA (Project Level) |
| Projects | Working Capital Locked in Projects (₹ & Days) |
| TC | TC (ordering) budget vs actual |
| Projects | Project progress (Actual vs plan) - Time vs physical (Aggregated View) |
| Projects | Actual time vs plan for Wind Specific KPIs (Aggregated View) |
| Projects | Critical statutory approvals completion (%) |
| TC | Inventory Turnover rate - as per ABC |

2. PMAG Dashboard

This dashboard is for governance and cross-functional oversight, helping to identify risks, ensure compliance, and monitor project health across the portfolio.

| Source Document | KPI |
| --- | --- |
| Projects | MW at Risk of Delay (Next 30/60/90 Days) |
| Projects | QA NC count and ageing by site/ contractors |
| Projects | RFI/NC count and ageing by site/ contractors (Critical to commission/ non-critical) |
| Projects | Critical statutory approvals completion (%) |
| Projects | Count of Issues in issue register - weather, financial, land... |
| Projects | Resource augmentation requirement (MMM) vs availability as per schedule |
| TC | Procurement Progress Percentage (Plan% Vs Actual %) |
| TC | PR/SR/NFA to PO/SO cycle time - actual versus SLA |
| TC | Count of PO amendments |
| Projects | Ageing of overdue vendor invoices vs contract terms |
| Projects | Count of Contracts Adhered to policy - Pulse |

3. Projects Team Dashboard (Solar & Wind)

This dashboard is focused on execution, providing a detailed, real-time view of construction progress, material readiness, and on-site issue management.

| Source Document | KPI |
| --- | --- |
| Projects | Project progress (Actual vs plan) - Time vs physical (with sub-KPIs for piling, MMS, modules, inverters) |
| Projects | PSS progress tracking (% completed) - milestone based monitoring |
| Projects | Progress tracking of Transmission line CKM - solar |
| Projects | Actual time vs plan for Wind Specific KPIs (with sub-KPIs for WTG Foundation, Erection, etc.) |
| Projects | WTG Material Set Readiness |
| Projects | WTG main component supply status (%) (TC and Project) |
| Projects | Count of Issues in issue register - weather, financial, land... |
| Projects | Avg Ageing of Open Punch Points - Critical to commission/ non-critical |
| Projects | Plan vs Actual - Machinery productivity (eg, crane) |
| Projects | Material reconciliation and theft details |
| Projects | Robotic Module Cleaning system (Nos) |

4. Techno-Commercial (Ordering) Dashboard

This dashboard provides visibility into the procurement lifecycle, from requisition and ordering to cost control and vendor performance.

| Source Document | KPI |
| --- | --- |
| TC | Procurement Progress Percentage (Plan% Vs Actual %) |
| TC | PR/SR/NFA to PO/SO cycle time - actual versus SLA |
| TC | TAT for PR/NFA - PO - GRN - invoicing |
| TC | Order completion rate |
| TC | Order status (Supply/ Service) + payment status |
| TC | % Emergency PR, PO, SO, NFA |
| TC | TC (ordering) budget vs actual |
| TC | TC (ordering) internal estimate (IE) vs actual |
| TC | Historical Pricing of materials across vendors |
| TC | Vendor/SO performance evaluation report |
| TC | Count of PO amendments |
| TC | PO Automation/STP Rate |

5. Techno-Commercial (Stores) Dashboard

This dashboard focuses on inventory management, material availability at the site, and the efficiency of the stores function.

| Source Document | KPI |
| --- | --- |
| TC | Inventory Turnover rate - as per ABC |
| TC | Inventory stockout rate |
| TC | Inventory Ageing |
| TC | GE to GRN Ageing |
| TC | Ageing and Value of materials issued to contractors |
| TC | Return rate of materials - Vendors |
| TC | Average Milestone Delay Due to Stores (days) |
| TC | Scrap as % of Inventory Value |
| TC | Total Inventory - Wind, solar, BESS, H2, etc - plant-wise |
| TC | Inventory Analysis (VED, FSN and ABC) |
| TC | Inventory optimisation (Min, max stock label. Reorder label) |
| TC | Emergency / Spot Procurement Cost % |