KPI Reference Document

Version 2.0  |  Confidential

This document outlines the Key Performance Indicators (KPIs) required for the solution, along with their business definitions, calculation logic, and underlying data sources. It is intended to serve as a functional reference for design, development, and validation activities.

1. Portfolio-Level KPIs

| KPI Name | Business Definition | Calculation Logic | Data Source(s) |
| --- | --- | --- | --- |
| Total Projects | Total number of active projects being tracked in the portfolio | Count of all active projects in Oracle P6 project master | PMAG Master Sheet / Oracle P6 |
| Portfolio Capacity | Total installed or planned energy capacity across all projects (in MW) | Sum of MW capacity for all projects in the portfolio. For Solar, capacity is extracted through the P6 project name. For Wind, capacity is calculated based on the weightage of Wind P6 projects. | Oracle P6 / PMAG Master Sheet |
| Delayed Projects | Number of projects that are behind schedule compared to baseline | Variance = Baseline Project Finish Date − COD Date (final one). For split projects (e.g., 425 MW + 75 MW), the COD of the final phase/project is considered. | Oracle P6 |
| Remaining PO Value | Remaining Supply (Modules) PO value for project execution | Total Supply PO Amount − Still to be Delivered Value (from ME2J). Line-item-level information to be captured through ME2N integration. | SAP (MB52, ME2N, ME2J) |
| Portfolio Progress | Cumulative progress across all projects at the portfolio level (e.g., FY26–27) | Weighted Average of project progress across the portfolio. | Oracle P6 |
| Project Progress (%) | Execution progress of an individual project | Progress (%) = Actual Non-Labour Units / Budgeted Non-Labour Units | Oracle P6 |
| Total PO Value | Total financial commitment made through purchase orders across all projects | Sum of all PO values (from SAP ME2J or equivalent source). Currency conversion in ME2J to be based on the INR exchange rate at the time the PO was raised. | SAP (ME2J) |
| Completed Projects | Number of projects that have reached full completion (COD achieved) | Count of projects where progress = 100% or status = completed | Oracle P6 |
| Critical Path | Sequence of activities that directly drive the project's Commercial Operation Date (COD) | Critical path derived based on the project COD. | Oracle P6 |
| At Completion Scope | Final projected scope considering completed and remaining work | At Completion Scope = Actual + Remaining. Value may be greater than or less than the approved budget. | Oracle P6 |
| Service Order | Financial tracking of service orders (in addition to supply orders) | Capture Total Budget, Committed Value, and Actualized Value (GRN + Service Entry) for service orders. | SAP |
| Schedule Variance | Deviation of project completion date from the approved baseline schedule | Schedule Variance = Forecast Finish Date − Baseline Project Finish Date | Oracle P6 |
| COD Tracking | Commercial Operation Date of the project | COD to be derived directly from activity dates only. | Oracle P6 |

KPIs Removed from Section 1: Average SPI, Average Progress (old logic — replaced with Portfolio Progress & Project Progress), Risk, Complexity.

2. Project-Level KPIs

| KPI | Source | Definition |
| --- | --- | --- |
| Progress (%) | Oracle P6 | Overall physical or duration-based completion percentage of the project. Sourced from Summary Duration Percent Complete in P6. |
| SAP PO Budget (₹ Cr) | SAP | Total value of all Purchase Orders issued for the project, shown in Crores. Sourced from SAP ME2J. Reflects total financial commitment to vendors. |
| Schedule Variance (Days) | Oracle P6 | Difference between the planned finish date and the current forecasted finish date. A negative value (e.g., –76 days) indicates the project is behind schedule. Sourced from P6 Summary Finish Date Variance. |
| Forecast COD | Oracle P6 | Expected Commercial Operations Date — when the project is forecast to begin generating power. Sourced from P6 Scheduled Finish Date. |
| Transmission Lines | Transmission | Total number of transmission line segments connected to the project. Should be hidden when no transmission data exists. |
| Substations | Transmission | Number of substation nodes associated with the project. Should only appear when relevant data is mapped. |
| Delayed Activities | Oracle P6 | Number of critical tasks currently behind their baseline schedule. Should support drill-down to list each delayed activity by name. |

3. Capacity KPIs

| KPI Name | Business Definition | Calculation Logic | Data Source(s) |
| --- | --- | --- | --- |
| Total Capacity (MW) | Total energy capacity across all projects in the portfolio | SUM(Project_Capacity_MW) | Oracle P6 |
| COD Done (MW) | Total capacity of projects that have achieved Commercial Operations Date (COD) | SUM(Project_Capacity_MW WHERE Status = 'Completed' OR COD_Date IS NOT NULL) | Oracle P6 |
| Trial Run Only (MW) | Capacity of projects currently in trial run stage (not fully commissioned) | SUM(Project_Capacity_MW WHERE Status = 'Trial Run') | Oracle P6 |
| Solar Portfolio (MW) | Total capacity of solar-based projects in the portfolio | SUM(Project_Capacity_MW WHERE Energy_Type = 'Solar') | Oracle P6 |
| Wind Portfolio (MW) | Total capacity of wind-based projects in the portfolio | SUM(Project_Capacity_MW WHERE Energy_Type = 'Wind') | Oracle P6 |
| Capacity by Region | Capacity distribution across regions | SUM(Project_Capacity_MW) GROUP BY Region | Oracle P6 |
| Active Capacity (MW) | Capacity of projects currently under execution (excluding completed & planning) | SUM(Project_Capacity_MW WHERE Status = 'Active') | Oracle P6 |
| Pipeline Capacity (MW) | Capacity of projects in planning or not yet started stage | SUM(Project_Capacity_MW WHERE Status IN ('Planned','Not Started')) | Oracle P6 |

4. Data Integration & Sync KPIs

| KPI Name | Business Definition | Calculation Logic | Data Source(s) |
| --- | --- | --- | --- |
| P6–SAP Mapping Coverage (%) | Percentage of projects successfully mapped between Oracle P6 and SAP | (Mapped_Projects / Total_P6_Projects) × 100 | Mapping Layer |
| Unmapped Projects | Projects available in Oracle P6 but not mapped to SAP | COUNT(Project_ID WHERE SAP_ID IS NULL) | Oracle P6 + Mapping Layer |
| Data Sync Status | Status of latest synchronization between systems | Latest Sync_Status (Success / Failed / Pending) | Integration Logs |
| Last Sync Timestamp | Most recent data refresh timestamp | MAX(Sync_Timestamp) | Integration Logs |
| Sync Failures Count | Number of failed synchronization attempts | COUNT(Sync_ID WHERE Status = 'Failed') | Integration Logs |
| Data Freshness (Hours) | Time lag between source system and consuming layer | Current_Time − Last_Sync_Timestamp | Integration Logs |
| Project Data Completeness (%) | Completeness of required fields across integrated systems | (No. of populated mandatory fields / Total mandatory fields) × 100 | Oracle P6 + SAP + Mapping Layer |
| Manual Sync Trigger Count | Number of manual sync actions triggered by users | COUNT(User_Triggered_Sync) | Integration Logs |

5. SAP Data Overview KPIs (Module-Level)

| KPI Name | Calculation Logic | Module Granularity | SAP Source Report(s) | Notes |
| --- | --- | --- | --- | --- |
| PO Volume | COUNT(distinct Purchase Order number) WHERE PO is created for a module, extracted from ME2J. Counts total number of module purchase orders created in the selected period/project. | Module / Project / WBS | ME2J | Counts PO header records, not PO line items; verify deduplication if a PO has multiple line items for the same module. |
| Inventory | SUM(Stock Quantity) WHERE Material = Module, extracted from MB52. Reflects total number of modules currently available in stock as of the latest stock snapshot. | Module / Plant / Storage Location | MB52 | Point-in-time snapshot; value changes with each goods movement posted in MB51. |
| Total Supply PO Amount | SUM(PO Line Net Value) WHERE PO Category = Supply PO AND Material = Module, extracted from ME2J. Represents total value of modules ordered through supply purchase orders. | Module / Project / WBS | ME2J | Net PO value before tax; confirm currency is standardized (e.g., converted to USD/INR) before aggregation. |
| Utilized Supply PO Amount | SUM(Goods Issue Value) WHERE Movement Type = Consumption AND Material = Module, extracted from MB51. Represents total value of modules consumed/used in project execution. | Module / Project / WBS | MB51 | Only goods issue movements tied to consumption movement types should be included; goods receipts and returns must be excluded. |
| Total SAP Budget | Equivalent to [Total Supply PO Amount]. Applicable only for modules — i.e., Total SAP Budget = SUM(PO Line Net Value) WHERE PO Category = Supply PO AND Material = Module, extracted from ME2J. | Module / Project / WBS | ME2J | This KPI is not an independently sourced budget figure — it mirrors Total Supply PO Amount by definition. Do not double-count in budget vs. actual comparisons. |

General Notes

All module-level metrics should be calculated at module level and rolled up to Project/WBS as needed for display.

Data refresh frequency, owner, and exact extraction schedule for MB51/MB52/ME2J should be confirmed with the SAP BASIS/Data team.

Currency and unit-of-measure standardization should be applied uniformly across PO Volume, Total Supply PO Amount, Utilized Supply PO Amount, and Total SAP Budget for consistent reporting.

New Rule (v2.0): All ME2J currency values must be converted to INR using the exchange rate applicable at the time the PO was raised.