## Slide 1
CPAG – Energy Cluster
Adani Green Energy Ltd
Aug-26

## Slide 2
Agenda
Executive Summary
Project Wise Update
Khavda Solar Ph – IV
            Project Information & Salient Features
            Progress Update
            Major Milestone- Next 3 Months
              Major Critical Issues
              System Study & PSS Progress Update

## Slide 3
Executive Summary
SN | Location | Project Name | FY 27 Plan (MW) | Planned till Aug’26 (MW) | Actual till Aug’26 (MW) | COD |  | Overall Project Progress |  | Remarks
 |  |  |  |  |  | Plan | Expected | Plan | Actual | 
1 | GJ | Khavda-Solar | 4,639 | 1,492 | 917 | 31-Mar-27 | 31-Mar-27 | 67% | 50% | Due to manpower constraint

## Slide 4
Commissioning: Plan vs. Forecast – Khavda Phase - IV
All nos. are in MW
COD |  | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Total
BUDGET | Solar | 492 | 325 | 400 | 275 |  |  |  |  | 250 | 1,509 | 863 | 525 | 4,639
ACTUAL / FCST | Solar | 342 | 325 | 150 |  | 100 | 150 | 113 | 313 | 50 | 1,500 | 947 | 650 | 4,639
All the figures are revised as per Revised AOP plan
Chart: 
| Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Budget | 492 | 325 | 400 | 275 | 250 | 1509 | 863 | 525
Actual / Fcst | 342 | 325 | 150 | 100 | 150 | 113 | 313 | 50 | 1500 | 947 | 650

## Slide 5
Khavda Solar

## Slide 6
Khavda Solar - Salient Features
Project | Khavda Phase-IV Solar Projects |  |  |  | 
Project Scope / Capacity | 4,639 MW |  |  |  | 
Owner/ Developer | Various SPV under AGEL and Group Project |  |  |  | 
Location | Khavda, Bhuj, Kutchh |  |  |  | 
Land Area | AGEL – 19000 Ha, SRPL – 9500 Ha |  |  |  | 
Project Commissioning | Progressively up to 31-Mar-27 |  |  |  | 
Project Configuration | Module | Inverter | Over Loading | MMS - Pitch | 
Parameters | 580 ~ 610 Wp | 275 ~ 300 kW | 1.32 ~ 1.5 | HSAT – 5.5m FT – 7.5m | 
Commissioning (FY 26-27) | Q1 | Q2 | Q3 | Q4 | Total
Original Budget Plan (MW) | 1,217 | 275 | 250 | 2,897 | 4,639
Actual / Expected (MW) | 817 | 100 / 250 | 475 | 3,097 | 4,639

## Slide 7
Khavda Phase-IV: Solar Plot wise Development
`
Project | AGEL / EPC | Plot | Budgeted Capacity (MW) | Commissioned (MW)
FY26 Carry forward | AGEL / KPI | A15a | 50 | 50
FY26 Carry forward | AGEL | S05a | 50 | 50
FY26 Carry forward | AGEL | A16b | 50 | 50
FY26 Carry forward | AGEL | A16c | 67 | 67
FY26 Carry forward | AGEL | A16d | 175 | 175
FY26 Carry forward | AGEL | A06 | 150 | 150
FY27 Project | Bondada | A01c | 25 | 25
FY27 Project | Bondada | A01d | 25 | 25
FY27 Project | Bondada | A01e | 25 | 25
FY27 Project | AGEL | A12 | 350 | 100
FY27 Project | Amaraja | A01 | 50 | 50
FY27 Project | S&W | A15b | 50 | 
FY27 Project | Amaraja | A02 | 150 | 150
FY27 Project | Amaraja | A01 | 150 | 
FY27 Project | Amaraja | A02 | 125 | 
FY27 Project | Bondada | A03 | 250 | 
FY27 Project | HILD | A03 | 250 | 
FY27 Project | Enrich | S07 | 300 | 
FY27 Project | KPI Green | S07 | 300 | 
FY27 Project | S&W | S09 | 400 | 
FY27 Project | AGEL | NHPC | 50 | 
FY27 Project | L&T | S02a | 175 | 
FY27 Project | KPI Green | S06a | 234 | 
FY27 Project | L&T | S01 | 100 | 
FY27 Project | L&T | S02a | 50 | 
FY27 Project | L&T | S01 | 200 | 
FY27 Project | S&W | A18 | 600 | 
FY27 Project | L&T | S02b | 112.5 | 
FY27 Project | L&T | S01 | 75 | 
FY27 Project | TBD | S10 | 50 | 
 |  |  | 4,639 | 917

## Slide 8: Khavda Solar - Physical Progress: S Curve
Gap Analysis |  |  |  |  | 
Progress Parameter | Weightage | Cumm. Plan | Cumm. Actual | Variance | Remarks for Variance
Engineering | 15% | 15% | 14% | 1% | 
Procurement | 30% | 25% | 20% | 5% | 
Construction | 55% | 28% | 16% | 12% | Due to manpower constraint
Total | 100% | 67% | 50% | 17% | 
Chart: Cumulative Progress (%)
| Mar-26 (Base) | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Plan | 0.34113 | 0.39481 | 0.5093 | 0.62663 | 0.65041 | 0.674 | 0.71031 | 0.79933 | 0.87672 | 0.93394 | 0.97459 | 0.98725 | 1
Actual | 0.336 | 0.37054 | 0.40038 | 0.43952 | 0.47684 | 0.50356

## Slide 9
Khavda Solar - Engineering Progress
Sr. No | Description | No. of Drawings | %
A (B+C) | Total | 4130 | 
B (RFC+b1+b2+b3) | Approved | 3251 | 79%
RFC | RFC | 613 | 
b1 | Cat. -I | 1433 | 
b2 | Cat. -II | 73 | 
b3 | Cat. -III | 12 | 
b4 | Cat. -IV | 1120 | 
C | Pending | 879 | 21%
9

## Slide 10: Khavda Solar - Procurement & Supply Status
Sr. No. | Packages | UOM | Scope | Ordering Completed | Balance Ordering | Delivered at site up to Aug-26 | 3 Month Look a Head |  | 
 |  |  |  |  |  |  | Sep-26 | Oct-26 | Nov-26
1 | Module | MWac | 4,639 | 2,317 | 2,322 | 1,542 | - | - | 576
2 | MMS | MWac | 4,639 | 4,589 | 50 | 1,542 | 200 | 683 | 492
3 | Inverter | MWac | 4,639 | 4,639 | - | 2,566 | 248 | 794 | 667
4 | IDT | Nos. | 372 | 368 | 4 | 181 | 20 | 88 | 82
5 | HT Panel | Sets | 372 | 368 | 4 | 132 | 4 | 32 | 99
6 | LT Panel | Nos. | 5,952 | 5,888 | 64 | 1,984 | - | 320 | 1,664
7 | HT Cable | MWac | 4,639 | 4,589 | 50 | 2,564 | 1,013 | 689 | 303
8 | LT Cable | MWac | 4,639 | 4,589 | 50 | 2,506 | 349 | 834 | 552
9 | DC Cable | MWac | 4,639 | 4,339 | 300 | 1,903 | 420 | 1,311 | 583
10 | Robotic Module Cleaning System | MWac | 4,639 | 2,530 | 2,109 | 1,492 | 125 | 300 | 1,063

## Slide 11: Khavda Solar - Construction Progress Update – Phase – IV (4,639 MW)
Sr. No. | Description | UOM | Scope | Completed up to Aug’26 | Balance | For the Month Aug’26 |  | Next 3 Month Rolling Plan |  |  | Completion Target
 |  |  |  |  |  | Plan | Actual | Sep’26 | Oct’26 | Nov’26 | 
1 | Piling | Nos | 1574829 | 959277 | 615,552 | 62,263 | 13,321 | 219,831 | 266,296 | 114,493 | 20-Jan-27
2 | Tracker up to Torque Tube | Tables | 119907 | 34590 | 85,317 | 12,296 | 3,986 | 14,821 | 22,720 | 19,843 | 30-Jan-27
3 | Tracker up to Transmission Shaft with Purlin | Tables | 119907 | 28287 | 91,620 | 11,925 | 820 | 13,708 | 22,237 | 19,054 | 30-Jan-27
4 | Module erection | MWdc | 6272 | 1188 | 5,084 | 412 | 203 | 349 | 3,692 | 3,826 | 20-Feb-27
5 | Transformer foundation up to rail | Nos | 372 | 241 | 131 | 27 |  | 52 | 60 | 20 | 23-Jan-27
6 | HT/LT Slab | Nos | 372 | 229 | 143 | 28 | 16 | 54 | 65 | 20 | 17-Jan-27
7 | HT LT Panel Shed & Sheeting | Nos | 372 | 103 | 269 | 17 | 0 | 46 | 91 | 60 | 19-Jan-27
8 | Transformer foundation Completion | Nos | 372 | 173 | 199 | 22 | 4 | 24 | 83 | 63 | 23-Jan-27
9 | IDT Erection | Nos | 372 | 103 | 269 | 14 |  | 25 | 79 | 92 | 06-Feb-27
10 | HT Panel Erection | Nos | 372 | 82 | 290 | 16 |  | 29 | 58 | 89 | 28-Jan-27
11 | LT Panel Erection | Nos | 5952 | 1144 | 4,808 | 528 | 128 | 620 | 622 | 1,062 | 04-Feb-27
12 | Inverter erection | Nos | 14066 | 3669 | 10,397 | 478 | 162 | 556 | 1,470 | 4,221 | 09-Feb-27
13 | LT Cable Laying | Km | 4421 | 1180 | 3,241 | 252 | 67 | 331 | 545 | 731 | 25-Jan-27
14 | HT Cable Laying | Km | 1686 | 655 | 1,031 | 71 | 0 | 158 | 410 | 245 | 07-Feb-27
15 | DC Cable | Kms | 35648 | 7708 | 27,940 | 2,729 | 917 | 2,369 | 5,159 | 6,024 | 19-Feb-27
16 | MC4 & VOC testing | MWac | 4639 | 733 | 3,907 | 221 | 12 | 305 | 205 | 325 | 26-Feb-27
17 | Robots Module Cleaning | MWac | 4639 | 758 | 3,881 | 237 |  | 309 | 260 | 320 | 10-Mar-27

## Slide 12: Khavda Solar - Construction Manpower – Phase – IV (4,639 MW)
Sr. No. | Description | UOM | Scope | Completed up to Aug’26 | Balance | Next 3 Month Manpower Requirement |  | 
 |  |  |  |  |  | Sep’26 | Oct’26 | Nov’26
1 | Piling | Nos | 1,574,829 | 959,277 | 615,552 | 735 | 697 | 403
2 | Tracker up to Torque Tube | Tables | 119,907 | 34,590 | 85,317 | 1,771 | 2,440 | 2,413
3 | Module erection | MWdc | 6,272 | 1,188 | 5,084 | 882 | 1,042 | 1,538
4 | Transformer foundation up to rail | Nos | 372 | 241 | 131 | 339 | 482 | 311
5 | HT/LT Slab | Nos | 372 | 229 | 143 | 257 | 186 | 91
6 | HT LT Panel Shed & Sheeting | Nos | 372 | 103 | 269 | 66 | 96 | 37
7 | Transformer foundation Completion | Nos | 372 | 173 | 199 | 31 | 120 | 37
8 | IDT Erection | Nos | 372 | 103 | 269 | 159 | 327 | 494
9 | HT Panel Erection | Nos | 372 | 82 | 290 | 28 | 35 | 56
10 | LT Panel Erection | Nos | 5,952 | 1,144 | 4,808 | 170 | 21 | 51
11 | Inverter erection | Nos | 14,066 | 3,669 | 10,397 | 72 | 44 | 98
12 | LT Cable Laying | Km | 4,421 | 1,180 | 3,241 | 184 | 223 | 120
13 | HT Cable Laying | Km | 1,686 | 655 | 1,031 | 128 | 177 | 76
14 | DC Cable | Kms | 35,648 | 7,708 | 27,940 | 167 | 214 | 220
15 | MC4 & VOC testing | MWac | 4,639 | 733 | 3,907 | 39 | 64 | 45
16 | Robots Module Cleaning | MWac | 4,639 | 758 | 3,881 | 145 | 83 | 157
 |  |  |  |  |  | 5,172 | 6,251 | 6,148

## Slide 13
Khavda Solar - Major Critical Issues
Sr. No. | Issues | Corrective Action | Action By |  | Current Status | Support Required
 |  |  | Whom | Date |  | 
1 | Insufficient workmen causing delay in construction work | Discussion with EPC partners is on going to increases the labor forces | Projects | Ongoing | Currently Average ~2174 Manpower is available in Solar for the Month Daily meetings at site being done with partners for expediting the job | -

## Slide 14: Khavda Solar - Major Milestone – Next 3 months
Sep-26 |  | Oct-26 |  | Nov-26 | 
Charging of following plots: |  | Charging of following plots: |  | Charging of following plots: | 
Plot No | Capacity (MW) | Plot No | Capacity (MW) | Plot No | Capacity (MW)
A12 | 100 | A12 | 62.5 | A12 | 37.5
A15b | 50 | NHPC | 50 | A01 | 150
 |  |  |  | A02 | 125
Total | 150 | Total | 113 | Total | 313
 |  | PSS-07(P1) Forecast charging by 30-Sep-26 |  | PSS-14(P2) Forecast charging by 21-Oct-26. NHPC (P1) Forecast Charging by 30-Sep-26. NHPC (P2) Forecast Charging by 25-Oct-26. | 

## Slide 15
Khavda PSS Status
PSS No. | Base Line Date | Charging Date (P1) | Charging Date (P2) | Charging Date (P3)
PSS-11 | 31-Jul-25 | 03-Feb-26 | 23-May-26 | -
PSS-12 | 31-Aug-25 | 11-Mar-26 | 10-Jun-26 | -
PSS-14 | 30-Oct-25 | 24-Mar-26 | 20-Jul-26 | 21-Oct-26
PSS-07 | 15-Apr-26 | 30-Sep-26 | 30-Oct-26 | -
NHPC | 15-Jun-26 | 14-Oct-26 | 25-Oct-26 | -
PSS-18 | 30-Apr-26 | 29-Nov-26 | 22-Mar-27 | 26-Apr-27

## Slide 16: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
2) | PSS-11 -1250MW (KPS-3) (1065MW Solar + 187.2MW Wind) Connectivity Application No 230700013 [Sarjan Realties Pvt. Ltd. (SRPL)] FY 25-26 : 300 MW Solar + 187.2 MW Wind (36 / 36 nos. WTG) | Harmonic Filters Finalisation | 20-Feb-25
 |  | PSS/E Submission – | 23-Apr-25
 |  | PSCAD Submission – | 23-Apr-25
 |  | Con-4 submission- | 23-Apr-25
 |  | Initial CTU Comments : +3 weeks | 28-May-25
 |  | Addressing CTU comments & resubmission Rev-1: + 3weeks | 09-Sep-25
 |  | CTU Comments: +4 weeks | 23-Sep-25
 |  | Addressing CTU comments: +2weeks | 18-Oct-25
 |  | Initial RLDC Comments: +3 weeks | -
 |  | Addressing RLDC comments & resubmission Rev1: + 3weeks | -
 |  | RLDC Comments: +2weeks | -
 |  | Addressing RLDC comments +2weeks | -
 |  | CON-5 Approval + 1week | 06-Jan-26
 |  | CON-6 (CAT-2) Agreement +2days | 08-Jan-26
 |  | First Time Charging - Form 4 approval | 08-Jan-26

## Slide 17: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
3) | PSS-12 - 1100MW (KPS-3) (1075MW Solar + 88.4MW Wind) Connectivity Application No 0230700014 [Sarjan Realties Pvt. Ltd. (SRPL)] FY 25-26 : 300 MW Solar + 140.4 MW Wind (27 / 27 nos. WTG) | Harmonic Filters Finalisation | 20-Feb-25
 |  | PSS/E Submission – | 12-May-25
 |  | PSCAD Submission – | 12-May-25
 |  | Con-4 submission- | 12-May-25
 |  | Initial CTU Comments : +4weeks | 03-Jul-25
 |  | Addressing CTU comments & resubmission Rev-1: + 3weeks | 20-Sep-25
 |  | CTU Comments: +2weeks | 04-Oct-25
 |  | Addressing CTU comments: +2weeks | 19-Dec-25
 |  | Initial RLDC Comments: +4weeks | -
 |  | Addressing RLDC comments & resubmission Rev1: + 3weeks | -
 |  | RLDC Comments: +2weeks | -
 |  | Addressing RLDC comments +2weeks | -
 |  | CON-5 Approval + 1week | 05-Feb-26
 |  | CON-6 (CAT-2) Agreement +2days | 10-Feb-26
 |  | First Time Charging - Form 4 approval | As per plant readiness

## Slide 18: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
4) | PSS-14- 1970MW (KPS-3) (1650MW Solar + 312MW Wind) Connectivity Application No 2200000953(1530 MW), 2200000477(75 MW), 2200000786(195 MW), 2200000602 (65 MW), 2200000785 (100 MW) [Adani Green Energy Ltd. (AGEL)] FY 25-26 : 379.6 MW Wind (73 / 73 nos. WTG) | Harmonic Filters Finalisation | 27-May-25
 |  | PSS/E Submission – | 29-Aug-25
 |  | PSCAD Submission – | 29-Aug-25
 |  | Con-4 submission- | 19-Sep-25
 |  | Initial CTU Comments : +4weeks | 15-Dec-25
 |  | Addressing CTU comments & resubmission Rev-1: + 4weeks | 06-Jan-26
 |  | CTU Comments: +2weeks | 19-Mar-26
 |  | Addressing CTU comments: +2weeks | 19-Mar-26
 |  | Initial RLDC Comments: +4weeks | 03-Nov-25
 |  | Addressing RLDC comments & resubmission Rev1: + 4weeks | 08-Dec-25
 |  | RLDC Comments: +2weeks | -
 |  | Addressing RLDC comments +2weeks | -
 |  | CON-5 Approval + 1week | 20-Mar-26
 |  | CON-6 (CAT-2) Agreement +2days | 21-Mar-26
 |  | First Time Charging - Form 4 approval | As per plant readiness

## Slide 19: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
4) | PSS-7 1050MW (KPS-1) 1050MW Solar Connectivity Application No 1670426092248 [Adani Green Energy Limited (AGEL)] | Harmonic Filters Finalisation | 17-Sep-25
 |  | PSS/E Submission – | 18-Oct-25
 |  | PSCAD Submission – | 18-Oct-25
 |  | Con-4 submission- | 04-Nov-25
 |  | Initial CTU Comments : +4weeks | 04-Dec-25
 |  | Addressing CTU comments & resubmission Rev-1: + 4weeks | 28-Jan-26
 |  | CTU Comments: +2weeks | 04-Dec-25
 |  | Addressing CTU comments: +2weeks | 18-Feb-26
 |  | Initial RLDC Comments: +4weeks | -
 |  | Addressing RLDC comments & resubmission Rev1: + 4weeks | 14-Apr-26
 |  | RLDC Comments: +2weeks | -
 |  | Addressing RLDC comments +2weeks | -
 |  | CON-5 Approval + 1week | 02-Oct-26
 |  | CON-6 (CAT-2) Agreement +2days | 09-Oct-26
 |  | First Time Charging - Form 4 approval | As per plant readiness

## Slide 20: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
4) | NHPC -600MW (KPS-3) (600MW Solar) Connectivity Application No 1200002635 [ Adani Solar Energy Barmer One Private Limited] FY 25-26 : 600 MW Solar | Harmonic Filters Finalisation | 23-Jun-25
 |  | PSS/E Submission – | 30-Jul-25
 |  | PSCAD Submission – | 30-Jul-25
 |  | Con-4 submission- | 09-Oct-25
 |  | Initial CTU Comments : +4weeks | 24-Nov-25
 |  | Addressing CTU comments & resubmission Rev-1: + 4weeks | 29-Jan-26
 |  | CTU Comments: +2weeks | 08-Apr-26
 |  | Addressing CTU comments: +2weeks | 29-Apr-26
 |  | Initial RLDC Comments: +4weeks | -
 |  | Addressing RLDC comments & resubmission Rev1: + 4weeks | 29-Apr-26
 |  | RLDC Comments: +2weeks | -
 |  | Addressing RLDC comments +2weeks | -
 |  | CON-5 Approval + 1week | 09-Sep-26
 |  | CON-6 (CAT-2) Agreement +2days | 11-Sep-26
 |  | First Time Charging - Form 4 approval | As per plant readiness

## Slide 21: System Study Progress
Status for CON 4/5/6 & System Study of Renewable Projects - Khavda Location |  |  | 
Sl. No | Project | Status | 
B | Khavda Projects : FY 2025-26 |  | 
4) | PSS-18 1875MW (KPS-1 - Temporary Connection) FY 26-27 : 1000 MW Solar + 254.8MW Wind | Harmonic Filters Finalisation | 31-Aug-26
 |  | PSS/E Submission – | 30-Sep-26
 |  | PSCAD Submission – | 30-Sep-26
 |  | Con-4 submission- | 30-Sep-26
 |  | Initial CTU Comments : +4weeks | 07-Oct-26
 |  | Addressing CTU comments & resubmission Rev-1: + 4weeks | 30-Sep-26
 |  | CTU Comments: +2weeks | 07-Oct-26
 |  | Addressing CTU comments: +2weeks | 15-Oct-26
 |  | Initial RLDC Comments: +4weeks | 07-Oct-26
 |  | Addressing RLDC comments & resubmission Rev1: + 4weeks | 22-Oct-26
 |  | RLDC Comments: +2weeks | 07-Oct-26
 |  | Addressing RLDC comments +2weeks | 15-Oct-26
 |  | CON-5 Approval + 1week | 30-Oct-26
 |  | CON-6 (CAT-2) Agreement +2days | 06-Nov-26
 |  | First Time Charging - Form 4 approval | As per plant readiness

## Slide 22: Summary : PSS – 11
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
PSS-11 Priority 2 Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 46 | 06-Mar-25 | 20-Apr-25 | Lot | 1 | 1 | 0 | 27-Mar-25 | 20-May-25 | Completed
MCR Building Civil Work-Upto Slab | 43 | 27-Feb-25 | 10-Apr-25 | Lot | 1 | 1 | 0 | 08-Mar-25 | 20-Jun-25 | Completed
SGR - 01 Civil Work-Upto Slab | 38 | 14-Mar-25 | 20-Apr-25 | Lot | 1 | 1 | 0 | 16-Mar-25 | 15-Sep-25 | Completed
Power Transformer - 01 & 02 Civil Work | 87 | 31-Mar-25 | 15-May-25 | Nos | 2 | 2 | 0 | 23-Mar-25 | 05-Oct-25 | Completed
SVG Civil Work – Foundation | 55 | 07-Mar-25 | 30-Apr-25 | Nos | 7 | 7 | 0 | 19-Jun-25 | 22-Aug-25 | Completed
Harmonic Filter Civil Work – Foundation | 52 | 10-Mar-25 | 30-Apr-25 | Nos | 4 | 4 | 0 | 15-Jun-25 | 24-Jul-25 | Completed
GIS & MCR PEB Erection | 38 | 24-Apr-25 | 31-May-25 | Lot | 2 | 2 | 0 | 26-May-25 | 25-Jul-25 | Completed
SGR - 01 PEB Erection | 29 | 28-Apr-25 | 05-Jun-25 | Lot | 1 | 1 | 0 | 21-Sep-25 | 29-Dec-25 | Completed
Power Transformer – 01&02 Erection | 80 | 21-Dec-25 | 04-Feb-26 | Nos | 2 | 2 | 0 | 18-Jul-25 | 28-Feb-26 | Completed
SGR - 01 Panel Erection | 32 | 21-Jul-25 | 21-Aug-25 | Set | 4 | 4 | 0 | 30-Oct-25 | 29-Dec-25 | Completed
GIS Main Bay Area (Inside Building) – Erection | 35 | 06-Jun-25 | 10-Jul-25 | Bay | 6 | 6 | 0 | 23-Jul-25 | 19-Sep-25 | Completed
MCR Erection | 57 | 14-May-25 | 09-Jul-25 | Lot | 1 | 1 | 0 | 17-Jul-25 | 06-Oct-25 | Completed
SVG - Erection | 22 | 1-Jul-25 | 22-Jul-25 | Nos | 7 | 5 | 2 | 04-Jan-26 | 22-Mar-26 | Completed
Harmonic Filter - Erection | 30 | 16-Jun-25 | 15-Jul-25 | Nos | 4 | 4 | 0 | 10-Jun-25 | 28-Jul-25 | Completed
Gantry | 28 | 04-Jun-25 | 01-Jul-25 | Nos | 2 | 2 | 0 | 10-Jun-25 | 17-Oct-26 | Completed
Testing & ready for charging | 21 | 11-Jul-25 | 31-Jul-25 | Lot | 1 | 1 | 0 | 13-Oct-25 | 03-Feb-26(P1) 23-May-26(P2) | Completed

## Slide 23: Summary : PSS – 12
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
PSS-11 Priority 2 Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 55 | 07-Mar-25 | 30-Apr-25 | Lot | 1 | 1 | 0 | 11-Apr-25 | 24-Jun-25 | Completed
MCR Building Civil Work-Upto Slab | 48 | 01-Mar-25 | 17-Apr-25 | Lot | 1 | 1 | 0 | 12-Mar-25 | 28-Jul-25 | Completed
SGR - 02 Civil Work-Upto Slab | 46 | 16-Mar-25 | 30-Apr-25 | Lot | 1 | 1 | 0 | 04-Apr-25 | 16-Oct-25 | Completed
Power Transformer – 03&04 Civil Work | 87 | 07-Apr-25 | 22-May-25 | Nos | 2 | 2 | 0 | 31-Mar-25 | 31-Oct-25 | Completed
SVG Civil Work – Foundation | 55 | 11-Mar-25 | 04-May-25 | Nos | 7 | 7 | 0 | 10-Aug-25 | 29-Dec-25 | Completed
Harmonic Filter Civil Work – Foundation | 52 | 14-Mar-25 | 04-May-25 | Nos | 4 | 4 | 0 | 28-Jul-25 | 16-Oct-25 | Completed
Firewall-02 | 46 | 01-Apr-25 | 16-May-25 | Nos | 1 | 1 | 0 | 01-Apr-25 | 11-Oct-25 | Completed
GIS & MCR PEB Erection | 46 | 07-May-25 | 21-Jun-25 | Lot | 2 | 2 | 0 | 29-Jul-25 | 15-Dec-25 | Completed
Power Transformer – 03&04 Erection | 70 | 25-Jun-25 | 29-Jul-25 | Nos | 2 | 2 | 0 | 06-Sep-25 | 29-May-26 | Completed
GIS Main Bay Area (Inside Building) – Erection | 33 | 07-Jul-25 | 08-Aug-25 | Bays | 6 | 0 | 6 | 06-Nov-25 | 04-Dec-25 | Completed
MCR Erection | 36 | 18-Jun-25 | 23-Jul-25 | Lot | 1 | 1 | 0 | 14-Oct-25 | 28-Dec-25 | Completed
SVG | 22 | 01-Aug-25 | 22-Aug-25 | Nos | 7 | 7 | 0 | 15-Jan-26 | 06-Mar-26 | Completed
Harmonic Filter | 31 | 16-Jul-25 | 15-Aug-25 | Nos | 4 | 4 | 0 | 23-Aug-25 | 09-Jun-26 | Completed
Gantry- Erection | 21 | 03-Jun-25 | 23-Jun-25 | Nos | 2 | 2 | 0 | 05-Nov-25 | 17-Dec-25 | Completed
Testing & ready for charging | 23 | 09-Aug-25 | 31-Aug-25 | Lot | 1 | 0.5 | 0.5 | 17-Dec-25 | 11-Mar-26(P1) 10-Jun-26(P2) | Completed

## Slide 24: Summary : PSS – 14
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
PSS-14 Priority 3 Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 53 | 07-Apr-25 | 30-May-25 | Lot | 1 | 1 | 0 | 01-Jun-25 | 07-Nov-25 | Completed
MCR Building Civil Work-Upto Slab | 64 | 05-Apr-25 | 08-Jun-25 | Lot | 1 | 1 | 0 | 02-Apr-25 | 11-Oct-25 | Completed
SGR - 03 Civil Work-Upto Slab | 51 | 22-Apr-25 | 15-Jun-25 | Lot | 1 | 1 | 0 | 6-Aug-25 | 29-Apr-26 | Completed
Power Transformer – 05&06 Civil Work | 87 | 15-Sep-25 | 14-Nov-25 | Nos | 2 | 2 | 0 | 16-Jul-25 | 21-Feb-26 | Completed
SVG Civil Work (Exc. Fencing) | 55 | 29-Jul-25 | 05-Dec-25 | Nos | 7 | 7 | 0 | 25-May-26 | 14-Jul-26 | Completed
Harmonic Filter Civil Work | 52 | 01-Aug-25 | 06-Jan-26 | Nos | 4 | 0 | 4 | 10-Sep-26 | 23-Sep-26 | 
Firewall-03 | 46 | 26-Oct-25 | 10-Jan-26 | Nos | 1 | 1 | 0 | 16-Oct-25 | 29-Apr-26 | Completed
GIS & MCR PEB Erection | 80 | 06-Jun-25 | 15-Jul-25 | Lot | 2 | 2 | 0 | 03-Nov-25 | 17-Jan-26 | Completed
SGR - 03 PEB Erection | 37 | 22-Jun-25 | 26-Jul-25 | Lot | 1 | 1 | 0 | 09-May-26 | 24-Jun-26 | Completed
Power Transformer – 05&06 Erection | 70 | 16-Feb-25 | 22-Mar-25 | Nos | 2 | 2 | 0 | 31-Jan-26 | 20-Aug-26 | Completed
SGR - 03 Panel Erection | 30 | 17-dec-25 | 29-Jan-26 | Sets | 4 | 4 | 0 | 26-May-26 | 10-Sep-26 | Testing WIP
GIS Main Bay Area (Inside Building) – Erection | 45 | 01-Aug-25 | 14-Sep-25 | Bays | 10 | 10 | 0 | 28-Dec-25 | 28-Jan-26 | Completed
MCR Panel Erection | 43 | 13-Aug-25 | 24-Sep-25 | Lot | 1 | 1 | 0 | 05-Dec-25 | 10-Feb-26 | Completed
SVG | 22 | 11-Nov-25 | 01-Dec-25 | Nos | 7 | 0 | 7 | 20-Sep-26 | 10-Oct-26 | 
Harmonic Filter | 31 | 8-Dec-25 | 5-Jan-26 | Nos | 4 | 0 | 4 | 17-Sep-26 | 18-Oct-26 | 
Testing & ready for charging | 23 | 22-Mar-26 | 31-Mar-26 | Lot | 3 | 2 | 1 | 01-Mar-26 | 24-Mar-26(P1) 20-Jul-26(P2) 21-Oct-26(P3) | P1 Charged P2 Charged

## Slide 25: Summary : PSS – 07
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
PSS-07 Priority 1 Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 54 | 15-Oct-25 | 01-Dec-25 | Lot | 1 | 1 | 0 | 24-Jun-25 | 10-Feb-26 | Completed
MCR Building Civil Work-Upto Slab | 55 | 19-Oct-25 | 30-Nov-25 | Lot | 1 | 1 | 0 | 28-Mar-25 | 28-Jan-26 | Completed
SGR Civil Work-Upto Slab | 47 | 01-Oct-25 | 14-Nov-25 | Lot | 1 | 1 | 0 | 6-Apr-25 | 05-Jan-26 | Completed
Power Transformer – 03&04 Civil Work | 83 | 18-Oct-26 | 18-Nov-26 | Nos | 2 | 2 | 0 | 08-Aug-26 | 12-Mar-26 | Completed
SVG Civil Work (Exc. Fencing) | 40 | 09-Oct-25 | 09-Nov-25 | Nos | 7 | 7 | 0 | 01-Apr-26 | 17-Jun-26 | Completed
Harmonic Filter Civil Work | 42 | 05-Nov-25 | 04-Dec-25 | Nos | 4 | 4 | 0 | 16-Feb-26 | 30-May-26 | Completed
Firewall-02 | 46 | 28-Oct-25 | 12-Dec-25 | Nos | 1 | 1 | 0 | 09-Aug-25 | 05-Jun-26 | Completed
GIS & MCR PEB Erection | 80 | 04-Dec-25 | 07-Jan-26 | Lot | 2 | 2 | 0 | 09-Feb-26 | 30-Jun-26 | Completed
SGR - 02 PEB Erection | 37 | 21-Nov-25 | 06-Jan-26 | Lot | 1 | 1 | 0 | 02-Feb-26 | 23-May-26 | Completed
Power Transformer – 03&04 Erection | 80 | 29-Jan-26 | 11-Mar-26 | Nos | 2 | 2 | 0 | 10-Feb-26 | 21-Aug-26 | 
SGR - 02 Panel Erection | 36 | 2-Jan-26 | 06-Feb-26 | Sets | 4 | 4 | 0 | 09-Apr-26 | 12-Aug-26 | Completed
GIS Main Bay Area (Inside Building) – Erection | 45 | 27-Jan-26 | 11-Mar-26 | Bays | 6 | 6 | 0 | 07-May-26 | 19-Jun-26 | 
MCR Panel Erection | 43 | 25-Jan-26 | 08-Apr-26 | Lot | 1 | 0.9 | 0.1 | 22-Feb-26 | 10-Sep-26 | Erection Completed Testing WIP
SVG | 22 | 17-feb-26 | 14-apr-26 | Nos | 7 | 7 | 0 | 12-May-26 | 21-Sep-26 | Erection Completed Testing WIP
Harmonic Filter | 30 | 10-Mar-26 | 10-Apr-26 | Nos | 4 | 3 | 1 | 03-Jun-26 | 12-Sep-26 | 
Testing & ready for charging | 16 | 18-Mar-26 | 15-Apr-26 | Lot | 1 | 0 | 1 | 22-Jun-26 | 25-Sep-26 | 

## Slide 26: Summary : NHPC PSS
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
NHPC PSS Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 44 | 15-Jan-26 | 27-Feb-26 | Lot | 1 | 1 | 0 | 27-Dec-25 | 23-Mar-26 | Completed
MCR Building Civil Work-Upto Slab | 48 | 24-Jan-26 | 12-Mar-26 | Lot | 1 | 1 | 0 | 27-Dec-25 | 24-Apr-26 | Completed
SGR Civil Work-Upto Slab | 42 | 24-Jan-26 | 06-Mar-26 | Lot | 1 | 1 | 0 | 28-Dec-25 | 11-Jun-26 | Completed
Power Transformer – 01&02 Civil Work | 56 | 26-Jan-26 | 18-Feb-26 | Nos | 2 | 2 | 0 | 30-Dec-25 | 25-Jul-26 | Completed
SVG Civil Work (Exc. Fencing) | 25 | 14-Jan-26 | 07-Feb-26 | Lot | 6 | 6 | 0 | 20-Feb-26 | 31-Jul-26 | Completed
Harmonic Filter Civil Work | 26 | 24-Jan-26 | 18-Feb-26 | Lot | 4 | 4 | 0 | 22-Feb-26 | 18-May-26 | Completed
GIS & MCR PEB Erection | 80 | 02-Mar-26 | 26-Apr-26 | Lot | 2 | 1.89 | 0.11 | 28-Apr-26 | 10-Sep-26 | 
SGR - PEB Erection | 37 | 17-Mar-26 | 16-Apr-26 | Lot | 1 | 0.92 | 0.08 | 11-Jun-26 | 10-Sep-26 | 
Power Transformer – 01 Erection | 35 | 16-May-26 | 05-Jun-26 | Nos | 2 | 0 | 2 | 27-Jul-26 | 16-Sep-26 | 
Power Transformer – 02 Erection | 35 | 26-May-26 | 10-Jun-26 | Nos | 2 | 0 | 2 | 29-Aug-26 | 02-Oct-26 | 
SGR - Panel Erection | 39 | 13-Mar-26 | 20-Apr-26 | Lot | 1 | 0 | 1 | 14-Jul-26 | 10-Sep-26 | 
GIS Main Bay Area (Inside Building) – Erection | 36 | 05-Apr-26 | 10-May-26 | Bays | 4 | 4 | 0 | 24-Jun-26 | 21-Aug-26 | Completed
MCR Panel Erection | 53 | 10-Apr-26 | 01-Jun-26 | Lot | 1 | 0.13 | 0.87 | 25-Jul-26 | 26-Sep-26 | 
SVG | 14 | 27-May-26 | 09-Jun-26 | Nos | 6 | 0 | 6 | 10-Sep-26 | 07-Oct-26 | 
Harmonic Filter | 31 | 01-May-26 | 31-May-26 | Nos | 4 | 4 | 0 | 16-Apr-26 | 28-Sep-26 | Testing yet to be started
Testing & ready for charging | 13 | 03-Jun-26 | 15-Jun-26 | Lot | 1 | 0 | 1 | 28-Sep-26 | 14-Oct-26 | P1(14-Oct-26) P2(25-Oct-26)

## Slide 27: Summary : PSS – 18
Activity | Duration | Schedule Start | Schedule Finish | UOM | Scope | Actual | Balance | Actual/ Forecast Start | Actual/ Forecast Finish | Remarks
PSS-18 Priority 1 Progress |  |  |  |  |  |  |  |  |  | 
GIS Building Civil Work-Upto Slab | 53 | 30-Dec-25 | 5-Mar-26 | Lot | 1 | 1 | 0 | 25-Dec-25 | 18-May-26 | Completed
MCR Building Civil Work-Upto Slab | 64 | 6-Jan-26 | 16-Mar-26 | Lot | 1 | 1 | 0 | 27-Dec-25 | 02-Jun-26 | Completed
SGR - 01 Civil Work-Upto Slab | 51 | 6-Jan-26 | 14-Mar-26 | Lot | 1 | 1 | 0 | 29-Dec-25 | 05-Apr-26 | Completed
Power Transformer – 01&02 Civil Work | 77 | 20-Jan-26 | 24-Feb-26 | Nos | 2 | 2 | 0 | 09-Feb-26 | 22-Jul-26 | Completed
SVG Civil Work (Exc. Fencing) | 55 | 07-Jan-26 | 5-Mar-26 | Nos | 8 | 3 | 5 | 10-Jul-26 | 19-Sep-26 | 
Harmonic Filter Civil Work | 52 | 31-Jan-26 | 25-Feb-26 | Nos | 4 | 0 | 4 | 17-Aug-26 | 06-Oct-26 | 
Firewall-01 | 46 | 11-Jan-26 | 22-Feb-26 | Nos | 1 | 0.90 | 0.10 | 06-Feb-26 | 10-Sep-26 | 
GIS & MCR PEB Erection | 80 | 13-Mar-26 | 18-Apr-26 | Lot | 2 | 1.96 | 0.04 | 25-May-26 | 10-Sep-26 | 
SGR - 01 PEB Erection | 37 | 17-Mar-26 | 16-Apr-26 | Lot | 1 | 0.90 | 0.15 | 28-May-26 | 10-Sep-26 | 
Power Transformer – 01&02 Erection | 70 | 20-Mar-26 | 30-Apr-26 | Nos | 2 | 0.34 | 1.66 | 09-Jun-26 | 26-Sep-26 | 
SGR - 01 Panel Erection | 30 | 20-Apr-26 | 23-May-26 | Sets | 4 | 3.5 | 0.5 | 22-Jul-26 | 12-Sep-26 | 
GIS Main Bay Area (Inside Building) – Erection | 45 | 13-Apr-26 | 21-May-26 | Bays | 9 | 0.2 | 8.8 | 17-Aug-26 | 09-Oct-26 | 
MCR Panel Erection | 43 | 29-Apr-26 | 18-May-26 | Lot | 1 | 0.11 | 0.89 | 17-Aug-26 | 13-Oct-26 | 
SVG | 22 | 26-Apr-26 | 26-May-26 | Nos | 7 | 0 | 7 | 20-Sep-26 | 05-Nov-26 | 
Harmonic Filter | 31 | 17-Apr-26 | 21-May-26 | Nos | 4 | 0 | 4 | 07-Oct-26 | 10-Nov-26 | 
Testing & ready for charging | 15 | 16-May-26 | 30-May-26 | Lot | 1 | 0 | 1 | 10-Oct-26 | 29-Nov-26 | 

## Slide 28: Khavda Tracker & Robot Installation Status
Summary | Tracker |  |  | Robot |  |  |  | 
 | Total | Auto | Non-Operational | Total | Installation | Online | RFI Completed | Auto Run
Up to 28-Feb-26 | 139464 | 137629 | 1835 | 23884 | 23884 | 23197 | 23884 | 21728
Up to 28-Feb-26 | 100% | 99% | 1.32% | 100% | 100% | 97% | 100% | 91%
01-Mar-26 to 31-Mar-26 | 7458 | 7151 | 307 | 2085 | 2079 | 2005 | 1694 | 1196
01-Mar-26 to 31-Mar-26 | 100% | 96% | 4% | 100% | 100% | 96% | 81% | 57%
01-Apr-26 to till date | 1143 | 2024 | 176 | 2116 | 2099 | 1788 | 71 | 17
01-Apr-26 to till date | 100% | 92% | 8% | 100% | 99% | 84% | 3% | 1%
Grand Total | 149122 | 146804 | 2318 | 28085 | 28062 | 26990 | 25649 | 22941
Grand Total | 100% | 98% | 2% | 100% | 100% | 96% | 95% | 89%

## Slide 29: Thank You