## Slide 1
CPAG – Energy Cluster
Adani Green Energy Ltd
Aug-26

## Slide 2
Agenda
Executive Summary
Project Wise Update
          Khavda Wind Ph – IV
            Project Information & Salient Features
            Progress Update
            Major Milestone- Next 3 Months
              Major Critical Issues

## Slide 3
Executive Summary
SN | Location | Project Name | FY 27 Plan (MW) | Planned till Aug’26 (MW) | Actual till Aug’26 (MW) | COD |  | Overall Project Progress |  | Remarks
 |  |  |  |  |  | Plan | Expected | Plan | Actual | 
1 | GJ | Khavda-Wind | 417 | 317 | 307 | 31-Mar-27 | 31-Mar-27 | 73% | 72% | 

## Slide 4
Commissioning: Plan vs. Forecast – Khavda Phase - IV
All nos. are in MW
COD |  | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Total
BUDGET | Wind | 99 | 31 | 26 | 83 | 78 |  |  |  |  |  | 50 | 50 | 417
ACTUAL / FCST | Wind | 99 | 31 | 26 | 78 | 73 | 10 |  |  |  |  | 50 | 50 | 417
All the figures are revised as per Revised AOP plan
Chart: 
| Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Budget | 99 | 31 | 26 | 83 | 78 | 50 | 50
Actual / Fcst | 99 | 31 | 26 | 78 | 73 | 10 | 50 | 50

## Slide 5
Khavda Wind

## Slide 6: Khavda Wind - Salient Features
Project | Khavda Phase-III Wind Projects |  |  |  | 
Project Scope / Capacity | Plan – 417.2 MW |  |  |  | 
Owner/ Developer | Various SPV under AGEL and Group Project |  |  |  | 
Location | Khavda, Bhuj, Kutchh |  |  |  | 
Land Area | AGEL – 19000 Ha, SRPL – 9500 Ha |  |  |  | 
Project Configuration | Wind Turbine |  |  |  | 
Parameters | 61 WTGs : ANIL 5.2 MW 20 WTGs : ANIL 5.0 MW |  |  |  | 
Commissioning (FY 25-26) | Q1 | Q2 | Q3 | Q4 | Total
Budget Plan (MW) | 156 | 161 | - | 100 | 417
Actual / Expected (MW) | 156 | 151 / 161 | - | 100 | 307 / 417

## Slide 7: Khavda Wind - Physical Progress: S Curve
Gap Analysis |  |  |  |  | 
Progress Parameter | Weightage | Cumm. Plan | Cumm. Actual | Variance | Remarks for Variance
Engineering | 5% | 100% | 99% | 1% | 
Procurement | 35% | 81% | 79% | 2% | 
Construction | 60% | 66% | 65% | 1% | 
Total | 100% | 73% | 72% | 1% | 
Chart: 
| 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447
Monthly Plan | 0.37368 | 0.14991 | 0.091624 | 0.048605 | 0.042895 | 0.025327 | 0.013364 | 0 | 0 | 0.027293 | 0.06385 | 0.10783 | 0.055628
Monthly Actual | 0.35862 | 0.12254 | 0.069722 | 0.082464 | 0.057997 | 0.02615 | 0.00018182 | 0 | 0 | 0 | 0 | 0 | 0
Monthly Forecast Plan
Cummulative Plan | 0.37368 | 0.52358 | 0.61521 | 0.66381 | 0.70671 | 0.73203 | 0.7454 | 0.7454 | 0.7454 | 0.77269 | 0.83654 | 0.94437 | 1
Cummulative Actual | 0.35862 | 0.48116 | 0.55088 | 0.63334 | 0.69134 | 0.71749
Cummulative Forecast Plan

## Slide 8: Khavda Wind - Procurement & 3 month rolling plan for Supply Status
S.No. | Packages | UOM | Scope (Plan for FY26-27) | Ordering Completed | Delivered at Site up to Aug'26 | Balance to Deliver | Next 3 Month Rolling Plan |  | 
 |  |  |  |  |  |  | Sep-26 | Oct-26 | Nov-26
1 | WTG Set (N-H-DT) | Nos. | 81 | 111 | 61 | 20 | - | - | -
2 | Blade | Nos. | 81 | 111 | 61 | 20 | - | - | -
3 | Tower | Nos. | 81 | 111 | 61 | 20 | - | - | -
4 | Transformer | Nos. | 81 | 111 | 74 | 7 | - | - | -
5 | HT Panel | Nos. | 81 | 111 | 65 | 16 | - | - | -
6 | 33 kV / UG Cable | Km | 306 | 306 | 274 | 32 | - | - | -

## Slide 9: Khavda Wind - Construction Progress Update
Sr. No | Activity | UOM | Scope (Plan for FY26-27) | Completed | Balance | Preceding Month Aug’26 |  | Next 3 Month Rolling Plan |  |  | Completion Target
 |  |  |  |  |  | Plan | Actual | Sep-26 | Oct-26 | Nov-26 | 
1 | Stone Column | Nos | 111 | 106 | 5 |  | 1 |  |  | 3 | 10-Dec-26
2 | WTG Foundation | Nos | 111 | 79 | 32 | 8 | 3 | 8 | 8 | 8 | 30-Dec-26
3 | USS Pre-cast Erection | Nos | 111 | 63 | 48 | 7 | 1 | 9 | 9 | 14 | 30-Dec-26
4 | WTG Erection | Nos | 81 | 61 | 20 | 10 | 10 |  |  |  | 15-Mar-27
5 | USS Erection | Nos | 81 | 61 | 20 | 2 | 2 |  |  |  | 31-Jan-27
6 | HT Cable Laying | Km | 306 | 265 | 41 |  | 22 |  |  |  | 20-Jan-27
7 | WTG Commissioning (Trial Run) | Nos | 81 | 59 | 22 | 16 | 14 | 2 |  |  | 31-Mar-27

## Slide 10: Khavda Wind - Machinery Summary
Sr No | Equipment Description | UOM | Actual available at site for the Month Aug’26 | Next 3 Month Rolling Forecast |  | 
 |  |  |  | Sep-26 | Oct-26 | Nov-26
1 | Rigs for Stone Column | Nos. | - | - | - | 2
2 | Main Crane Package for WTG Erection | Nos. | 9 | - | - | -
Note: 1 crane is with the O&M team..

## Slide 11
Chart: 
| Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Forecast | Plan | Forecast | Plan | Forecast | Plan | Forecast | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27
Wind | 1733 | 1387 | 1593 | 1319 | 1444 | 1347 | 1309 | 1189 | 836 | 870 | 836 | 346 | 346 | 210 | 210 | 546 | 686 | 686
Khavda Wind: Manpower Deployment Plan vs Actual
Forecast Manpower are based on EPC partners inputs.

## Slide 12: Thank You