## MDL PSS Summery (2) (hidden)
STATUS AS ON DATE | [5 empty] | STATUS AS ON DATE |  | 01.01.2025
KHAVDA- BESS PSS MDL STATUS | [5 empty] | KHAVDA PSS MDL STATUS-PHASE-3 | [5 empty] | Approval Status
1 | PSS-5 |  |  |  | REMARKS | 1 | PSS-6 |  |  |  | REMARKS | RFC | A1 | A2 | A3 | I | UR | [10 empty] | Date : | 2026-09-04
| CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF! |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 14 | 56% | Hyosung-19 added-offline submitted docu. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | KHAVDA- BESS PSS MDL STATUS
|  | Not Submitted | #REF! | #REF! |  |  |  | Not Submitted | 11 | 44% | [7 empty] | Project | Total Docment |  |  | Approval Status | [6 empty] | Not Submitted
|  | Total | #REF! |  |  |  |  | Total | 25 | [9 empty] | Total | In-House | Vendor | Total | RFC | A1 | A2 | A3 | I | UR | Total | In-House | Vendor
2 | PSS-8 |  |  |  | REMARKS | 2 | PSS-7 |  |  |  | REMARKS | RFC | A1 | A2 | A3 | I | UR | PSS-5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF! |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 9 | 47.37% | Hyosung-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | PSS-8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Not Submitted | #REF! | #REF! |  |  |  | Not Submitted | 10 | 52.63% | [7 empty] | PSS-10 | 102 | 0 | 102 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12 | 0 | 12
|  | Total | #REF! |  |  |  |  | Total | 19 | [8 empty] | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | PSS-10 |  |  |  | REMARKS | 3 | PSS-11 |  |  |  | REMARKS | RFC | A1 | A2 | A3 | I | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF! |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 8 | 42.11% | Hyosung-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Not Submitted | #REF! | #REF! |  |  |  | Not Submitted | 11 | 57.89%
|  | Total | #REF! |  |  |  |  | Total | 19
| Grand Total |  |  |  | REMARKS |  | Grand Total |  |  |  | REMARKS
| CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF! |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF!
|  | Not Submitted | #REF! | #REF! |  |  |  | Not Submitted | #REF! | #REF!
|  | Total | #REF! |  |  |  |  | Total | #REF!

## PSS09
PSS09_Adani Green Energy 27 A Limited (AGE27AL) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10
1 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
2 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
3 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
4 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-V-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
5 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-V-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
6 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
7 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Ornet | 6497-ORNT-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
8 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
9 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
10 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
11 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-V-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
12 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
13 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Vendor | Tesla | 6497-TESL-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document | 2026-06-12 |  |  | Not Submitted | [50 empty] | E
14 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
15 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
16 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-01-30 | 2026-09-30 |  | Not Submitted | [50 empty] | E
17 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
18 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
19 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
20 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
21 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
22 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Kunal on 23.06.2026 | [45 empty] | E
23 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
24 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
25 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
26 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 09.07.2026 | [45 empty] | E
27 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
28 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
29 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
30 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
31 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
32 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
33 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
34 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
35 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
36 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
37 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
38 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
39 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
40 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | M
41 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | M
42 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
43 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunal on 17.03.2026 | [45 empty] | E
44 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
45 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
46 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
47 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
48 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
49 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
50 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 02.03.2026 | [45 empty] | E
51 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
52 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
53 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery | Vendor | CATL | 6497-CATL-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
54 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
55 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
56 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
57 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 16.04.2026 | [45 empty] | E
58 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Tinkle Khalasi_18.04.2026 | [45 empty] | E
59 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
60 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
61 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
62 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
63 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
64 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
65 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
66 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
67 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
68 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
69 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
70 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
71 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
72 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | I
73 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
74 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0002 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
75 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
76 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
77 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
78 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
79 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
80 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
81 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
82 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0003 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
83 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
84 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Under Review |  |  | Under Review |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
85 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
86 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
87 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS | Vendor | Inovance | 6497-INOV-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
88 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | CSS | Vendor | Akshar | 6497-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing | 2026-01-31 |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
89 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT Panel-Outdoor | Vendor | Popular SGR | 6497-PSGR-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | NR | 2026-05-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
90 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | ACDB | Vendor | Prima Automation | 6497-PRMA-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) |  |  | 2026-01-28 |  |  | Cat. -I | NR | 2026-06-24 | Cat. -I |  |  | NR | 2026-07-03 | Cat. -I |  | Rev.07 | [40 empty] | E
91 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
92 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT Cable | Vendor | Vendor | 6497-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
93 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT Cable | Vendor | Vendor | 6497-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
94 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LT Cable | Vendor | Vendor | 6497-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
95 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LT Cable | Vendor | Vendor | 6497-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
96 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control Cable | Vendor | Vendor | 6497-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
97 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Opteical fiber cable | Vendor | Vendor | 6497-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
98 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PEB Building | Vendor | Vendor | 6497-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
99 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PEB Building | Vendor | Vendor | 6497-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
100 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PEB Building | Vendor | Vendor | 6497-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
101 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PEB Building | Vendor | Vendor | 6497-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
102 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-Q-0001 | 51H2-E-EMS-EMS-DE-Q-V-0001 | EMS SCADA System Architecture Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
103 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-I-0001 | 51H2-E-EMS-EMS-DE-I-V-0001 | EMS Panel Drawing for Central Control Room, Network Panel, Site Level RTU RIO Panel, PCS Plateform RIO Panel, Junction Box for Ethernet Switches & LIUs | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
104 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0001 | 51H2-E-EMS-EMS-DE-D-V-0001 | EMS System Components Datasheet - Including all equipments | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
105 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0002 | 51H2-E-EMS-EMS-DE-D-V-0002 | Project BOM (Bill of Materials) - Includes Hardware and Software | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
106 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-O-0001 | 51H2-E-EMS-EMS-DE-O-V-0001 | Factory Acceptance Test (FAT) Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
107 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-O-0002 | 51H2-E-EMS-EMS-DE-O-V-0002 | SAT Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
108 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-I-0002 | 51H2-E-EMS-EMS-DE-I-V-0002 | Logic Diagram for EMS | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
109 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-E-0001 | 51H2-E-EMS-EMS-DE-E-V-0001 | Wiring Detailed Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
110 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0003 | 51H2-E-EMS-EMS-DE-D-V-0003 | Input Output List/Summary | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
111 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-O-0003 | 51H2-E-EMS-EMS-DE-O-V-0003 | Factory Integrated Test (FIT) Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
112 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-E-0002 | 51H2-E-EMS-EMS-DE-E-V-0002 | Panel Grounding Scheme | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
113 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-O-0004 | 51H2-E-EMS-EMS-DE-O-V-0004 | Document Dosier | Information | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
114 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-I-0003 | 51H2-E-EMS-EMS-DE-I-V-0003 | Interconnection Detailed Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
115 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-I-0004 | 51H2-E-EMS-EMS-DE-I-V-0004 | EMS Screens & Report Format | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
116 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-S-0001 | 51H2-E-EMS-EMS-DE-S-V-0001 | Functional Design Specification (FDS) | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
117 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0004 | 51H2-E-EMS-EMS-DE-D-V-0004 | IP List | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
118 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-M-0001 | 51H2-E-EMS-EMS-DE-M-V-0001 | EMS O&M Manual | Information | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
119 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0005 | 51H2-E-EMS-EMS-DE-O-V-0005 | Detailed Erection; Pre-Commissioning and Commissioning Procedure | Information | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
120 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-C-0001 | 51H2-E-EMS-EMS-DE-C-V-0001 | Heat Dissipation & Load Calculation | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
121 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-S-0002 | 51H2-E-EMS-EMS-DE-S-V-0002 | Cyber Security Specification | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
122 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-I-0005 | 51H2-E-EMS-EMS-DE-I-V-0005 | FIT Testing panel wiring diagram | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
123 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-Q-0002 | 51H2-E-EMS-EMS-DE-Q-V-0002 | FIT Testing panel System architecture | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
124 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0006 | 51H2-E-EMS-EMS-DE-D-V-0005 | EMS System Datasheet - IT Hardware Components | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
125 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Vendor | 6497-XXXX-EMS-GEN-DE-D-0007 | 51H2-E-EMS-EMS-DE-D-V-0006 | EMS System Datasheet - Enclosures Accessories Components | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
126 |  | EMS |  | Vendor | 6497-XXXX-EMS-GEN-DE-N-0001 | 51H2-E-EMS-EMS-DE-N-V-0001 | Complete Documentation of Implemented Protocols Between Various Elements | Approval | Document |  |  |  | delete |  |  | delete | [47 empty] | E
127 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0001 |  | General Arrangement Layout Drawing | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
128 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0002 | 51H2-E-HFL-HFL-DE-G-V-0001 | Drawing and GTP for Series Reactors | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
129 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0003 | 51H2-E-HFL-HFL-DE-G-V-0002 | Drawing and GTP for Off Load Isolator | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 28-04-2026 15-06-2026 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
130 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0004 | 51H2-E-HFL-HFL-DE-G-V-0003 | Drawing and GTP for NCT | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
131 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0005 | 51H2-E-HFL-HFL-DE-G-V-0004 | Drawing and GTP for Lightning Arrestor | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 |  | NR | 2026-09-02 | Cat. -I | [42 empty] | E
132 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0006 | 51H2-E-HFL-HFL-DE-D-V-0001 | Drawing and GTP for MV Capacitors | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.01 | [45 empty] | E
133 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-G-0007 | 51H2-E-HFL-HFL-DE-E-V-0001 | Drawing and GTP for Damping Resistor | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-04-28 | 2026-05-01 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
134 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-D-0001 | 51H2-E-HFL-HFL-DE-D-V-0002 | Data sheet for Termination kit | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-04-29 | 2026-05-01 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
135 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-D-0002 | 51H2-E-HFL-HFL-DE-G-V-0005 | Data sheet for Control Cable | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-04-29 | 2026-05-01 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
136 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-D-0003 | 51H2-E-HFL-HFL-DE-C-V-0001 | Data sheet for DWC pipe | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-04-29 | 2026-05-01 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
137 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-D-0004 | 51H2-E-HFL-HFL-DE-G-V-0006 | Drawing & Data sheet for Earth Pit & Earth Flats | Approval | Document | 2026-05-04 |  |  | Cat. -I | 29-04-2026 14-05-2026 | 01-05-2026 14-05-2026 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
138 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-E-0001 | 51H2-E-HFL-HFL-DE-G-V-0007 | Single Line Diagram | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
139 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DE-C-0001 |  | Design Calculation sheet for Harmonic Filter |  |  | 2026-05-04 |  |  | delete | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.01 |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [40 empty] | E
140 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DC-L-0001 |  | Equipment Foundation Layout Drawing |  |  | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | Drawing number is not mentioned in the drawing. | [45 empty] | C
141 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Vendor | Clerient | 6497-CPSL-HFL-GEN-DC-C-0001 | 51H2-E-HFL-HFL-DE-D-V-0003 | Structure calculations |  |  | 2026-05-04 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
142 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery Container | In-house | In-house | 6497-ADNI-CDN-BCN-DC-V-0001 | 51H2-E-CIV-BCN-DC-V-I-0001 | Precast foundation drawing for Battery container-CATL | Approval | Drawing | 2025-12-23 |  |  | RFC | 2025-12-27 | 2025-12-27 | RFC | 6497-BESS-SITE-T-0001 |  | 2026-01-07 | 2026-01-08 | RFC | 6497-BESS-SITE-T-0003 | [41 empty] | C
143 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery Container | In-house | In-house | 6497-ADNI-CDN-BCN-DC-H-0001 | 51H2-E-CIV-BCN-DC-H-I-0001 | Fabrication drawing for Precast foundation drawing for Battery container | Approval | Drawing |  |  |  | Cat. -I | 2025-01-09 | 2025-01-09 | RFC | 6497-BESS-SITE-T-0004 |  | 2026-02-18 | 2026-02-18 | Cat. -I | 6497-BESS-SITE-T-0011 |  | 2026-03-17 | 2026-03-17 | Cat. -I | 6497-BESS-SITE-T-0022 | [36 empty] | C
144 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  |  | 6497-ADNI-CDN-CTF-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR NIFPS PSS-9 | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 | [46 empty] | C
144 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  |  | 6497-ADNI-CDN-CTF-DC-H-0002 |  | ERECTION DRAWING OF COUPLING TRANSFORMER FOUNDATION (FOR TESLA MAKE) TYPICAL FOOTING, PRECAST DRAWING.(PSS9) |  |  | 2026-07-16 |  |  | Cat. -IV | 2026-07-23 | 2026-07-24 | Cat. -IV | 6497-BESS-SITE-T-0062 |  | 2026-07-24 | 2026-07-25 | Cat. -IV | 6497-BESS-SITE-T-0063 |  | 2026-08-06 | 2026-08-06 | Cat. -IV | 6497-BESS-SITE-T-0070 | [36 empty] | C
145 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) |  |  |  | 6497-ADNI-CDN-STC-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR STAIRCASE-BCF PSS-9 | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 | [46 empty] | C
146 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Overall-FDN | In-house | In-house | 6497-ADNI-CDN-CIV-DC-V-0001 | 51H2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing | 2025-12-23 |  |  | RFC | 2206-01-05 | 2206-01-05 | RFC | 6497-BESS-SITE-T-0002 | [46 empty] | C
147 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform |  | In-house | 6497-ADNI-CDN-LCR-DC-V-0001 |  | LAYOUT FOR LOCAL CONTROL ROOM / ELECTRICAL ROOM – FOUNDATION PLAN & SECTION DETAILS |  |  | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 6497-BESS-SITE-T-0005 | [46 empty] | C
148 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform |  | In-house | 6497-ADNI-CDN-HGR-DC-V-0001 |  | LAYOUT FOR OUTDOOR SWITCHGEAR ROOM – FOUNDATION PLAN & SECTION DETAILS |  |  | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 6497-BESS-SITE-T-0005 | [46 empty] | C
149 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  | In-house | 6497-ADNI-CDN-CTF-DC-V-0005 |  | LAYOUT FOR HT-LT PANEL (PCS) SUPPORTING PLATFROM – FOUNDATION PLAN & SECTION DETAILS |  |  | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 6497-BESS-SITE-T-0005 | [46 empty] | C
150 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  | In-house | 6497-ADNI-CDN-CTF-DC-V-0001 |  | Coupling Transformer Foundation Layout and RC Details-Ornet | [5 empty] | RFC | 2026-02-10 | 2026-02-11 | RFC | 6497-BESS-SITE-T-0008 |  | 2026-04-02 | 2026-04-03 | RFC | 6497-BESS-SITE-T-0025 | [41 empty] | C
151 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  | In-house | 6497-ADNI-CDN-CTF-DC-V-0007 |  | Coupling Transformer Foundation Layout and RC Details-Tesla | [5 empty] | RFC | 2026-02-10 | 2026-02-11 | RFC | 6497-BESS-SITE-T-0008 | [46 empty] | C
152 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station |  | In-house | 6497-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS09) TYPICAL FOOTING, PRECAST DRAWING | [5 empty] | RFC | 2026-03-16 | 2026-03-16 | RFC | 6497-BESS-SITE-T-0021 | [46 empty] | C
| PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer Station | In-House | In-house | 6497-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval |  |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 6497-BESS-SITE-T-0056 | [46 empty] | C
173 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | SECURITY BARRACK | In-House | In-house | 6497-ADNI-CDN-SEB-DC-V-0001 |  | TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m (BESS PLANT AREA)-PSS09 | Approval | Document |  |  |  | RFC | 2026-06-20 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0048 | [46 empty] | C
153 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | ROAD,Drain & Fencing |  | In-house | 6497-ADNI-CDN-ROD-DC-L-0001 |  | BESS APPROACH ROAD AND CROSS SECTION | Approval | Drawing | 2026-02-20 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
154 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | ROAD,Drain & Fencing | In-house | In-house | 6497-ADNI-CDN-ROD-DC-L-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-02-20 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
155 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | High Mast |  | In-house | 6497-ADNI-CDN-HML-DC-L-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 6497-BESS-SITE-T-0013 | [46 empty] | C
156 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | High Mast |  | In-house | 6497-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 6497-BESS-SITE-T-0016 | [46 empty] | E
157 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-Q-0001 |  | EMS System Architecture | Approval | Drawing | 2026-02-27 |  |  | Not Submitted | [50 empty] | I
158 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0001 |  | IP Address List | Approval | Document | 2026-02-27 |  |  | Not Submitted | [50 empty] | I
159 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0002 |  | Datasheet Of Server & Operator Workstation | Approval | Document | 2026-02-20 |  |  | Not Submitted | [50 empty] | I
160 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0003 |  | Datasheet Of Network Switches | Approval | Document | 2026-02-17 |  |  | Not Submitted | [50 empty] | I
161 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0004 |  | Datasheet Of Firewall | Approval | Document | 2026-02-17 |  |  | Not Submitted | [50 empty] | I
162 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0005 |  | Datasheet Of Printer | Approval | Document | 2026-02-17 |  |  | Not Submitted | [50 empty] | I
163 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0006 |  | Datasheet Of GPS | Approval | Document | 2026-02-20 |  |  | Not Submitted | [50 empty] | I
164 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0007 |  | Datasheet Of Historian Server | Approval | Document | 2026-02-20 |  |  | Not Submitted | [50 empty] | I
165 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0008 |  | Datasheet Of Serial Convertor | Approval | Document | 2026-02-18 |  |  | Not Submitted | [50 empty] | I
166 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0009 |  | Datasheet Of Console | Approval | Document | 2026-02-18 |  |  | Not Submitted | [50 empty] | I
167 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0010 |  | Datasheet Of Chair | Approval | Document | 2026-02-18 |  |  | Not Submitted | [50 empty] | I
168 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0011 |  | Power Consumption and Heat Dissipation | Approval | Document | 2026-02-27 |  |  | Not Submitted | [50 empty] | I
169 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0012 |  | Datasheet Of EMS Controller | Approval | Document | 2026-02-19 |  |  | Not Submitted | [50 empty] | I
170 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0013 |  | Datasheet Of EMS IO Module | Approval | Document | 2026-02-19 |  |  | Not Submitted | [50 empty] | I
171 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0014 |  | Datasheet Of Power Supply | Approval | Document | 2026-02-27 |  |  | Not Submitted | [50 empty] | I
172 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0015 |  | Datasheet Of Indoor Cabinets | Approval | Document | 2026-02-19 |  |  | Not Submitted | [50 empty] | I
173 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0016 |  | Datasheet Of Field Network Cabinet | Approval | Document | 2026-02-27 |  |  | Not Submitted | [50 empty] | I
174 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0017 |  | Datasheet Of Monitor | Approval | Document | 2026-02-23 |  |  | Not Submitted | [50 empty] | I
175 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0018 |  | Datasheet Of Large Screen | Approval | Document | 2026-02-23 |  |  | Not Submitted | [50 empty] | I
176 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0019 |  | Datasheet Of Fiber Optic Patch Panel | Approval | Document | 2026-02-23 |  |  | Not Submitted | [50 empty] | I
177 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0020 |  | Bill of Material (BOM) | Approval | Document | 2026-02-25 |  |  | Not Submitted | [50 empty] | I
178 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-S-0001 |  | EMS Functional Design Specifications | Approval | Document | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
179 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-G-0001 |  | EMS Cabinet General Arrangement & Wiring Diagram | Approval | Drawing | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
180 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-G-0002 |  | Substation RTU Cabinet General Arrangement & Wiring Diagram | Approval | Drawing | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
181 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-G-0003 |  | Network Cabinet General Arrangement & Wiring Diagram | Approval | Drawing | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
182 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-G-0004 |  | IDT/Network Cabinet General Arrangement & Wiring Diagram | Approval | Drawing | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
183 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-G-0005 |  | Control Room Server Cabinet General Arrangement & Wiring Diagram | Approval | Drawing | 2026-03-06 |  |  | Not Submitted | [50 empty] | I
184 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-E-0001 |  | Cabinet Grounding Scheme | Approval | Drawing | 2026-03-10 |  |  | Not Submitted | [50 empty] | I
185 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0001 |  | IO Assignment-EMS Controller | Approval | Drawing | 2026-03-09 |  |  | Not Submitted | [50 empty] | I
186 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0002 |  | IO Assignment-Substation Controller | Approval | Drawing | TBD |  |  | Not Submitted | [50 empty] | I
187 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0003 |  | EMS Control Philosophy Flow Chart | Approval | Drawing | TBD |  |  | Not Submitted | [50 empty] | I
188 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0004 |  | EMS Factory Acceptance Test Procedure (FAT) | Approval | Drawing | 2026-03-17 |  |  | Not Submitted | [50 empty] | I
189 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0005 |  | EMS Logic Print | Approval | Drawing | 2026-04-30 |  |  | Not Submitted | [50 empty] | I
190 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0006 |  | EMS HMI Print | Approval | Drawing | 2026-04-30 |  |  | Not Submitted | [50 empty] | I
191 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0001 |  | EMS FAT Report | Approval | Document | 2026-05-04 |  |  | Not Submitted | [50 empty] | I
192 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0007 |  | EMS Site Acceptance Test Procedure (SAT) | Approval | Drawing | 2026-04-14 |  |  | Not Submitted | [50 empty] | I
193 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0002 |  | EMS SAT Report | Approval | Document | 2026-06-26 |  |  | Not Submitted | [50 empty] | I
194 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-D-0021 |  | Pre-commissioning and Commissioning Check list | Approval | Drawing | 2026-04-14 |  |  | Not Submitted | [50 empty] | I
195 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-M-0001 |  | EMS Operation & Maintenance Manual | Approval | Document | 2026-04-14 |  |  | Not Submitted | [50 empty] | I
196 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-S-0002 |  | Cyber Security Functional Design Specification | Approval | Document | 2026-03-16 |  |  | Not Submitted | [50 empty] | I
197 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0008 |  | CSVA Procedure | Approval | Document | 2026-03-19 |  |  | Not Submitted | [50 empty] | I
198 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0009 |  | Cyber Security FAT Procedure | Approval | Document | 2026-03-16 |  |  | Not Submitted | [50 empty] | I
199 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0010 |  | Cyber Security SAT Procedure | Approval | Document | 2026-04-14 |  |  | Not Submitted | [50 empty] | I
200 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-O-0011 |  | Cyber Security Risk Assessment TOR | Approval | Document | 2026-02-20 |  |  | Not Submitted | [50 empty] | I
201 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0003 |  | Cyber Security Risk Assessment Report | Approval | Document | TBD |  |  | Not Submitted | [50 empty] | I
202 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0004 |  | CSVA Report | Approval | Document | TBD |  |  | Not Submitted | [50 empty] | I
203 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0005 |  | VAPT Report | Approval | Document | 2026-04-30 |  |  | Not Submitted | [50 empty] | I
204 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0006 |  | Cyber Security FAT Report | Approval | Document | 2026-04-30 |  |  | Not Submitted | [50 empty] | I
205 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Vendor | Honeywell | 6497-HNWL-EMS-GEN-DI-R-0007 |  | Cyber Security SAT Report | Approval | Document | 2026-06-26 |  |  | Not Submitted | [50 empty] | I
206 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Overall-FDN | Consultant | Worley | 6497-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | delete |  |  | delete | [47 empty] | C
207 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Shed | Consultant | Worley | 6497-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-09 | Approval | Drawing |  |  |  | Cat. -IV | 2026-02-11 | 2026-02-11 | Cat. -IV | 6497-BESS-SITE-T-0009 |  | 2026-03-05 | 2026-03-05 | Cat. -IV | 6497-BESS-SITE-T-0019 | [41 empty] | S
208 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Platform | Consultant | Worley | 6497-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing |  |  |  | Cat. -I | 2026-02-07 | 2026-02-09 | Cat. -IV | 6497-BESS-SITE-T-0007 |  | 2026-03-05 | 2026-03-06 | Cat. -I | 6497-BESS-SITE-T-0020 | [41 empty] | C
209 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Foundation | Consultant | Worley | 6497-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
210 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Platform | Consultant | Worley | 6497-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 | [46 empty] | C
211 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Platform | Consultant | Worley | 6497-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) | [5 empty] | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 6497-BESS-SITE-T-0068 | [46 empty] | C
212 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) |  |  |  | 6497-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-9 | [5 empty] | Not Submitted | [50 empty] | S
213 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
214 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing |  |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
215 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | [5 empty] | Cat. -I_Star | NR |  |  |  |  | 2026-02-14 | 2026-02-16 | Cat. -I | 6497-BESS-SITE-T-0010 |  | 2026-04-23 | 2026-04-23 | Cat. -I | 6497-BESS-SITE-T-0028 |  | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 6497-BESS-SITE-T-0065 | [26 empty] | C
216 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 | [46 empty] | C
217 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room | [5 empty] | RFC | 2026-07-25 | 2026-07-25 | RFC | 6497-BESS-SITE-T-0064 | [46 empty] | C
218 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-9 | [5 empty] | Cat. -I | 2026-02-07 | 2026-02-09 | Cat. -IV | 6497-BESS-SITE-T-0007 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 6497-BESS-SITE-T-0015 | [41 empty] | S
219 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing |  |  |  | Cat. -I | 2026-04-01 | 2026-04-02 | Cat. -I | 6497-BESS-SITE-T-0023 |  | NR |  |  |  |  | 2026-06-09 | 2026-06-09 | Cat. -I | 6497-BESS-SITE-T-0044 | [36 empty] | C
220 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
221 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room | [5 empty] | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 6497-BESS-SITE-T-0072 | [46 empty] | C
222 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 | [46 empty] | C
223 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | CSS | Consultant | Worley | 6497-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing |  |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 6497-BESS-SITE-T-0006 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 6497-BESS-SITE-T-0015 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 6497-BESS-SITE-T-0027 | [36 empty] | C
224 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Battery Container-CATL | Consultant | Worley | 6497-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 | [46 empty] | C
225 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Consultant | Worley | 6497-WRLY-OEN-CTF-DC-U-0001 |  | Cable support near coupling transformer area | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 6497-BESS-SITE-T-0055 | [46 empty] | C
226 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Consultant | Worley | 6497-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
227 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Consultant | Worley | 6497-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 6497-BESS-SITE-T-0012 | [46 empty] | C
228 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | ROAD,Drain & Fencing | Consultant | Worley | 6497-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
229 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | SECURITY BARRACK | Consultant | Worley | 6497-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing |  |  |  | delete |  |  | delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
230 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | High Mast | Consultant | Worley | 6497-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Rupak, not in worley scope._21.02.2026 | [45 empty] | C
231 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
232 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
233 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room | [5 empty] | Cat. -IV | 2026-08-29 | 2026-08-31 | Cat. -IV | 6497-BESS-SITE-T-0076 | [46 empty] | C
234 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Consultant | Worley | 6497-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document |  |  |  | RFC | 2026-07-14 | 2026-07-15 | RFC | 6497-BESS-SITE-T-0058 | [46 empty] | C
235 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Overall SLD | Consultant | Worley | 6497-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing |  |  |  | RFC | 2026-03-02 | 2026-03-02 | Cat. -I | 6497-BESS-SITE-T-0018 |  | 2026-06-10 | 2026-06-10 | RFC | 6497-BESS-SITE-T-0046 |  | 2026-08-05 | 2026-08-05 | RFC | 6497-BESS-SITE-T-0069 | [36 empty] | E
236 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Aux Plant SLD | Consultant | Worley | 6497-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD | [5 empty] | Cat. -I | 2026-04-01 | 2026-04-02 | Cat. -I | 6497-BESS-SITE-T-0024 | [46 empty] | E
237 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Ovearall Layout - Electrical | Consultant | Worley | 6497-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing |  |  |  | RFC | 26-02-2026a 26-06-2026 | 26-02-2026a 26-06-2026 | RFC | 6497-BESS-SITE-T-0017 6497-BESS-SITE-T-0052 | Due to crane pad implementation at site . So, not required new revision | 2026-07-15 | 2026-07-15 | RFC | 6497-BESS-SITE-T-0059 | [41 empty] | E
238 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Ovearall Layout - Electrical | Consultant | Worley | 6497-WRLY-OEN-BES-DE-L-0002 |  | Layout Options | [5 empty] | Not Submitted | [50 empty] | E
239 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Overall Equipment Layout - Electrical | Consultant | Worley | 6497-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) | [5 empty] | RFC | 2026-07-15 | 2026-07-15 | RFC | 6497-BESS-SITE-T-0059 | [46 empty] | E
240 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Plant Earthing Layout | Consultant | Worley | 6497-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing |  |  |  | RFC | 2026-05-12 | 2026-05-12 | RFC | 6497-BESS-SITE-T-0035 |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0050 | [41 empty] | E
241 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Plant Earthing Design | Consultant | Worley | 6497-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
242 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Plant Lightning Layout | Consultant | Worley | 6497-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing |  |  |  | RFC | 2026-05-11 | 2026-05-11 | RFC | 6497-BESS-SITE-T-0033 |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0050 | [41 empty] | E
243 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Plant Lightning design | Consultant | Worley | 6497-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
244 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Illumination | Consultant | Worley | 6497-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing |  |  |  | RFC | 2026-05-11 | 2026-05-11 | RFC | 6497-BESS-SITE-T-0034 |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0050 | [41 empty] | E
245 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Illumination | Consultant | Worley | 6497-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | RFC | NR |  |  |  |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0050 | [41 empty] | E
246 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | PCS Platform | Consultant | Worley | 6497-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS | [5 empty] | Not Submitted | [50 empty] | E
247 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | AC & DC Cable Layout | Consultant | Worley | 6497-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing |  |  |  | RFC | 2026-05-11 | 2026-05-11 | RFC | 6497-BESS-SITE-T-0033 |  | 2026-06-26 | 2026-06-26 | RFC | 6497-BESS-SITE-T-0051 |  | 2026-07-16 | 2026-07-17 | RFC | 6497-BESS-SITE-T-0060 | [36 empty] | E
248 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | AC & DC Cable Layout | Consultant | Worley | 6497-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing |  |  |  | RFC | 2026-05-11 | 2026-05-11 | RFC | 6497-BESS-SITE-T-0033 |  | 2026-06-26 | 2026-06-26 | RFC | 6497-BESS-SITE-T-0051 |  | 2026-07-11 | 2026-07-11 | RFC | 6497-BESS-SITE-T-0054 | [36 empty] | E
249 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | AC & DC Cable Layout | Consultant | Worley | 6497-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-30 | 2026-05-30 | Cat. -IV | 6497-BESS-SITE-T-0040 |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0049 | [41 empty] | E
250 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT-FO Cable | Consultant | Worley | 6497-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing |  |  |  | RFC | 2026-05-02 | 2026-05-04 | Cat. -I | 6497-BESS-SITE-T-0030 |  | 2026-07-15 | 2026-07-15 | RFC | 6497-BESS-SITE-T-0059 |  | 2026-08-13 | 2026-08-13 | RFC | 6497-BESS-SITE-T-0075 | [36 empty] | E
251 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT-FO Cable | Consultant | Worley | 6497-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing |  |  |  | RFC | 2026-05-02 | 2026-05-04 | Cat. -I | 6497-BESS-SITE-T-0030 |  | 2026-07-15 | 2026-07-15 | RFC | 6497-BESS-SITE-T-0059 |  | 2026-08-13 | 2026-08-13 | RFC | 6497-BESS-SITE-T-0075 | [36 empty] | E
252 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT-FO Cable | Consultant | Worley | 6497-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-08 | 26-05-202 | Cat. -I | 6497-BESS-SITE-T-0037 |  | 2026-06-22 | 2026-06-22 | RFC | 6497-BESS-SITE-T-0049 | [41 empty] | E
253 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | HT-FO Cable | Consultant | Worley | 6497-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document |  |  |  | RFC | NR |  |  |  |  | 2026-05-29 | 2026-05-29 | RFC | 6497-BESS-SITE-T-0039 | [41 empty] | E
254 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Cable Sizing | Consultant | Worley | 6497-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
255 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Equipment Sizing | Consultant | Worley | 6497-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
256 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control & Auxillary Cable | Consultant | Worley | 6497-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | [5 empty] | RFC | 2026-05-28 | 2026-05-28 | RFC | 6497-BESS-SITE-T-0038 |  | 2026-07-16 | 2026-07-17 | RFC | 6497-BESS-SITE-T-0060 | [41 empty] | E
257 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control & Auxillary Cable | Consultant | Worley | 6497-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) | [5 empty] | RFC | 2026-05-28 | 2026-05-28 | RFC | 6497-BESS-SITE-T-0038 |  | 2026-07-16 | 2026-07-17 | RFC | 6497-BESS-SITE-T-0060 | [41 empty] | E
258 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control & Auxillary Cable | Consultant | Worley | 6497-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
259 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control & Auxillary Cable | Consultant | Worley | 6497-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
260 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Control & Auxillary Cable | Consultant | Worley | 6497-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document |  |  |  | RFC | 2026-05-15 | 2026-05-15 | Cat. -IV | 6497-BESS-SITE-T-0036 |  | 2026-07-22 | 2026-07-22 | RFC | 6497-BESS-SITE-T-0061 | [41 empty] | E
261 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Consultant | Worley | 6497-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. | [5 empty] | Not Submitted | [50 empty] | E
262 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | MV SGR Platform | Consultant | Worley | 6497-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR | [5 empty] | RFC | 2026-05-30 | 2026-05-30 | RFC | 6497-BESS-SITE-T-0040 |  | 2026-06-08 | 2026-06-08 | RFC | 6497-BESS-SITE-T-0043 | [41 empty] | E
263 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | LCR Platform | Consultant | Worley | 6497-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR | [5 empty] | Cat. -I | 2026-04-09 | 2026-04-09 | Cat. -I | 6497-BESS-SITE-T-0026 | [46 empty] | E
264 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | CSS | Consultant | Worley | 6497-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS | [5 empty] | RFC | 2026-05-02 | 2026-05-02 | Cat. -I | 6497-BESS-SITE-T-0029 |  | 2026-08-12 | 2026-08-12 | RFC | 6497-BESS-SITE-T-0074 | [41 empty] | E
265 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Consultant | Worley | 6497-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document |  |  |  | Cat. -I | 2026-06-12 | 2026-06-12 | Cat. -I | 6497-BESS-SITE-T-0047 | [46 empty] | E
266 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Consultant | Worley | 6497-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
267 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Harmonic Filter | Consultant | Worley | 6497-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document |  |  |  | Cat. -I | 2026-07-27 | 2026-07-28 | Cat. -I | 6497-BESS-SITE-T-0066 | [46 empty] | E
268 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification | [5 empty] | RFC | 2026-06-09 | 2026-06-10 | RFC | 6497-BESS-SITE-T-0045 | [46 empty] | E
269 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). | [5 empty] | Under Review | 2026-08-17 |  | Under Review | [47 empty] | E
270 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Existing PSS Modification | Consultant | Worley | 6497-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
271 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
272 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
273 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
274 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
275 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  |  |  |  | Not Submitted | [50 empty] | I
276 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS |  |  | 2026-04-06 |  |  | Cat. -I | NR | 2026-08-10 | Cat. -I | 6497-BESS-SITE-T-0073 | [46 empty] | I
277 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-02 | 2026-06-02 | Cat. -IV_Star | 6497-BESS-SITE-T-0041 |  | 2206-06-23 | 2026-07-01 | Cat. -IV_Star | 6497-BESS-SITE-T-0053 | [41 empty] | I
278 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | EMS | Consultant | Worley | 6497-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-04 | 2026-06-04 | Cat. -IV_Star | 6497-BESS-SITE-T-0042 |  | 2026-07-27 | 2026-07-28 | Cat. -IV_Star | 6497-BESS-SITE-T-0067 | [41 empty] | I
279 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Fire Fighting | Consultant | Worley | 6497-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 09 BESS PLANT | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
280 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | ROAD | Consultant | Worley | 6497-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-04-16 |  |  | Cat. -I | NR |  |  |  |  | 2026-05-07 | 2026-05-07 | Cat. -I | 6497-BESS-SITE-T-0031 |  | 2026-05-09 | 2026-05-11 | Cat. -I | 6497-BESS-SITE-T-0032 | [36 empty] | C
| PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Coupling Transformer | Consultant | Worley | 6497-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
281 | PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Fire Fighting | Vendor | ATPL | 6497-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | 2026-07-14 | 2026-07-14 | RFC | 6497-BESS-SITE-T-0057 |  | 2026-08-07 | 2026-08-07 | RFC | 6497-BESS-SITE-T-0071 | [41 empty] | E
| PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Fire Fighting | Vendor | ATPL | 6497-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS09_Adani Green Energy 27 A Limited (AGE27AL) | Fire Fighting | Vendor | ATPL | 6497-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | RFC | 2026-07-14 | 2026-07-14 | RFC | 6497-BESS-SITE-T-0057 | [46 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 2 | 0.8811%
[5 empty] | RFC |  | 37 | 16.3%
[5 empty] | Cat. -I |  | 53 | 23.35%
[5 empty] | Cat. -I_Star |  | 11 | 4.846%
[5 empty] | Cat. -II |  | 4 | 1.762%
[5 empty] | Cat. -III |  | 0 | 0%
[5 empty] | Cat. -IV |  | 43 | 18.94%
[5 empty] | Cat. -IV_Star |  | 2 | 0.8811%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 152 | 66.96%
[5 empty] | Not Submitted |  | 75 | 33.04%
[5 empty] | Grand Total |  | 227 | 100%

## PSS08B
PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10
1 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing | 2026-05-21 |  |  | Under Review | 2026-05-23 | 2026-06-15 | Cat. -I_Star |  |  | 2026-06-29 |  | Under Review | [42 empty] | E
2 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing | 2026-05-21 |  |  | Cat. -I | 2026-05-23 | 2026-06-15 | Cat. -I | [47 empty] | E
3 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing | 2026-05-21 |  |  | Cat. -I | 2026-05-23 | 2026-06-15 | Cat. -I | [47 empty] | E
4 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-V-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing | 2026-05-21 |  |  | delete |  |  | delete | [47 empty] | E
5 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document | 2026-05-21 |  |  | Cat. -I | 2026-05-23 | 2026-06-15 | Cat. -I | [47 empty] | E
6 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N3-TESL-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document | 2026-05-21 |  |  | Cat. -IV | 2026-05-23 | 2026-06-15 | Cat. -IV | [47 empty] | E
11 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N3-ORNT-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | 2026-06-03 | 2026-06-09 | Cat. -I |  | Submitted by mail | NR | 2026-06-29 | Cat. -I | [42 empty] | E
10 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N3-ORNT-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | 2026-06-03 | 2026-06-09 | Cat. -I |  | Submitted by mail | [45 empty] | E
7 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N3-ORNT-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0005 | NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Cat. -I | 2026-06-03 | 2026-06-09 | Cat. -I |  | Submitted by mail | [45 empty] | E
12 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N3-ORNT-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Cat. -IV | 2026-06-03 | 2026-06-09 | Cat. -IV |  | Submitted by mail | [45 empty] | E
13 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N3-ORNT-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | 2026-06-03 | 2026-06-09 | Cat. -I |  | Submitted by mail | [45 empty] | E
14 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
15 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
16 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
17 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
18 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
19 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
20 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I | [47 empty] | E
21 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
22 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
23 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
24 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
25 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
26 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
27 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
28 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
29 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
30 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
31 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
32 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
33 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
34 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
35 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 document number "51N3-GRTP-BTR-LCO-DE-R-0001" mentioned innthe document | [45 empty] | E
36 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
37 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
38 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 document number "51N3-GRTP-BTR-GEN-DE-E-0003" mentioned innthe document | [45 empty] | E
39 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
40 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | M
41 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 16.04.2026 | [45 empty] | M
42 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | M
43 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
44 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
45 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
46 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
47 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
48 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-02-28 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
49 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
50 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
51 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
52 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
53 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Great Power | 51N3-GRTP-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-02-28 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
54 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
55 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
56 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
57 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
58 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Tinkle Khalasi_18.04.2026 | [45 empty] | E
59 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
60 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
61 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
62 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
63 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
64 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
65 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
66 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
67 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
68 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
69 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
70 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | I
71 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunalkumar Patel on 23.06.2026 | [45 empty] | I
72 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 24.06.2026 | [45 empty] | I
73 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | I
74 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0002 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 23.06.2026 | [45 empty] | I
75 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
76 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
77 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
78 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
79 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
80 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
81 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -III |  |  | Cat. -III |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
82 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0003 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -III |  |  | Cat. -III |  | Document received by Mr. Krunalkumar Patel on 29.04.2026 | [45 empty] | E
83 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 24.06.2026 | [45 empty] | E
84 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
85 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
86 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
87 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | SINENG | 51N3-SING-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
88 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Vendor | Akshar | 51N3-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing | 2026-01-31 |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
89 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT Panel-Outdoor | Vendor | Symatic | 51N3-SYMC-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | 2026-05-21 | 2026-05-21 | Cat. -I | XXXX-BESS-SITE-T-0001 |  | 2026-08-11 | 2026-08-11 | Cat. -I |  | Rev.05 | [40 empty] | E
90 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | ACDB | Vendor | Prima Automation | 51N3-PRMA-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) |  |  | 2026-01-28 |  |  | Cat. -I | NR | 2026-06-24 | Cat. -I |  |  | NR | 2026-07-03 | Cat. -I |  | Rev.07 | [40 empty] | E
91 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Vendor | 51N3-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
92 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT Cable | Vendor | Vendor | 51N3-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
93 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT Cable | Vendor | Vendor | 51N3-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
94 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LT Cable | Vendor | Vendor | 51N3-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
95 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LT Cable | Vendor | Vendor | 51N3-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
96 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control Cable | Vendor | Vendor | 51N3-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
97 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Opteical fiber cable | Vendor | Vendor | 51N3-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
98 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N3-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
99 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N3-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
100 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N3-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
101 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N3-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
102 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0001 | 51H2-E-EMS-EMS-DE-Q-V-0001 | Datasheet for Controller and its components | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
103 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0002 | 51H2-E-EMS-EMS-DE-I-V-0001 | Datasheet for I/O Module (AI/AO/DI/DO) | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
104 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0003 | 51H2-E-EMS-EMS-DE-D-V-0001 | Datasheet for Engineering Server / Operator Workstation / Monitor | Approval | Document | 2026-10-07 |  |  | Not Submitted | [50 empty] | I
105 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0004 | 51H2-E-EMS-EMS-DE-D-V-0002 | Datasheet for Printers | Approval | Document | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
106 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0005 | 51H2-E-EMS-EMS-DE-O-V-0001 | Datasheet for Cisco Network Switch | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
107 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0006 | 51H2-E-EMS-EMS-DE-O-V-0002 | Datasheet of DO Relay | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
108 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0007 | 51H2-E-EMS-EMS-DE-I-V-0002 | Datasheet of GPS | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
109 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0008 | 51H2-E-EMS-EMS-DE-E-V-0001 | Datasheet of Console Desk & Printer Table | Approval | Drawing | 2026-04-07 |  |  | Not Submitted | [50 empty] | I
110 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0009 | 51H2-E-EMS-EMS-DE-D-V-0003 | Datasheet of 55' LED | Approval | Document | 2026-04-07 |  |  | Not Submitted | [50 empty] | I
111 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0010 | 51H2-E-EMS-EMS-DE-O-V-0003 | Data Sheet of Link Interface Unit | Approval | Drawing | 2026-04-07 |  |  | Not Submitted | [50 empty] | I
112 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0011 | 51H2-E-EMS-EMS-DE-E-V-0002 | Data Sheet of Patch Panel and Patch Chords (for RJ45 and FO) | Approval | Drawing | 2026-04-07 |  |  | Not Submitted | [50 empty] | I
113 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0012 | 51H2-E-EMS-EMS-DE-O-V-0004 | Datasheet of DR PC and Monitor | Information | Drawing | 2026-10-07 |  |  | Not Submitted | [50 empty] | I
114 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0013 | 51H2-E-EMS-EMS-DE-I-V-0003 | Datasheet of Firewall | Approval | Drawing | 2026-03-07 |  |  | Not Submitted | [50 empty] | I
115 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0014 | 51H2-E-EMS-EMS-DE-I-V-0004 | Datasheet of Power Supply | Approval | Drawing | 2026-05-07 |  |  | Not Submitted | [50 empty] | I
116 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0015 | 51H2-E-EMS-EMS-DE-S-V-0001 | Datasheet of Serial Converter | Approval | Drawing | 2026-05-07 |  |  | Not Submitted | [50 empty] | I
117 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0016 | 51H2-E-EMS-EMS-DE-D-V-0004 | Datasheet of OGS/PwCS Server | Approval | Document | 2026-10-07 |  |  | Not Submitted | [50 empty] | I
118 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0017 | 51H2-E-EMS-EMS-DE-M-V-0001 | Datasheet of NAS | Information | Document | 2026-08-07 |  |  | Not Submitted | [50 empty] | I
119 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0018 | 51H2-E-EMS-EMS-DE-O-V-0005 | Datasheet of KVM | Information | Drawing | 2026-08-07 |  |  | Not Submitted | [50 empty] | I
120 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0019 | 51H2-E-EMS-EMS-DE-C-V-0001 | Datasheet of Industrial Switch | Approval | Document | 2026-08-07 |  |  | Not Submitted | [50 empty] | I
121 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-Q-0001 | 51H2-E-EMS-EMS-DE-S-V-0002 | System Architecture | Approval | Document | 2026-07-15 |  |  | Not Submitted | [50 empty] | I
122 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-G-0001 | 51H2-E-EMS-EMS-DE-I-V-0005 | EMS Control Cabinet Drawings (GA/IA) | Approval | Document | 2026-07-15 |  |  | Not Submitted | [50 empty] | I
123 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-O-0001 | 51H2-E-EMS-EMS-DE-Q-V-0002 | EMS Cabinet Power Consumption and Heat Dissipation | Approval | Document | 2026-07-15 |  |  | Not Submitted | [50 empty] | I
124 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-E-0001 | 51H2-E-EMS-EMS-DE-D-V-0005 | Wiring Scheme for IO Signals | Approval | Document | 2026-10-07 |  |  | Not Submitted | [50 empty] | I
125 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-B-0001 | 51H2-E-EMS-EMS-DE-D-V-0006 | Bill of Quantity (H/w + S/w) | Approval | Document | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
126 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-E-0002 | 51H2-E-EMS-EMS-DE-N-V-0001 | Panel Grounding Scheme | Approval | Document | 2026-07-15 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-D-0020 |  | I/O List |  |  | 2026-07-15 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-M-0001 |  | Operation and Maintenance Manual |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-GEN-DI-I-0001 |  | Interconnection Detail drawing |  |  | 2026-07-25 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-S-0001 |  | Functional Design Specification |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-E-0001 |  | Signal exchange signal |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-I-0001 |  | Control Logic PDF |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-O-0001 |  | SCADA HMI Screens PDF |  |  | 2026-07-25 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-O-0002 |  | FAT Procedure |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-O-0003 |  | SAT Procedure |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-M-0001 |  | Software Manuals (Softcopy) |  |  | 2026-07-17 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-O-0004 |  | Pre-Commissioning and Commissioning Test Procedure |  |  | 2026-07-17 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-SCD-DI-D-0001 |  | IP List |  |  | 2026-07-17 |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Emerson | 51N3-EMSN-EMS-OTH-DI-S-0001 |  | Cyber Security specifciation |  |  | 2026-07-20 |  |  | Not Submitted | [50 empty] | I
127 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0001 |  | General Arrangement Layout Drawing | [5 empty] | Not Submitted | [50 empty] | E
128 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0002 | 51H2-E-HFL-HFL-DE-G-V-0001 | Drawing and GTP for Series Reactors | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
129 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0003 | 51H2-E-HFL-HFL-DE-G-V-0002 | Drawing and GTP for Off Load Isolator | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
130 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0004 | 51H2-E-HFL-HFL-DE-G-V-0003 | Drawing and GTP for NCT | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
131 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0005 | 51H2-E-HFL-HFL-DE-G-V-0004 | Drawing and GTP for Lightning Arrestor | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
132 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0001 | 51H2-E-HFL-HFL-DE-D-V-0001 | Data sheet for Termination kit | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
133 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-E-0001 | 51H2-E-HFL-HFL-DE-E-V-0001 | Single Line Diagram | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
134 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0002 | 51H2-E-HFL-HFL-DE-D-V-0002 | Data sheet for Control Cable | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
135 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0006 | 51H2-E-HFL-HFL-DE-G-V-0005 | Drawing and GTP for Post Insulators | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
136 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-C-0001 | 51H2-E-HFL-HFL-DE-C-V-0001 | Design Calculation sheet for Harmonic Filter | Approval | Document |  |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
137 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0007 | 51H2-E-HFL-HFL-DE-G-V-0006 | Drawing and GTP for MV Capacitors | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
138 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0008 | 51H2-E-HFL-HFL-DE-G-V-0007 | Drawing and GTP for Damping Resistor | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
139 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DC-L-0001 |  | Equipment Foundation Layout Drawing | [5 empty] | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
140 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-G-0009 |  | GA Earth Matt Layout Drawing | [5 empty] | Not Submitted | [50 empty] | E
141 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0003 | 51H2-E-HFL-HFL-DE-D-V-0003 | Data sheet for DWC pipe | [5 empty] | Not Submitted | [50 empty] | E
142 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0004 | 51H2-E-HFL-HFL-DE-D-V-0004 | Drawing & Data sheet for Earth Pit | [5 empty] | Not Submitted | [50 empty] | E
143 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-I-0001 |  | 12000KVAR,33KV,3PH,50HZ.OUTDOOR FIXED TYPE TUNED REACTIVE POWER COMPENSATION SCHEME. | [5 empty] | Not Submitted | [50 empty] | E
144 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter |  | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0005 | 51H2-E-HFL-HFL-DE-D-V-0005 | Data sheet for GI Earth Flats | [5 empty] | Not Submitted | [50 empty] | E
145 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Vendor | 51N3-XXXX-HFL-GEN-DE-D-0006 | 51H2-E-HFL-HFL-DE-D-V-0006 | Data sheet for Lighting Pole | [5 empty] | Not Submitted | [50 empty] | E
146 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0001 |  | Technical Datasheet for GUI for Fire Detection System with workstation | Approval |  |  |  |  | Not Submitted | [50 empty] | I
147 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0002 |  | Technical Datasheet for Repeater Alarm Panel (RAP). | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
148 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0003 |  | Technical Datasheet of Local Fire Alarm Panel (LFAP) | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
149 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0004 |  | Technical Datasheet of Main Fire Alarm Panel (MFAP) | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
150 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0005 |  | Technical Datasheet for Smoke Detector with Base | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
151 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0006 |  | Technical Datasheet for Addressable Manual Call Point (Indoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
152 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0007 |  | Technical Datasheet for Weatherproof Manual Call Point (Outdoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
153 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0008 |  | Technical Datasheet for Addressable Monitor Module | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
154 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0009 |  | Technical Datasheet for Addressable Control Module | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
155 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0010 |  | Technical Datasheet for Addressable Hooter cum strobe (Indoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
156 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0011 |  | Technical Datasheet for Weatherproof Hooter cum strobe (outdoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
157 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0012 |  | Technical Datasheet for Network Switch | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
158 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0013 |  | Technical Datasheet for Isolator Module | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
159 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0014 |  | Technical Datasheet for Fire Alarm Cable - 2 core * 1.5sq.mm FRLS ARM | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
160 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0015 |  | Technical Datasheet for Power Cable - 3 core * 2.5sq.mm ARM | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
161 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0016 |  | Technical Datasheet for Fire Extinguisher 6 Kgs .ABC type (Portable ) | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
162 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-D-0017 |  | Technical Datasheet for Fire Extinguisher 9 Kgs.CO2 type Trolley arrangement (Portable ) | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
163 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-G-0001 |  | G.A of Fire Alarm Panel | Information |  | 15.01.2026 |  |  | Not Submitted | [50 empty] | I
164 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-O-0001 |  | TYPICAL MOUNTING DETAILS FOR DEVICES & MODULES | Information |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
165 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-L-0001 |  | Complete Layout Drawing of FDA System- PSS 8 | Approval |  | 16.01.2026 |  |  | Cat. -I_Star | NR | 2026-02-06 | Cat. -I_Star | 51N3-BESS-SITE-T-0004 | [46 empty] | I
166 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-L-0002 |  | Complete Layout Drawing of FIRE EXTINGUISHER System- PSS 8 | Approval |  | 20.02.2026 |  |  | Not Submitted | [50 empty] | I
167 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-E-0001 |  | Schematic Diagram of fire alarm system - PSS 8 | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
168 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-B-0001 |  | Cable Schedule - PSS 8 | Information |  | 17.01.2026 |  |  | Not Submitted | [50 empty] | I
169 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N3-JHCI-FDS-FAS-DI-I-0001 |  | Cause & Effect Diagram | Information |  | 25.01.2026 |  |  | Not Submitted | [50 empty] | I
170 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N3-ADNI-CDN-CTF-DC-V-0001 |  | Coupling Transformer Foundation Layout and RC Details-Ornet | Approval | Drawing | 2026-06-12 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N3-ADNI-CDN-CTF-DC-V-0005 |  | LAYOUT FOR HT-LT PANEL (PCS) SUPPORTING PLATFROM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51N3-BESS-SITE-T-0002 |  | 2026-02-18 | 18-02-20-26 | RFC | 51N3-BESS-SITE-T-0007 | [41 empty] | C
170 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N3-ADNI-CDN-CTF-DC-V-0007 |  | Coupling Transformer Foundation Layout and RC Details-Tesla | Approval | Drawing |  |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51N3-BESS-SITE-T-0002 |  | 2026-03-05 | 2026-03-06 | RFC | 51N3-BESS-SITE-T-0017 |  | 2026-07-11 | 2026-07-13 | RFC | 51N3-BESS-SITE-T-0048 | [36 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N3-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS11) TYPICAL FOOTING, PRECAST DRAWING | Approval |  |  |  |  | RFC | 2026-03-19 | 2026-03-19 | RFC | 51N3-BESS-SITE-T-0020 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N3-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval |  |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 51N3-BESS-SITE-T-0048 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container | In-House | In-house | 51N3-ADNI-CDN-BCN-DC-V-0001 |  | Precast foundation drawing for Battery container-Great Power | Approval | Drawing | 2026-01-30 |  |  | RFC | 2026-02-02 | 2026-02-03 | RFC | 51N3-BESS-SITE-T-0001 |  | 2026-02-19 | 2026-02-19 | RFC | 51N3-BESS-SITE-T-0009 | [41 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | In-House | In-house | 51N3-ADNI-CDN-LCR-DC-V-0001 |  | LAYOUT FOR LOCAL CONTROL ROOM / ELECTRICAL ROOM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51N3-BESS-SITE-T-0002 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | In-House | In-house | 51N3-ADNI-CDN-HGR-DC-V-0001 |  | LAYOUT FOR OUTDOOR SWITCHGEAR ROOM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51N3-BESS-SITE-T-0002 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | In-House | In-house | 51N3-ADNI-CDN-ROD-DC-L-0001 |  | BESS APPROACH ROAD AND CROSS SECTION | Approval | Drawing | 2026-02-20 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | In-House | In-house | 51N3-ADNI-CDN-ROD-DC-L-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-02-20 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast | In-House | In-house | 51N3-ADNI-CDN-HML-DC-L-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 51N3-BESS-SITE-T-0010 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast | In-House | In-house | 51N3-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 51N3-BESS-SITE-T-0012 | [46 empty] | E
164 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Overall-FDN | Consultant | Worley | 51N3-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | C
165 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Shed | Consultant | Worley | 51N3-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-08 | Approval | Drawing |  |  |  | Cat. -I | 2026-03-05 | 2026-03-06 | Cat. -I | 51N3-BESS-SITE-T-0016 | [46 empty] | S
166 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N3-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-03-16 | 2026-03-16 | Cat. -IV | 51N3-BESS-SITE-T-0018 |  | NR |  |  |  |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | [36 empty] | C
167 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Foundation | Consultant | Worley | 51N3-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
168 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N3-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | [46 empty] | C
169 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N3-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) | [5 empty] | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 51N3-BESS-SITE-T-0056 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform |  | Worley | 51N3-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-8B | [5 empty] | Not Submitted | [50 empty] | S
170 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
172 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing |  |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | Approval | Drawing |  |  |  | Cat. -I_Star | NR |  |  |  |  | 2026-04-17 | 2026-04-18 | Cat. -I | 51N3-BESS-SITE-T-0024 |  | 2026-07-11 | 2026-07-11 | Cat. -I | 51N3-BESS-SITE-T-0047 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0054 | [31 empty] | C
173 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | [46 empty] | C
174 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room | [5 empty] | RFC | 2026-07-25 | 2026-07-25 | RFC | 51N3-BESS-SITE-T-0052 | [46 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform |  | Worley | 51N3-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-8B | [5 empty] | Cat. -I | 2026-02-24 | 2026-02-25 | Cat. -I | 51N3-BESS-SITE-T-0011 | [46 empty] | S
175 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N3-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-02-27 | 2026-02-27 | Cat. -I | 51N3-BESS-SITE-T-0014 |  | 2026-07-11 | 2026-07-11 | Cat. -I_Star | 51N3-BESS-SITE-T-0046 | Drawing number 51I4-WRLY-EDN-HGR-DC-V-0001 is mentioned in the drawing. As discussed with Mr. Punith, drawing number will be change in the next revision_11.07.2026 | [40 empty] | C
171 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N3-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
176 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N3-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room | [5 empty] | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 51N3-BESS-SITE-T-0058 | [46 empty] | C
177 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N3-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | [46 empty] | C
178 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Consultant | Worley | 51N3-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing |  |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 51N3-BESS-SITE-T-0003 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 51N3-BESS-SITE-T-0011 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 51N3-BESS-SITE-T-0025 | [36 empty] | C
179 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container-CATL | Consultant | Worley | 51N3-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
180 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N3-WRLY-OEN-CTF-DC-U-0001 |  | Cable support near coupling transformer area | Approval | Drawing |  |  |  | Cat. -I_Star | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N3-BESS-SITE-T-0053 | [46 empty] | C
181 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N3-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
182 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N3-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 51N3-BESS-SITE-T-0008 | [46 empty] | C
182 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | Consultant | Worley | 51N3-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
183 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | SECURITY BARRACK | Consultant | Worley | 51N3-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing |  |  |  | delete |  |  | delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
184 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast | Consultant | Worley | 51N3-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Rupak, not in worley scope._21.02.2026 | [45 empty] | C
185 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
186 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
187 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
188 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N3-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document |  |  |  | Not Submitted | [50 empty] | C
189 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Overall SLD | Consultant | Worley | 51N3-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing |  |  |  | RFC | 2026-02-27 | 2026-02-27 | RFC | 51N3-BESS-SITE-T-0015 |  | 2026-06-10 | 2026-06-10 | RFC | 51N3-BESS-SITE-T-0040 | [41 empty] | E
190 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Aux Plant SLD | Consultant | Worley | 51N3-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD | [5 empty] | Cat. -I | 2026-04-01 | 2026-04-02 | Cat. -I | 51N3-BESS-SITE-T-0021 | [46 empty] | E
191 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Ovearall Layout - Electrical | Consultant | Worley | 51N3-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing |  |  |  | RFC | 2026-07-22 | 2026-07-22 | RFC | 51N3-BESS-SITE-T-0049 | Due to crane pad implementation at site . So, not required new revision | 2026-08-13 | 14-02-2026 13-08-2026 | RFC | 51N3-BESS-SITE-T-0006 51N3-BESS-SITE-T-0061 | [41 empty] | E
192 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Ovearall Layout - Electrical | Consultant | Worley | 51N3-WRLY-OEN-BES-DE-L-0002 |  | Layout Options | [5 empty] | Not Submitted | [50 empty] | E
193 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Overall Equipment Layout - Electrical | Consultant | Worley | 51N3-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) | [5 empty] | RFC | NR | 2026-02-13 | RFC | 51N3-BESS-SITE-T-0005 | [46 empty] | E
194 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Earthing Layout | Consultant | Worley | 51N3-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing |  |  |  | RFC | 21-05-2026 02-06-2026 | 21-05-2026 02-06-2026 | RFC | 51N3-BESS-SITE-T-0029 51N3-BESS-SITE-T-0037 |  | 2026-06-25 | 2026-06-25 | RFC | 51N3-BESS-SITE-T-0043 | [41 empty] | E
195 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Earthing Design | Consultant | Worley | 51N3-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
196 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Lightning Layout | Consultant | Worley | 51N3-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing |  |  |  | RFC | 2026-05-30 | 2026-05-30 | RFC | 51N3-BESS-SITE-T-0035 |  | 2026-06-25 | 2026-06-25 | RFC | 51N3-BESS-SITE-T-0044 | [41 empty] | E
197 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Lightning design | Consultant | Worley | 51N3-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
198 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Illumination | Consultant | Worley | 51N3-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing |  |  |  | RFC | 2026-05-21 | 2026-05-21 | RFC | 51N3-BESS-SITE-T-0032 |  | 2026-06-25 | 2026-06-25 | RFC | 51N3-BESS-SITE-T-0044 | [41 empty] | E
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Illumination | Consultant | Worley | 51N3-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | RFC | NR |  |  |  |  | 2026-06-25 | 2026-06-25 | RFC | 51N3-BESS-SITE-T-0044 | [41 empty] | E
199 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N3-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS | [5 empty] | Not Submitted | [50 empty] | E
200 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N3-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing |  |  |  | RFC | 2026-05-22 | 2026-05-22 | RFC | 51N3-BESS-SITE-T-0030 |  | 2026-07-24 | 2026-07-24 | RFC | 51N3-BESS-SITE-T-0051 |  | 2026-08-12 | 2026-08-12 | RFC | 51N3-BESS-SITE-T-0060 | [36 empty] | E
201 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N3-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing |  |  |  | RFC | 2026-05-22 | 2026-05-22 | RFC | 51N3-BESS-SITE-T-0030 |  | 2026-07-24 | 2026-07-24 | RFC | 51N3-BESS-SITE-T-0051 |  | 2026-08-12 | 2026-08-12 | RFC | 51N3-BESS-SITE-T-0060 | [36 empty] | E
202 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N3-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-30 | 2026-05-30 | Cat. -IV | 51N3-BESS-SITE-T-0034 |  | 2206-06-18 | 2026-06-18 | RFC | 51N3-BESS-SITE-T-0041 | [41 empty] | E
203 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N3-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing |  |  |  | RFC | 17-03-2026 20.05.2026 | 17-03-2026 20.05.2026 | RFC | 51N3-BESS-SITE-T-0019 51N3-BESS-SITE-T-0028 | As per the discussed with Mr. Kaushal Patel_20.05.2026 & considered 20.05.2026 documents | 16-04-2026 24-07-2026 | 16-04-2026 24-07-2026 | RFC | 51N3-BESS-SITE-T-0023 51N3-BESS-SITE-T-0051 | As per the discussed with Mr. Kaushal Patel document is deleted_20.05.2026 | [40 empty] | E
204 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N3-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing |  |  |  | RFC | 17-03-2026 20.05.2026 | 17-03-2026 20.05.2026 | RFC | 51N3-BESS-SITE-T-0019 51N3-BESS-SITE-T-0028 | As per the discussed with Mr. Kaushal Patel_20.05.2026 & considered 20.05.2026 documents | 16-04-2026 24-07-2026 | 16-04-2026 24-07-2026 | RFC | 51N3-BESS-SITE-T-0023 51N3-BESS-SITE-T-0051 | As per the discussed with Mr. Kaushal Patel document is deleted_20.05.2026 | [40 empty] | E
205 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N3-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-20 | 2026-05-20 | RFC | 51N3-BESS-SITE-T-0028 |  | 2026-06-22 | 2026-06-23 | RFC | 51N3-BESS-SITE-T-0042 | [41 empty] | E
206 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N3-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
207 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Cable Sizing | Consultant | Worley | 51N3-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
208 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Equipment Sizing | Consultant | Worley | 51N3-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
209 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N3-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | [5 empty] | RFC | 22-05-2026 29-05-2026 | 23-05-2026\ 29-05-2026 | RFC | 51N3-BESS-SITE-T-0031 51N3-BESS-SITE-T-0033 | [46 empty] | E
210 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N3-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) | [5 empty] | RFC | 22-05-2026 29-05-2026 | 23-05-2026\ 29-05-2026 | RFC | 51N3-BESS-SITE-T-0031 51N3-BESS-SITE-T-0033 |  | 2026-08-05 | 2026-08-05 | RFC | 51N3-BESS-SITE-T-0057 | [41 empty] | E
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N3-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N3-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
211 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N3-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document |  |  |  | RFC | 2026-05-22 | 2026-05-22 | RFC | 51N3-BESS-SITE-T-0030 |  | 2026-08-05 | 2026-08-05 | RFC | 51N3-BESS-SITE-T-0057 |  | 2026-08-12 | 2026-08-12 | RFC | 51N3-BESS-SITE-T-0060 | [36 empty] | E
212 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N3-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. | [5 empty] | Not Submitted | [50 empty] | E
213 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N3-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR | [5 empty] | RFC | 2026-06-03 | 2026-06-03 | RFC | 51N3-BESS-SITE-T-0039 | [46 empty] | E
214 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N3-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR | [5 empty] | Cat. -I | 2026-04-09 | 2026-04-09 | Cat. -I | 51N3-BESS-SITE-T-0022 | [46 empty] | E
215 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Consultant | Worley | 51N3-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS | [5 empty] | RFC | 2026-05-02 | 2026-05-02 | Cat. -I | 51N3-BESS-SITE-T-0026 |  | 2026-08-12 | 2026-08-12 | RFC | 51N3-BESS-SITE-T-0059 | [41 empty] | E
216 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N3-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
217 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N3-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
218 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N3-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
219 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification | [5 empty] | Not Submitted | [50 empty] | E
220 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). | [5 empty] | Not Submitted | [50 empty] | E
221 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N3-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
222 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
223 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
224 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
225 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
226 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  |  |  |  | Not Submitted | [50 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS |  |  | 2026-04-06 |  |  | Cat. -I_Star | NR |  |  |  |  | NR |  |  |  |  | 2026-07-23 | 2026-07-23 | Cat. -I_Star | 51N3-BESS-SITE-T-0050 | [36 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-02 | 2026-06-02 | Cat. -IV_Star | 51N3-BESS-SITE-T-0036 |  | 2026-06-23 | 2026-07-01 | Cat. -IV_Star | 51N3-BESS-SITE-T-0045 |  | 2026-07-27 | 2026-07-28 | Cat. -IV_Star | 51N3-BESS-SITE-T-0055 | [36 empty] | I
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N3-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-02 | 2026-06-02 | Cat. -IV_Star | 51N3-BESS-SITE-T-0038 |  | NR |  |  |  |  | 2026-07-27 | 2026-07-28 | Cat. -IV_Star | 51N3-BESS-SITE-T-0055 | [36 empty] | I
227 | PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Consultant | Worley | 51N3-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 08B BESS PLANT | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD | Consultant | Worley | 51N3-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-05-05 |  |  | Cat. -I | NR |  |  |  |  | 2026-05-09 | 2026-05-11 | Cat. -I | 51N3-BESS-SITE-T-0027 | [41 empty] | C
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N3-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N3-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | NR | 2026-08-24 | RFC | 51N3-BESS-SITE-T-0062 | [46 empty] | E
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N3-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS08B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N3-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 1 | 0.4184%
[5 empty] | RFC |  | 30 | 12.55%
[5 empty] | Cat. -I |  | 35 | 14.64%
[5 empty] | Cat. -I_Star |  | 19 | 7.95%
[5 empty] | Cat. -II |  | 5 | 2.092%
[5 empty] | Cat. -III |  | 2 | 0.8368%
[5 empty] | Cat. -IV |  | 42 | 17.57%
[5 empty] | Cat. -IV_Star |  | 2 | 0.8368%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 136 | 56.9%
[5 empty] | Not Submitted |  | 103 | 43.1%
[5 empty] | Grand Total |  | 239 | 100%

## PSS10B
PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10
1 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-G-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | [41 empty] | E
2 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-G-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | [41 empty] | E
3 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-G-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | NR | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [41 empty] | E
4 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-G-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
5 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-G-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
6 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | [41 empty] | E
7 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Ornet | 51N2-ORNT-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Cat. -IV | NR | 2026-02-26 | Cat. -IV | XXXX-BESS-SITE-T-0001 | [46 empty] | E
8 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-G-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | rev.02 | [45 empty] | E
9 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-G-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | reV.01 | [45 empty] | E
10 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-G-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
11 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-G-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
12 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-G-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
13 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | [46 empty] | E
14 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Vendor | Tesla | 51N2-TESL-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
15 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
16 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
17 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
18 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
19 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
20 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
21 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
22 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
23 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
24 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
25 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
26 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
27 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 17.03.2026 | [45 empty] | E
28 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
29 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
30 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
31 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
32 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
33 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
34 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
35 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
36 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
37 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
38 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
39 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
40 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
41 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
42 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
43 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
44 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
45 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
46 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
47 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
48 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
49 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
50 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
51 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
52 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
53 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
54 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery | Vendor | Jinco | 51N2-JNCO-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
55 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
56 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
57 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
58 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 16.04.2026 | [45 empty] | E
59 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
60 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
61 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
62 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
63 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
64 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
65 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
66 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
67 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
68 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
69 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
70 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
71 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
72 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
73 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | I
74 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
75 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0002 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
76 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
77 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
78 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
79 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
80 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
81 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
82 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
83 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0003 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
84 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
85 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Under Review |  |  | Under Review |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
86 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
87 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
88 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS | Vendor | Inovance | 51N2-INOV-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
89 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Vendor | Akshar | 51N2-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing |  |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
90 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT Panel-Outdoor | Vendor | Trisqure | 51N2-TSQR-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | NR | 2026-04-30 | Cat. -I |  | Rev.14 | NR | 2026-05-30 | Cat. -I |  | Rev.15 | NR | 2026-06-10 | Cat. -I |  | Rev.16 | NR | 2206-07-31 | Cat. -I |  | Rev.20 | [30 empty] | E
91 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ACDB | Vendor | Active Engineers | 51N2-ACTE-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) | [5 empty] | Cat. -I | NR |  |  |  |  | NR | 2026-01-22 | Cat. -I | 51I4-BESS-SITE-T-0003 |  | NR |  |  |  |  | NR | 2026-07-03 | Cat. -I |  |  | 2026-07-31 | 2026-07-31 | Cat. -I | [27 empty] | E
92 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Vendor | 51N2-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
93 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT Cable | Vendor | Vendor | 51N2-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
94 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT Cable | Vendor | Vendor | 51N2-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
95 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LT Cable | Vendor | Vendor | 51N2-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
96 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LT Cable | Vendor | Vendor | 51N2-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
97 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control Cable | Vendor | Vendor | 51N2-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
98 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Opteical fiber cable | Vendor | Vendor | 51N2-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
99 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N2-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
100 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N2-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
101 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N2-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
102 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PEB Building | Vendor | Vendor | 51N2-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
103 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-Q-0001 | 51H2-E-EMS-EMS-DE-Q-V-0001 | EMS SCADA System Architecture Drawing | Approval | Drawing | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
104 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-I-0001 | 51H2-E-EMS-EMS-DE-I-V-0001 | EMS Panel Drawing for Central Control Room, Network Panel, Site Level RTU RIO Panel, PCS Plateform RIO Panel, Panel for Ethernet Switches & LIUs | Approval | Drawing | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
105 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-D-0001 | 51H2-E-EMS-EMS-DE-D-V-0001 | EMS System Datasheet - Schneider Components | Approval | Document | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
106 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-D-0002 | 51H2-E-EMS-EMS-DE-D-V-0002 | EMS System Datasheet - IT Hardware Components | Approval | Document | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
107 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-D-0003 | 51H2-E-EMS-EMS-DE-O-V-0001 | EMS System Datasheet - Enclosures Accessories Components | Approval | Drawing | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
108 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-B-0001 | 51H2-E-EMS-EMS-DE-O-V-0002 | Project BOM (Bill of Materials) - Includes Hardware and Software | Approval | Drawing | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
109 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-O-0001 | 51H2-E-EMS-EMS-DE-I-V-0002 | Factory Acceptance Test (FAT) Procedure | Approval | Drawing | 2026-01-10 |  |  | Not Submitted | [50 empty] | E
110 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-O-0002 | 51H2-E-EMS-EMS-DE-E-V-0001 | Site Acceptance Test (SAT) Procedure | Approval | Drawing | 2026-01-23 |  |  | Not Submitted | [50 empty] | E
111 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-I-0002 | 51H2-E-EMS-EMS-DE-D-V-0003 | Logic Diagram for EMS | Approval | Document | 02 week from inputs received from M/s AGEL |  |  | Not Submitted | [50 empty] | E
112 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-E-0001 | 51H2-E-EMS-EMS-DE-O-V-0003 | Panel Grounding Scheme | Approval | Drawing | 13-01-2026* |  |  | Not Submitted | [50 empty] | E
113 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-O-0003 | 51H2-E-EMS-EMS-DE-E-V-0002 | Document Dosier | Information | Drawing | After Site Commissioning |  |  | Not Submitted | [50 empty] | E
114 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-I-0003 | 51H2-E-EMS-EMS-DE-O-V-0004 | EMS Screens & Report Format | Approval | Drawing | 04 week from inputs received from M/s AGEL |  |  | Not Submitted | [50 empty] | E
115 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-S-0001 | 51H2-E-EMS-EMS-DE-I-V-0003 | Functional Design Specification (FDS) | Approval | Drawing | 02 week from inputs received from M/s AGEL |  |  | Not Submitted | [50 empty] | E
116 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-D-0004 | 51H2-E-EMS-EMS-DE-I-V-0004 | IP List | Approval | Drawing | 01 week from approval of System Architecture |  |  | Not Submitted | [50 empty] | E
117 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-M-0001 | 51H2-E-EMS-EMS-DE-S-V-0001 | EMS O&M Manual | Information | Drawing | After Site Commissioning |  |  | Not Submitted | [50 empty] | E
118 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-O-0004 | 51H2-E-EMS-EMS-DE-D-V-0004 | Detailed Erection, Pre-Commissioning and Commissioning Procedure | Information | Document | 07 Days After Successful FAT |  |  | Not Submitted | [50 empty] | E
119 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-C-0001 | 51H2-E-EMS-EMS-DE-M-V-0001 | Heat Dissipation & Load Calculation | Approval | Document | 03 Days After Panel Drawing Approval |  |  | Not Submitted | [50 empty] | E
120 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-S-0002 | 51H2-E-EMS-EMS-DE-O-V-0005 | Cyber Security Specification / Checklist | Approval | Drawing | 2026-01-07 |  |  | Not Submitted | [50 empty] | E
121 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Vendor | Adaptive | 51N2-ADAP-EMS-GEN-DE-N-0001 | 51H2-E-EMS-EMS-DE-C-V-0001 | Complete Documentation of Implemented Protocols Between Various Elements | Information | Document | 2026-01-17 |  |  | Not Submitted | [50 empty] | E
122 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0001 |  | Drawing and GTP for Series Reactors | Information |  | At the time of HOTO |  |  | Cat. -I | NR | 2026-03-24 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
123 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0002 |  | Drawing and GTP for Off Load Isolator | Approval | Document | 21.03.2026 |  |  | Cat. -I | NR | 21-03-2026 15-06-2026 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
124 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0003 |  | Drawing and GTP for NCT | Approval | Document | 21.03.2026 |  |  | Cat. -I | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
125 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0004 |  | Drawing and GTP for Lightning Arrestor | Approval | Document | 21.03.2026 |  |  | Cat. -I | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
126 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-D-0001 |  | Data sheet for Termination kit | Approval | Document | 21.03.2026 |  |  | Cat. -I | 2026-04-02 | 2026-04-07 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
127 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-E-0001 |  | Single Line Diagram | Approval | Document | 24.03.2026 |  |  | Cat. -I | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
128 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-D-0002 |  | Data sheet for Control Cable | Approval | Document | 21.03.2026 |  |  | Cat. -I | 2026-04-02 | 2026-04-07 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
129 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-C-0001 |  | Design Calculation sheet for Harmonic Filter | Approval | Document | 24.03.2026 |  |  | delete | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 |  |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [40 empty] | E
130 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0005 |  | Drawing and GTP for MV Capacitors | Approval | Document | 21.03.2026 |  |  | Cat. -I | NR | 2026-03-24 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
131 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0006 |  | Drawing and GTP for Damping Resistor | Approval | Document | 21.03.2026 |  |  | Not Submitted | [50 empty] | E
132 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-D-0003 |  | Data Sheet of GI Earth Flats | Approval | Document | NA |  |  | Cat. -I | 2026-05-14 | 2026-05-14 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
133 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0007 |  | Drawing & Data sheet for Earth Pit | Approval | Document | 24.03.2026 |  |  | Cat. -I | 2026-04-02 | 2026-04-07 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
134 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-D-0004 |  | Data sheet for DWC Pipe |  |  | 24.03.2026 |  |  | Cat. -I | 2026-04-02 | 2026-04-07 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
135 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DC-L-0001 |  | Equipment Foundation Layout Drawing |  |  | 24.03.2026 |  |  | Not Submitted | [50 empty] | C
136 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0008 |  | GA Earth Matt Layout Drawing |  |  | 21.03.2026 |  |  | Cat. -I | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
137 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DE-L-0009 |  | General Arrangement Layout Drawing |  |  | 21.03.2026 |  |  | Cat. -I | NR | 2026-03-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
138 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Vendor | Clarient | 51N2-CPSL-HFL-GEN-DC-C-0001 |  | Structure calculations |  |  | 21.03.2026 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
141 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0001 |  | Technical Datasheet for GUI for Fire Detection System with workstation | Approval |  | Submitted on 21.03.2026 |  |  | Not Submitted | [50 empty] | I
142 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0002 |  | Technical Datasheet for Repeater Alarm Panel (RAP). | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
143 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0003 |  | Technical Datasheet of Local Fire Alarm Panel (LFAP) | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
144 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0004 |  | Technical Datasheet of Main Fire Alarm Panel (MFAP) | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
145 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0005 |  | Technical Datasheet for Smoke Detector with Base | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
146 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0006 |  | Technical Datasheet for Addressable Manual Call Point (Indoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
147 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0007 |  | Technical Datasheet for Weatherproof Manual Call Point (Outdoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
148 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0008 |  | Technical Datasheet for Addressable Monitor Module | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
149 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0009 |  | Technical Datasheet for Addressable Control Module | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
150 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0010 |  | Technical Datasheet for Addressable Hooter cum strobe (Indoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
151 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0011 |  | Technical Datasheet for Weatherproof Hooter cum strobe (outdoor) | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
152 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0012 |  | Technical Datasheet for Network Switch | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
153 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0013 |  | Technical Datasheet for Isolator Module | Approval |  | 14.01.2026 |  |  | Not Submitted | [50 empty] | I
154 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0014 |  | Technical Datasheet for Fire Alarm Cable - 2 core * 1.5sq.mm FRLS ARM | Approval |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
155 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0015 |  | Technical Datasheet for Power Cable - 3 core * 2.5sq.mm ARM | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
156 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0016 |  | Technical Datasheet for Fire Extinguisher 6 Kgs .ABC type (Portable ) | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
157 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-D-0017 |  | Technical Datasheet for Fire Extinguisher 9 Kgs.CO2 type Trolley arrangement (Portable ) | Approval |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
158 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-G-0001 |  | G.A of Fire Alarm Panel | Information |  | 15.01.2026 |  |  | Not Submitted | [50 empty] | I
159 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-O-0001 |  | TYPICAL MOUNTING DETAILS FOR DEVICES & MODULES | Information |  | 13.01.2026 |  |  | Not Submitted | [50 empty] | I
160 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-L-0001 |  | Complete Layout Drawing of FDA System- PSS 10 | Approval |  | 14.01.2026 |  |  | Cat. -I_Star | NR |  |  |  |  | NR | 2026-02-07 | Cat. -I_Star | 51N2-BESS-SITE-T-0018 | [41 empty] | I
161 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-L-0002 |  | Complete Layout Drawing of FIRE EXTINGUISHER System- PSS 10 | Approval |  | 21.01.2026 |  |  | Not Submitted | [50 empty] | I
162 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-E-0001 |  | Schematic Diagram of fire alarm system - PSS 10 | Approval |  | 09.01.2026 |  |  | Not Submitted | [50 empty] | I
163 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-B-0001 |  | Cable Schedule - PSS 10 | Information |  | 16.01.2026 |  |  | Not Submitted | [50 empty] | I
164 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Deection |  | Johnson Controls | 51N2-JHCI-FDS-FAS-DI-I-0001 |  | Cause & Effect Diagram | Information |  | 25.01.2026 |  |  | Not Submitted | [50 empty] | I
165 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container | In-house | In-house | 51N2-ADNI-CDN-BCN-DC-V-0001 | 51H2-E-CIV-BCN-DC-V-I-0001 | Precast foundation drawing for Battery container-Great Power | Approval | Drawing |  |  |  | RFC | 2025-12-15 | 2025-12-15 | RFC | 51N2-BESS-SITE-T-0001 |  | 2025-12-23 | 2025-12-23 | RFC | 51N2-BESS-SITE-T-0006 | [40 empty] | C | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container | In-house | In-house | 51N2-ADNI-CDN-BCN-DC-V-0003 |  | TYP.FOUNDATION COLUMN BEAM PRECAST DRAWING_JINKO | [5 empty] | RFC | 2026-01-31 | 2026-02-02 | RFC | 51N2-BESS-SITE-T-0013 | [46 empty] | C
166 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container | In-house | In-house | 51N2-ADNI-CDN-BCN-DC-H-0001 | 51H2-E-CIV-BCN-DC-H-I-0001 | Fabrication drawing for Precast foundation drawing for Battery container | Approval | Drawing |  |  |  | RFC | 2026-01-09 | 2026-01-09 | RFC | 51N2-BESS-SITE-T-0009 | [45 empty] | C | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container | In-house | In-house | 51N2-ADNI-CDN-BCN-DC-H-0003 |  | FEBRICATION DRAWING OF BESS FOUNDATION TYPICAL MONOLITHIC BEAM PRECAST DRAWING FOR CONTAINER JINKO (BESS-10B) | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 |  | 2026-02-17 | 2026-02-17 | Cat. -I | 51N2-BESS-SITE-T-0025 | [41 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) |  | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR NIFPS PSS-10B | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 | [46 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-H-0002 |  | ERECTION DRAWING OF COUPLING TRANSFORMER FOUNDATION (FOR TESLA MAKE) TYPICAL FOOTING, PRECAST DRAWING.(PSS9) |  |  | 2026-08-05 |  |  | Cat. -IV | 2026-08-06 | 2026-08-06 | Cat. -IV | 51N2-BESS-SITE-T-0091 | [46 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) |  | In-house | In-house | 51N2-ADNI-CDN-STC-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR STAIRCASE-BCF PSS-10B | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 | [46 empty] | C
167 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Overall-FDN | In-house | In-house | 51N2-ADNI-CDN-CIV-DC-V-0001 | 51H2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | RFC | NR |  |  |  |  | 2025-12-16 | 2025-12-16 | RFC | 51N2-BESS-SITE-T-0002 |  | 2025-12-17 | 2025-12-18 | RFC | 51N2-BESS-SITE-T-0005 |  | 2025-12-23 | 2025-12-23 | RFC | 51N2-BESS-SITE-T-0007 | [30 empty] | C | C
168 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | In-house | In-house | 51N2-ADNI-CDN-ROD-DC-L-0001 | 51H2-E-CIV-ROD-DC-L-I-0001 | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | RFC | 2025-12-29 | 2025-12-29 | RFC | 51N2-BESS-SITE-T-0008 | [45 empty] | C | C
169 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-V-0001 | 51H2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details-Ornet | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 51N2-BESS-SITE-T-0010 |  | 2026-01-21 | 2026-01-21 | RFC | 51N2-BESS-SITE-T-0012 |  | 2025-02-09 | 2026-02-10 | RFC | 51N2-BESS-SITE-T-0020 |  | 2026-02-14 | 2026-02-14 | RFC | 51N2-BESS-SITE-T-0023 | [30 empty] | C | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-V-0005 |  | HT-LT PANEL SUPPORTING PLATFROM R.C.C DETAILS / LAYOUT FOR PCS ROOM FOUNDATION PLAN & SECTION DETAIL | Approval | Drawing |  |  |  | RFC | 2025-12-18 | 2025-12-18 | RFC | 51N2-BESS-SITE-T-0005 |  | 2026-02-06 | 2026-02-06 | RFC | 51N2-BESS-SITE-T-0016 | [41 empty] | C
170 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-V-0007 |  | Coupling Transformer Foundation Layout and RC Details-Tesla | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 51N2-BESS-SITE-T-0010 | [46 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-house | In-house | 51N2-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS10B) TYPICAL FOOTING, PRECAST DRAWING | [5 empty] | RFC | 2026-03-16 | 2026-03-16 | RFC | 51N2-BESS-SITE-T-0035 | [46 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer Station | In-House | In-house | 51N2-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval |  |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 51N2-BESS-SITE-T-0079 | [46 empty] | C
171 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Local Control Room | In-house | In-house | 51N2-ADNI-CDN-LCR-DC-L-0001 | 51H2-E-CIV-LCR-DC-L-I-0001 | Foundation beam Layout for Local Control Room | Approval | Drawing |  |  |  | RFC | 2025-12-17 | 2025-12-17 | RFC | 51N2-BESS-SITE-T-0004 | [45 empty] | C | C
172 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT SGR Buildng | In-house | In-house | 51N2-ADNI-CDN-HGR-DC-L-0001 | 51H2-E-CIV-SGR-DC-L-I-0001 | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | RFC | 2025-12-16 | 2025-12-16 | RFC | 51N2-BESS-SITE-T-0003 |  | 2025-12-17 | 2025-12-17 | RFC | 51N2-BESS-SITE-T-0004 | [40 empty] | C | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | In-house | In-house | 51N2-ADNI-CDN-ROD-DC-L-0001 |  | BESS APPROACH ROAD AND CROSS SECTION | Approval | Drawing | 2026-02-20 |  |  | Not Submitted | [50 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | Consultant | In-house | 51N2-ADNI-CDN-ROD-DC-L-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-02-20 |  |  | Not Submitted | [50 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast |  | In-house | 51N2-ADNI-CDN-HML-DC-L-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 51N2-BESS-SITE-T-0027 | [46 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast |  | In-house | 51N2-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 51N2-BESS-SITE-T-0030 |  | 2026-04-10 | 2026-04-10 | RFC | 51N2-BESS-SITE-T-0040 | [41 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter |  | In-house | 51N2-ADNI-CDN-HFL-DC-L-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Drawing | 2026-04-04 |  |  | RFC | 2026-04-04 | 2026-04-04 | RFC | 51N2-BESS-SITE-T-0038 | [46 empty] | C
173 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | SECURITY BARRACK | In-House | In-house | 51N2-ADNI-CDN-SEB-DC-V-0001 |  | TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m (BESS PLANT AREA)-PSS10B | Approval | Document |  |  |  | RFC | 2026-06-20 | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0067 | [46 empty] | C
173 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Overall-FDN | Consultant | Worley | 51N2-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
174 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Shed | Consultant | Worley | 51N2-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-10B | Approval | Drawing |  |  |  | Cat. -IV | 2026-02-11 | 2026-02-11 | Cat. -IV | 51N2-BESS-SITE-T-0022 |  | 2026-03-05 | 2026-03-05 | Cat. -IV | 51N2-BESS-SITE-T-0033 | [41 empty] | S
175 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N2-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing |  |  |  | Cat. -I | NR | 2026-02-07 | Cat. -I | 51N2-BESS-SITE-T-0017 |  | 2026-03-05 | 2026-03-06 | Cat. -I | 51N2-BESS-SITE-T-0034 | [41 empty] | C
176 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Foundation | Consultant | Worley | 51N2-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
177 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N2-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | C
178 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N2-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) | [5 empty] | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 51N2-BESS-SITE-T-0089 | [46 empty] | C
[5 empty] | 51N2-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-10B | [5 empty] | Not Submitted | [50 empty] | S
179 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
181 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing |  |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | [5 empty] | Cat. -I_Star | NR |  |  |  |  | 2026-02-14 | 2026-02-16 | Cat. -I | 51N2-BESS-SITE-T-0024 |  | 2026-04-23 | 2026-04-23 | Cat. -I | 51N2-BESS-SITE-T-0045 |  | 2026-07-11 | 2026-07-11 | Cat. -I | 51N2-BESS-SITE-T-0078 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51N2-BESS-SITE-T-0086 | [26 empty] | C
182 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing |  |  |  | RFC | 2206-06-26 | 2026-06-27 | RFC | 51N2-BESS-SITE-T-0075 | [46 empty] | C
183 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room | [5 empty] | RFC | 2026-07-25 | 2026-07-25 | RFC | 51N2-BESS-SITE-T-0084 | [46 empty] | C
[5 empty] | 51N2-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-10B | [5 empty] | Cat. -I | 2026-02-07 | 2026-02-09 | Cat. -IV | 51N2-BESS-SITE-T-0019 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 51N2-BESS-SITE-T-0028 | [41 empty] | S
184 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N2-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing |  |  |  | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0016 |  | 2026-02-25 | 2026-02-25 | Cat. -I | 51N2-BESS-SITE-T-0029 | [41 empty] | C
180 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N2-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
185 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N2-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room | [5 empty] | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 51N2-BESS-SITE-T-0092 | [46 empty] | C
186 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N2-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing |  |  |  | RFC | 2206-06-26 | 2026-06-27 | RFC | 51N2-BESS-SITE-T-0075 | [46 empty] | C
187 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Consultant | Worley | 51N2-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing |  |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 51N2-BESS-SITE-T-0014 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 51N2-BESS-SITE-T-0028 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 51N2-BESS-SITE-T-0044 | [36 empty] | C
188 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Battery Container-CATL | Consultant | Worley | 51N2-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | C
189 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N2-WRLY-OEN-CTF-DC-U-0001 |  | Cable support near coupling transformer area | Approval | Drawing |  |  |  | RFC | 2206-06-26 | 2026-06-27 | RFC | 51N2-BESS-SITE-T-0075 | [46 empty] | C
190 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N2-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
191 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N2-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 51N2-BESS-SITE-T-0026 | [46 empty] | C
191 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD,Drain & Fencing | Consultant | Worley | 51N2-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
192 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | SECURITY BARRACK | Consultant | Worley | 51N2-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing |  |  |  | delete |  |  | delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
193 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | High Mast | Consultant | Worley | 51N2-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | C
194 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
195 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
196 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room | [5 empty] | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
197 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N2-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document |  |  |  | Delete | [50 empty] | C
198 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Overall SLD | Consultant | Worley | 51N2-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing |  |  |  | RFC | 2026-02-27 | 2026-02-27 | RFC | 51N2-BESS-SITE-T-0032 |  | 2026-06-10 | 2026-06-10 | RFC | 51N2-BESS-SITE-T-0062 | [41 empty] | E
199 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Aux Plant SLD | Consultant | Worley | 51N2-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD | [5 empty] | Cat. -I | 2026-04-01 | 2026-04-02 | Cat. -I | 51N2-BESS-SITE-T-0036 | [46 empty] | E
200 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Ovearall Layout - Electrical | Consultant | Worley | 51N2-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing |  |  |  | RFC | 26-02-2026 25-06-2026 | 26-02-2026 25-06-2026 | RFC | 51N2-BESS-SITE-T-0031 51N2-BESS-SITE-T-0072 | Due to crane pad implementation at site . So, not required new revision | 2026-07-23 | 2026-07-23 | RFC | 51N2-BESS-SITE-T-0083 | [41 empty] | E
201 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Ovearall Layout - Electrical | Consultant | Worley | 51N2-WRLY-OEN-BES-DE-L-0002 |  | Layout Options | [5 empty] | Not Submitted | [50 empty] | E
202 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Overall Equipment Layout - Electrical | Consultant | Worley | 51N2-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) | [5 empty] | RFC | 2026-06-10 | 2026-06-10 | RFC | 51N2-BESS-SITE-T-0063 |  | 2026-07-14 | 2026-07-14 | RFC | 51N2-BESS-SITE-T-0080 | [41 empty] | E
203 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Earthing Layout | Consultant | Worley | 51N2-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing |  |  |  | RFC | 2026-04-24 | 2026-04-24 | RFC | 51N2-BESS-SITE-T-0046 |  | 2026-06-22 | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0068 | [41 empty] | E
204 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Earthing Design | Consultant | Worley | 51N2-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
205 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Lightning Layout | Consultant | Worley | 51N2-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing |  |  |  | RFC | 2026-04-30 | 2026-04-30 | RFC | 51N2-BESS-SITE-T-0049 |  | 2026-06-22 | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0068 | [41 empty] | E
206 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Plant Lightning design | Consultant | Worley | 51N2-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
207 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Illumination | Consultant | Worley | 51N2-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing |  |  |  | RFC | 2026-04-21 | 2026-04-21 | RFC | 51N2-BESS-SITE-T-0043 |  | 2026-06-22 | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0068 | [41 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Illumination | Consultant | Worley | 51N2-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | RFC | NR |  |  |  |  | 2026-06-22 | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0068 | [41 empty] | E
208 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | PCS Platform | Consultant | Worley | 51N2-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS | [5 empty] | RFC | 2026-06-05 | 2026-06-05 | RFC | 51N2-BESS-SITE-T-0061 | [46 empty] | E
209 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N2-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing |  |  |  | RFC | 2026-05-12 | 2026-05-12 | Cat. -I | 51N2-BESS-SITE-T-0054 |  | 2026-06-22 | 2026-06-23 | RFC | 51N2-BESS-SITE-T-0070 |  | 2026-07-11 | 2026-07-11 | RFC | 51N2-BESS-SITE-T-0076 | [36 empty] | E
210 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N2-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing |  |  |  | RFC | 2026-05-12 | 2026-05-12 | Cat. -I | 51N2-BESS-SITE-T-0054 |  | 2026-06-22 | 2026-06-23 | RFC | 51N2-BESS-SITE-T-0070 |  | 2026-07-11 | 2026-07-11 | RFC | 51N2-BESS-SITE-T-0076 |  | 2026-08-05 | 2026-08-05 | RFC | 51N2-BESS-SITE-T-0090 | [31 empty] | E
211 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | AC & DC Cable Layout | Consultant | Worley | 51N2-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document |  |  |  | Cat. -IV | 2026-04-14 | 2026-04-14 | RFC | 51N2-BESS-SITE-T-0042 |  | 2026-06-15 | 2026-06-16 | Cat. -IV | 51N2-BESS-SITE-T-0065 | [41 empty] | E
212 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N2-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing |  |  |  | RFC | 02-04-2026 09-04-2026 | 02-04-2026 09-04-2026 | Cat. -I | 51N2-BESS-SITE-T-0037 51N2-BESS-SITE-T-0039 |  | 2026-05-20 | 2026-05-20 | RFC | 51N2-BESS-SITE-T-0056 |  | 2026-06-26 | 2026-06-26 | RFC | 51N2-BESS-SITE-T-0074 |  | NR |  |  |  |  | 2026-08-12 | 2026-08-12 | RFC | 51N2-BESS-SITE-T-0096 | [26 empty] | E
213 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N2-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing |  |  |  | RFC | 2026-04-09 | 2026-04-09 | Cat. -I | 51N2-BESS-SITE-T-0039 |  | 2026-05-20 | 2026-05-20 | RFC | 51N2-BESS-SITE-T-0056 |  | 2026-06-26 | 2026-06-26 | RFC | 51N2-BESS-SITE-T-0074 |  | NR |  |  |  |  | 2026-08-12 | 2026-08-12 | RFC | 51N2-BESS-SITE-T-0096 | [26 empty] | E
214 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N2-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document |  |  |  | Cat. -IV | 2026-04-13 | 2026-04-13 | RFC | 51N2-BESS-SITE-T-0041 |  | 2026-06-13 | 2026-06-15 | Cat. -IV | 51N2-BESS-SITE-T-0064 | [41 empty] | E
215 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | HT-FO Cable | Consultant | Worley | 51N2-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document |  |  |  | Cat. -I | 2026-04-28 | 2026-04-28 | Cat. -I | 51N2-BESS-SITE-T-0048 | [46 empty] | E
216 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Cable Sizing | Consultant | Worley | 51N2-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
217 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Equipment Sizing | Consultant | Worley | 51N2-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
218 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N2-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | [5 empty] | RFC | 2026-05-01 | 2026-05-01 | RFC | 51N2-BESS-SITE-T-0051 |  | 2026-06-26 | 2026-06-26 | RFC | 51N2-BESS-SITE-T-0073 | [41 empty] | E
219 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N2-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) | [5 empty] | RFC | 2026-05-01 | 2026-05-01 | RFC | 51N2-BESS-SITE-T-0051 |  | 2026-06-26 | 2026-06-26 | RFC | 51N2-BESS-SITE-T-0073 | [41 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N2-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2027-07-11 | 2027-07-11 | RFC | 51N2-BESS-SITE-T-0077 | [46 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N2-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2027-07-11 | 2027-07-11 | RFC | 51N2-BESS-SITE-T-0077 | [46 empty] | E
220 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Control & Auxillary Cable | Consultant | Worley | 51N2-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document |  |  |  | Cat. -IV | 2026-04-30 | 2026-04-30 | Cat. -I | 51N2-BESS-SITE-T-0050 |  | 2026-06-13 | 2026-06-15 | Cat. -IV | 51N2-BESS-SITE-T-0064 | [41 empty] | E
221 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N2-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. | [5 empty] | Under Review | 2026-06-02 | 2026-06-02 | RFC | 51N2-BESS-SITE-T-0058 |  | 2026-08-18 |  | Under Review | [42 empty] | E
222 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | MV SGR Platform | Consultant | Worley | 51N2-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR | [5 empty] | RFC | 2026-04-27 | 2026-04-27 | Cat. -I | 51N2-BESS-SITE-T-0047 |  | 2026-05-18 | 2026-05-18 | RFC | 51N2-BESS-SITE-T-0055 | [41 empty] | E
223 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | LCR Platform | Consultant | Worley | 51N2-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR | [5 empty] | Not Submitted | [50 empty] | E
224 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | CSS | Consultant | Worley | 51N2-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS | [5 empty] | RFC | 2026-05-02 | 2026-05-02 | Cat. -I | 51N2-BESS-SITE-T-0052 |  | 2026-08-05 | 2026-08-10 | RFC | 51N2-BESS-SITE-T-0093 | [41 empty] | E
225 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N2-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document |  |  |  | Cat. -I | 2026-06-05 | 2026-06-05 | Cat. -I | 51N2-BESS-SITE-T-0060 |  | 2026-07-27 | 2026-07-28 | Cat. -I | 51N2-BESS-SITE-T-0087 | [41 empty] | E
226 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N2-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document |  |  |  | Cat. -I | 2026-07-21 | 2026-07-21 | Cat. -IV | 51N2-BESS-SITE-T-0081 |  | 2026-08-11 | 2026-08-11 | Cat. -I | 51N2-BESS-SITE-T-0095 | [41 empty] | E
227 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Harmonic Filter | Consultant | Worley | 51N2-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
228 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification | [5 empty] | Not Submitted | [50 empty] | E
229 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). | [5 empty] | Not Submitted | [50 empty] | E
230 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Existing PSS Modification | Consultant | Worley | 51N2-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
231 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
232 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
233 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
234 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
235 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  |  |  |  | Not Submitted | [50 empty] | I
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS |  |  | 2026-04-06 |  |  | Cat. -I | NR |  |  |  |  | NR |  |  |  |  | 2026-07-23 | 2026-07-23 | Cat. -I | 51N2-BESS-SITE-T-0082 | [36 empty] | I
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV | NR |  |  |  |  | 2026-06-23 | 2026-06-24 | Cat. -IV | 51N2-BESS-SITE-T-0071 |  | 2026-08-04 | 2026-08-11 | Cat. -IV | 51N2-BESS-SITE-T-0094 | [36 empty] | I
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | EMS | Consultant | Worley | 51N2-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-02 | 2026-06-02 | Cat. -IV | 51N2-BESS-SITE-T-0057 |  | 2026-06-03 | 2026-06-03 | Cat. -IV_Star | 51N2-BESS-SITE-T-0059 |  | 2026-07-27 | 2026-07-27 | Cat. -IV_Star | 51N2-BESS-SITE-T-0085 | [36 empty] | I
236 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Consultant | Worley | 51N2-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 10B BESS PLANT | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
237 | PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | ROAD | Consultant | Worley | 51N2-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-04-04 |  |  | Cat. -I | NR |  |  |  |  | 2026-05-07 | 2026-05-07 | Cat. -I | 51N2-BESS-SITE-T-0053 | [41 empty] | C
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Coupling Transformer | Consultant | Worley | 51N2-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N2-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | NR | 2026-06-18 | RFC | 51N2-BESS-SITE-T-0066 |  | 2026-07-29 | 2026-07-29 | RFC | 51N2-BESS-SITE-T-0088 | [41 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N2-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS10B_Adani Renewable Energy 35 Limited (ARE35L) | Fire Fighting | Vendor | ATPL | 51N2-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | RFC | NR | 2026-06-22 | RFC | 51N2-BESS-SITE-T-0069 | [46 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 2 | 0.8584%
[5 empty] | RFC |  | 41 | 17.6%
[5 empty] | Cat. -I |  | 54 | 23.18%
[5 empty] | Cat. -I_Star |  | 12 | 5.15%
[5 empty] | Cat. -II |  | 4 | 1.717%
[5 empty] | Cat. -III |  | 0 | 0%
[5 empty] | Cat. -IV |  | 50 | 21.46%
[5 empty] | Cat. -IV_Star |  | 1 | 0.4292%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 164 | 70.39%
[5 empty] | Not Submitted |  | 69 | 29.61%
[5 empty] | Grand Total |  | 233 | 100%

## PSS12
PSS12_Adani Green Energy 27 C Limited (AGE27CL) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10
1 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-G-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | rev.02 | [45 empty] | E
2 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-G-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | reV.01 | [45 empty] | E
3 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-G-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
4 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-G-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
5 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-G-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
6 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | NR | 2026-01-20 | Cat. -I | 51N2-BESS-SITE-T-0011 | [46 empty] | E
7 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Vendor | Tesla | 6764-TESL-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
8 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
9 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
10 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-01-30 | 2026-09-30 |  | Not Submitted | [50 empty] | E
11 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
12 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
13 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
14 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
15 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
16 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Kunal on 23.06.2026 | [45 empty] | E
17 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
18 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
19 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
20 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 09.07.2026 | [45 empty] | E
21 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
22 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
23 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
24 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
25 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
26 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
27 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
28 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
29 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
30 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
31 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
32 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
33 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
34 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | M
35 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | M
36 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
37 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunal on 17.03.2026 | [45 empty] | E
38 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
39 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
40 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
41 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
42 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
43 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
44 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 02.03.2026 | [45 empty] | E
45 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
46 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
47 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery | Vendor | CATL | 6764-CATL-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
48 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
49 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
50 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
51 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
52 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Tinkle Khalasi_18.04.2026 | [45 empty] | E
53 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
54 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
55 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
56 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
57 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunalkumar Patel on 09.03.2026 | [45 empty] | E
58 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
59 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
60 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
61 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
62 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
63 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
64 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
65 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
66 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | I
67 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
68 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0002 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
69 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
70 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
71 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
72 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
73 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
74 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
75 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [45 empty] | E
76 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0003 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
77 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunalkumar Patel on 05.03.2026 | [45 empty] | E
78 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
79 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
80 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
81 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS | Vendor | Inovance | 6764-INOV-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. krunal on 03.03.2026 | [45 empty] | E
82 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | CSS | Vendor | Akshar | 6764-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing |  |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
83 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT Panel-Outdoor | Vendor | Trisqure | 6764-TSQR-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | NR | 2026-04-30 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.14 | NR | 2026-05-30 | Cat. -I |  | Rev.15 | NR | 2026-06-10 | Cat. -I |  | Rev.16 | NR | 2206-07-31 | Cat. -I |  | Rev.20 | [30 empty] | E
84 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | ACDB | Vendor | Active Engineers | 6764-ACTE-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) | [5 empty] | Cat. -I | NR |  |  |  |  | NR | 2026-01-22 | Cat. -I | 51I4-BESS-SITE-T-0003 |  | NR |  |  |  |  | NR | 2026-07-03 | Cat. -I |  |  | 2026-07-31 | 2026-07-31 | Cat. -I | [27 empty] | E
85 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
86 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT Cable | Vendor | Vendor | 6764-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
87 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT Cable | Vendor | Vendor | 6764-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
88 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LT Cable | Vendor | Vendor | 6764-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
89 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LT Cable | Vendor | Vendor | 6764-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
90 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control Cable | Vendor | Vendor | 6764-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
91 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Opteical fiber cable | Vendor | Vendor | 6764-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
92 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PEB Building | Vendor | Vendor | 6764-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
93 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PEB Building | Vendor | Vendor | 6764-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
94 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PEB Building | Vendor | Vendor | 6764-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
95 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PEB Building | Vendor | Vendor | 6764-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
96 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-Q-0001 | 51H2-E-EMS-EMS-DE-Q-V-0001 | EMS SCADA System Architecture Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
97 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-I-0001 | 51H2-E-EMS-EMS-DE-I-V-0001 | EMS Panel Drawing for Central Control Room, Network Panel, Site Level RTU RIO Panel, PCS Plateform RIO Panel, Junction Box for Ethernet Switches & LIUs | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
98 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0001 | 51H2-E-EMS-EMS-DE-D-V-0001 | EMS System Components Datasheet - Including all equipments | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
99 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0002 | 51H2-E-EMS-EMS-DE-D-V-0002 | Project BOM (Bill of Materials) - Includes Hardware and Software | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
100 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-O-0001 | 51H2-E-EMS-EMS-DE-O-V-0001 | Factory Acceptance Test (FAT) Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
101 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-O-0002 | 51H2-E-EMS-EMS-DE-O-V-0002 | SAT Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
102 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-I-0002 | 51H2-E-EMS-EMS-DE-I-V-0002 | Logic Diagram for EMS | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
103 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-E-0001 | 51H2-E-EMS-EMS-DE-E-V-0001 | Wiring Detailed Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
104 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0003 | 51H2-E-EMS-EMS-DE-D-V-0003 | Input Output List/Summary | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
105 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-O-0003 | 51H2-E-EMS-EMS-DE-O-V-0003 | Factory Integrated Test (FIT) Procedure | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
106 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-E-0002 | 51H2-E-EMS-EMS-DE-E-V-0002 | Panel Grounding Scheme | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
107 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-O-0004 | 51H2-E-EMS-EMS-DE-O-V-0004 | Document Dosier | Information | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
108 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-I-0003 | 51H2-E-EMS-EMS-DE-I-V-0003 | Interconnection Detailed Drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
109 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-I-0004 | 51H2-E-EMS-EMS-DE-I-V-0004 | EMS Screens & Report Format | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
110 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-S-0001 | 51H2-E-EMS-EMS-DE-S-V-0001 | Functional Design Specification (FDS) | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
111 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0004 | 51H2-E-EMS-EMS-DE-D-V-0004 | IP List | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
112 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-M-0001 | 51H2-E-EMS-EMS-DE-M-V-0001 | EMS O&M Manual | Information | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
113 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0005 | 51H2-E-EMS-EMS-DE-O-V-0005 | Detailed Erection; Pre-Commissioning and Commissioning Procedure | Information | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
114 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-C-0001 | 51H2-E-EMS-EMS-DE-C-V-0001 | Heat Dissipation & Load Calculation | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
115 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-S-0002 | 51H2-E-EMS-EMS-DE-S-V-0002 | Cyber Security Specification | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
116 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-I-0005 | 51H2-E-EMS-EMS-DE-I-V-0005 | FIT Testing panel wiring diagram | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
117 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-Q-0002 | 51H2-E-EMS-EMS-DE-Q-V-0002 | FIT Testing panel System architecture | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
118 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0006 | 51H2-E-EMS-EMS-DE-D-V-0005 | EMS System Datasheet - IT Hardware Components | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
119 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Vendor | 6764-XXXX-EMS-GEN-DE-D-0007 | 51H2-E-EMS-EMS-DE-D-V-0006 | EMS System Datasheet - Enclosures Accessories Components | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
120 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS |  | Vendor | 6764-XXXX-EMS-GEN-DE-N-0001 | 51H2-E-EMS-EMS-DE-N-V-0001 | Complete Documentation of Implemented Protocols Between Various Elements | Approval | Document |  |  |  | Delete |  |  | Delete | [47 empty] | E
121 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0001 |  | General Arrangement Layout Drawing | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
122 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0002 | 51H2-E-HFL-HFL-DE-G-V-0001 | Drawing and GTP for Series Reactors | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
123 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0003 | 51H2-E-HFL-HFL-DE-G-V-0002 | Drawing and GTP for Off Load Isolator | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
124 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0004 | 51H2-E-HFL-HFL-DE-G-V-0003 | Drawing and GTP for NCT | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
125 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0005 | 51H2-E-HFL-HFL-DE-G-V-0004 | Drawing and GTP for Lightning Arrestor | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
126 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0006 | 51H2-E-HFL-HFL-DE-D-V-0001 | Drawing and GTP for MV Capacitors | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
127 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-G-0007 | 51H2-E-HFL-HFL-DE-E-V-0001 | Drawing and GTP for Damping Resistor | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
128 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-D-0001 | 51H2-E-HFL-HFL-DE-D-V-0002 | Data sheet for Termination kit | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
129 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-D-0002 | 51H2-E-HFL-HFL-DE-G-V-0005 | Data sheet for Control Cable | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
130 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-D-0003 | 51H2-E-HFL-HFL-DE-C-V-0001 | Data sheet for DWC pipe | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
131 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-D-0004 | 51H2-E-HFL-HFL-DE-G-V-0006 | Drawing & Data sheet for Earth Pit & Earth Flats | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
131 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-D-0005 | 51H2-E-HFL-HFL-DE-G-V-0006 | DATA SHEET FOR FRP/GRP LIGHTING POLES | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
132 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-E-0001 | 51H2-E-HFL-HFL-DE-G-V-0007 | Single Line Diagram | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
133 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DE-C-0001 |  | Design Calculation sheet for Harmonic Filter | Approval | Document | 2026-04-28 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
134 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DC-L-0001 |  | Equipment Foundation Layout Drawing | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | C
135 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Vendor | Hitachi | 6764-HTHI-HFL-GEN-DC-C-0001 | 51H2-E-HFL-HFL-DE-D-V-0003 | Structure calculations | Approval | Document | 2026-04-28 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
140 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-Q-0001 |  | EMS System Architecture |  |  | 2026-01-09 |  |  | Not Submitted | [50 empty] | I
141 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0001 |  | IP Address List |  |  | 2026-01-23 |  |  | Not Submitted | [50 empty] | I
142 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0002 |  | Datasheet Of Server & Operator Workstation |  |  | 2026-01-09 |  |  | Not Submitted | [50 empty] | I
143 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0003 |  | Datasheet Of Network Switches |  |  | 2026-01-09 |  |  | Not Submitted | [50 empty] | I
144 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0004 |  | Datasheet Of Firewall |  |  | 2026-01-09 |  |  | Not Submitted | [50 empty] | I
145 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0005 |  | Datasheet Of Printer |  |  | 2026-01-12 |  |  | Not Submitted | [50 empty] | I
146 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0006 |  | Datasheet Of GPS |  |  | 2026-01-12 |  |  | Not Submitted | [50 empty] | I
147 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0007 |  | Datasheet Of Historian Server |  |  | 2026-01-12 |  |  | Not Submitted | [50 empty] | I
148 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0008 |  | Datasheet Of Serial Convertor |  |  | 2026-01-12 |  |  | Not Submitted | [50 empty] | I
149 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0009 |  | Datasheet Of Console |  |  | 2026-01-15 |  |  | Not Submitted | [50 empty] | I
150 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-D-0010 |  | Datasheet Of Chair |  |  | 2026-01-12 |  |  | Not Submitted | [50 empty] | I
151 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-C-0001 |  | Power Consumption and Heat Dissipation |  |  | 2026-01-15 |  |  | Not Submitted | [50 empty] | I
152 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-B-0001 |  | Bill of Material (BOM) |  |  | 2026-01-16 |  |  | Not Submitted | [50 empty] | I
153 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-S-0001 |  | EMS Functional Design Specifications |  |  | 2026-01-21 |  |  | Not Submitted | [50 empty] | I
154 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0001 |  | EMS Cabinet General Arrangement & Wiring Diagram |  |  | 2026-01-28 |  |  | Not Submitted | [50 empty] | I
155 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0002 |  | Substation RTU Cabinet General Arrangement & Wiring Diagram |  |  | 2026-01-28 |  |  | Not Submitted | [50 empty] | I
156 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0003 |  | Network Cabinet General Arrangement & Wiring Diagram |  |  | 2026-02-04 |  |  | Not Submitted | [50 empty] | I
157 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0004 |  | IDT/Network Cabinet General Arrangement & Wiring Diagram |  |  | 2026-02-11 |  |  | Not Submitted | [50 empty] | I
158 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0005 |  | Control Room Server Cabinet General Arrangement & Wiring Diagram |  |  | 2026-02-04 |  |  | Not Submitted | [50 empty] | I
159 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0006 |  | Cabinet Grounding Scheme |  |  | 2026-02-04 |  |  | Not Submitted | [50 empty] | I
160 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0011 |  | IO Assignment-EMS Controller |  |  | 2026-02-16 |  |  | Not Submitted | [50 empty] | I
161 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-G-0012 |  | IO Assignment-Substation Controller |  |  | TBD |  |  | Not Submitted | [50 empty] | I
162 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-I-0001 |  | EMS Control Philosophy Flow Chart |  |  | 2026-01-30 |  |  | Not Submitted | [50 empty] | I
163 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-O-0001 |  | EMS Factory Acceptance Test Procedure (FAT) |  |  | 2026-03-03 |  |  | Not Submitted | [50 empty] | I
164 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-O-0002 |  | EMS Logic Print |  |  | 2026-04-15 |  |  | Not Submitted | [50 empty] | I
165 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-O-0003 |  | EMS HMI Print |  |  | 2026-04-15 |  |  | Not Submitted | [50 empty] | I
166 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-R-0001 |  | EMS FAT Report |  |  | 2026-04-17 |  |  | Not Submitted | [50 empty] | I
167 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-O-0004 |  | EMS Site Acceptance Test Procedure (SAT) |  |  | 2026-03-30 |  |  | Not Submitted | [50 empty] | I
168 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Vendor | Honeywell | 6764-HNWL-EMS-GEN-DI-R-0002 |  | EMS SAT Report |  |  | 2026-06-12 |  |  | Not Submitted | [50 empty] | I
169 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery Container | In-House | In-house | 6764-ADNI-CDN-BCN-DC-V-0001 | 51H2-E-CIV-BCN-DC-V-I-0001 | Precast foundation drawing for Battery container-SVOLT | Approval | Drawing |  |  |  | RFC | 2025-12-15 | 2025-12-15 | RFC | 6764-BESS-SITE-T-0001 |  | 2205-12-19 | 2025-12-19 | RFC | 6764-BESS-SITE-T-0005 | [41 empty] | C
170 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery Container | In-House | In-house | 6764-ADNI-CDN-BCN-DC-H-0001 | 51H2-E-CIV-BCN-DC-H-I-0001 | Fabrication drawing for Precast foundation drawing for Battery container | Approval | Drawing | 2025-12-17 |  |  | Cat. -I | 2026-01-09 | 2026-01-09 | RFC | 6764-BESS-SITE-T-0007 |  | 2026-02-18 | 2026-02-18 | Cat. -I | 6764-BESS-SITE-T-0019 | [41 empty] | C
171 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Overall-FDN | In-House | In-house | 6764-ADNI-CDN-CIV-DC-V-0001 | 51H2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | RFC | NR |  |  |  |  | 2025-12-17 | 2025-12-18 | RFC | 6764-BESS-SITE-T-0004 | [41 empty] | C
172 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | ROAD,Drain & Fencing | In-House | In-house | 6764-ADNI-CDN-ROD-DC-L-0001 | 51H2-E-CIV-ROD-DC-L-I-0001 | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | RFC | 2025-12-29 | 2025-12-29 | RFC | 6764-BESS-SITE-T-0006 | [46 empty] | C
173 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer Station | In-House | In-house | 6764-ADNI-CDN-CTF-DC-V-0001 | 51H2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details-Ornet | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 6764-BESS-SITE-T-0008 |  | 2026-01-21 | 2026-01-21 | RFC | 6764-BESS-SITE-T-0009 |  | 2026-02-09 | 2026-02-10 | RFC | 6764-BESS-SITE-T-0015 |  | 2026-02-14 | 2026-02-14 | RFC | 6764-BESS-SITE-T-0017 | [31 empty] | C
174 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer Station | In-House | In-house | 6764-ADNI-CDN-CTF-DC-V-0007 |  | Coupling Transformer Foundation Layout and RC Details-Tesla | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 6764-BESS-SITE-T-0008 | [46 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer Station | In-House | In-house | 6764-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS11) TYPICAL FOOTING, PRECAST DRAWING | [5 empty] | RFC | 2026-03-16 | 2026-03-16 | RFC | 6764-BESS-SITE-T-0029 | [46 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer Station | In-House | In-house | 6764-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval |  |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 6764-BESS-SITE-T-0074 | [46 empty] | C
175 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer Station | In-House | In-house | 6764-ADNI-CDN-CTF-DC-V-0005 | 51H2-E-CIV-CTF-DC-V-I-0005 | HT-LT PANEL SUPPORTING PLATFROM R.C.C DETAILS / LAYOUT FOR PCS ROOM FOUNDATION PLAN & SECTION DETAIL | Approval | Drawing | 2025-12-17 |  |  | RFC | 2025-12-17 | 2025-12-17 | RFC | 6764-BESS-SITE-T-0004 |  | 2026-01-29 | 2026-01-30 | RFC | 6764-BESS-SITE-T-0010 | [41 empty] | C
176 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Local Control Room | In-House | In-house | 6764-ADNI-CDN-LCR-DC-L-0001 | 51H2-E-CIV-LCR-DC-L-I-0001 | Foundation beam Layout for Local Control Room | Approval | Drawing |  |  |  | RFC | 2025-12-17 | 2025-12-17 | RFC | 6764-BESS-SITE-T-0003 | [46 empty] | C
177 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT SGR Buildng | In-House | In-house | 6764-ADNI-CDN-HGR-DC-L-0001 | 51H2-E-CIV-SGR-DC-L-I-0001 | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | RFC | 2025-12-16 | 2025-12-16 | RFC | 6764-BESS-SITE-T-0002 |  | 2025-12-17 | 2025-12-17 | RFC | 6764-BESS-SITE-T-0003 | [41 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | ROAD,Drain & Fencing | In-House | In-house | 6764-ADNI-CDN-ROD-DC-L-0001 |  | BESS APPROACH ROAD AND CROSS SECTION | Approval | Drawing | 2026-02-20 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | ROAD,Drain & Fencing | In-House | In-house | 6764-ADNI-CDN-ROD-DC-L-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-02-20 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | High Mast | In-House | In-house | 6764-ADNI-CDN-HML-DC-L-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 6764-BESS-SITE-T-0021 | [46 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | High Mast | In-House | In-house | 6764-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 6764-BESS-SITE-T-0023 |  | 2026-04-10 | 2026-04-10 | RFC | 6764-BESS-SITE-T-0035 | [41 empty] | E
173 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | In-House | In-house | 6764-ADNI-CDN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document | 2026-05-19 |  |  | RFC | 2026-05-19 | 2026-05-20 | RFC | 6764-BESS-SITE-T-0049 | [46 empty] | C
173 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | SECURITY BARRACK | In-House | In-house | 6764-ADNI-CDN-SEB-DC-V-0001 |  | TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m (BESS PLANT AREA)-PSS12 | Approval | Document |  |  |  | RFC | 2026-06-20 | 2026-06-22 | RFC | 6764-BESS-SITE-T-0063 | [46 empty] | C
178 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Overall-FDN | Consultant | Worley | 6764-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing | 2026-01-30 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
179 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Shed | Consultant | Worley | 6764-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-12 | Approval | Drawing | 2026-01-15 |  |  | Cat. -IV | 2026-02-11 | 2026-02-11 | Cat. -IV | 6764-BESS-SITE-T-0016 |  | 2026-03-05 | 2026-03-05 | Cat. -IV | 6764-BESS-SITE-T-0027 | [41 empty] | S
180 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Platform | Consultant | Worley | 6764-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing | 2026-01-23 |  |  | Cat. -I | NR | 2026-02-07 | Cat. -I | 6764-BESS-SITE-T-0013 |  | 2026-03-05 | 2026-03-06 | Cat. -I | 6764-BESS-SITE-T-0028 | [41 empty] | C
181 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Foundation | Consultant | Worley | 6764-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing | 2026-01-17 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
182 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Platform | Consultant | Worley | 6764-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing | 2026-01-20 |  |  | Not Submitted | [50 empty] | C
183 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Platform | Consultant | Worley | 6764-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) |  |  | 2026-01-15 |  |  | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 6764-BESS-SITE-T-0081 | [46 empty] | C
184 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing | 2026-01-23 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
186 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DC-V-0003 6764-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing | 2026-01-30 |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | [5 empty] | Cat. -I_Star | NR |  |  |  |  | 2026-02-14 | 2026-02-16 | Cat. -I | 6764-BESS-SITE-T-0018 |  | 2026-04-10 | 2026-04-11 | Cat. -I | 6764-BESS-SITE-T-0037 |  | 2026-07-11 | 2026-07-11 | Cat. -I | 6764-BESS-SITE-T-0073 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 6764-BESS-SITE-T-0079 | [26 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-12 | [5 empty] | Not Submitted | [50 empty] | S
187 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing | 2026-01-30 |  |  | RFC | 2026-06-26 | 2026-06-27 | RFC | 6764-BESS-SITE-T-0071 | [46 empty] | C
188 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room |  |  | 2026-01-17 |  |  | RFC | 2026-07-25 | 2026-07-25 | RFC | 6764-BESS-SITE-T-0078 | [46 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-12 | [5 empty] | Cat. -I | 2026-02-07 | 2026-02-09 | Cat. -IV | 6764-BESS-SITE-T-0014 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 6764-BESS-SITE-T-0022 | [41 empty] | S
189 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | MV SGR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing | 2026-01-30 |  |  | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 6764-BESS-SITE-T-0012 |  | 2026-02-27 | 2026-02-27 | Cat. -I | 6764-BESS-SITE-T-0025 |  | 2026-06-09 | 2026-06-09 | Cat. -I | 6764-BESS-SITE-T-0053 | [36 empty] | C
185 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | MV SGR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing | 2026-01-23 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
190 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | MV SGR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room |  |  | 2026-01-17 |  |  | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 6764-BESS-SITE-T-0082 | [46 empty] | C
191 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | MV SGR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing | 2026-01-30 |  |  | RFC | 2026-06-26 | 2026-06-27 | RFC | 6764-BESS-SITE-T-0071 | [46 empty] | C
192 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | CSS | Consultant | Worley | 6764-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing | 2026-01-23 |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 6764-BESS-SITE-T-0011 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 6764-BESS-SITE-T-0022 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 6764-BESS-SITE-T-0038 | [36 empty] | C
193 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Battery Container-CATL | Consultant | Worley | 6764-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing | 2026-01-23 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
194 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Consultant | Worley | 6764-WRLY-OEN-CTF-DC-U-0001 |  | Coupling Transformer Foundation Layout and RC Details | Approval | Drawing |  |  |  | RFC | 2026-06-26 | 2026-06-27 | RFC | 6764-BESS-SITE-T-0071 | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
195 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Consultant | Worley | 6764-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS |  |  | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
196 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Consultant | Worley | 6764-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 6764-BESS-SITE-T-0020 | [46 empty] | C
196 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | ROAD,Drain & Fencing | Consultant | Worley | 6764-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
197 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | SECURITY BARRACK | Consultant | Worley | 6764-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
198 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | High Mast | Consultant | Worley | 6764-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing | 2026-02-20 |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Rupak, not in worley scope._21.02.2026 | [45 empty] | C
199 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room |  |  | 2026-02-27 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
200 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room |  |  | 2026-02-27 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
201 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room |  |  | 2026-02-27 |  |  | RFC | 2026-06-13 | 2026-06-13 | RFC | 6764-BESS-SITE-T-0057 | [46 empty] | C
202 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Consultant | Worley | 6764-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document | 2026-02-20 |  |  | delete |  |  | delete | [47 empty] | C
203 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Overall SLD | Consultant | Worley | 6764-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing | 2026-01-27 |  |  | RFC | 2026-02-27 | 2026-02-27 | RFC | 6764-BESS-SITE-T-0026 |  | 2026-06-10 | 2026-06-10 | RFC | 6764-BESS-SITE-T-0055 | [41 empty] | E
204 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Aux Plant SLD | Consultant | Worley | 6764-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD |  |  | 2026-01-28 |  |  | RFC | 2026-04-01 | 2026-04-02 | RFC | 6764-BESS-SITE-T-0031 | [46 empty] | E
205 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Ovearall Layout - Electrical | Consultant | Worley | 6764-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing | 2026-01-27 |  |  | RFC | 26-02-2026 24-06-2026 | 26-02-2026 24-06-2026 | RFC | 6764-BESS-SITE-T-0024 6764-BESS-SITE-T-0067 | Due to crane pad implementation at site | [45 empty] | E
206 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Ovearall Layout - Electrical | Consultant | Worley | 6764-WRLY-OEN-BES-DE-L-0002 |  | Layout Options |  |  | 2026-02-05 |  |  | Not Submitted | [50 empty] | E
207 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Overall Equipment Layout - Electrical | Consultant | Worley | 6764-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) |  |  | 2026-02-02 |  |  | RFC | 2026-06-10 | 2026-06-11 | RFC | 6764-BESS-SITE-T-0056 |  | 2026-07-21 | 2026-07-21 | RFC | 6764-BESS-SITE-T-0076 | [41 empty] | E
208 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Plant Earthing Layout | Consultant | Worley | 6764-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing | 2026-02-14 |  |  | RFC | 2026-04-27 | 2026-04-27 | Cat. -I | 6764-BESS-SITE-T-0039 |  | 2026-06-18 | 2026-06-18 | RFC | 6764-BESS-SITE-T-0061 | [41 empty] | E
209 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Plant Earthing Design | Consultant | Worley | 6764-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation |  |  | 2026-01-31 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
210 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Plant Lightning Layout | Consultant | Worley | 6764-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing | 2026-02-20 |  |  | RFC | 2026-06-18 | 2026-06-18 | RFC | 6764-BESS-SITE-T-0061 | [46 empty] | E
211 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Plant Lightning design | Consultant | Worley | 6764-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation |  |  | 2026-02-10 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
212 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Illumination | Consultant | Worley | 6764-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing | 2026-02-24 |  |  | RFC | 2026-04-30 | 2026-04-30 | RFC | 6764-BESS-SITE-T-0043 |  | 2026-06-19 | 2026-06-19 | RFC | 6764-BESS-SITE-T-0062 | [41 empty] | E
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Illumination | Consultant | Worley | 6764-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | RFC | NR |  |  |  |  | 2026-06-18 | 2026-06-18 | RFC | 6764-BESS-SITE-T-0061 | [41 empty] | E
213 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | PCS Platform | Consultant | Worley | 6764-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS |  |  | 2026-02-05 |  |  | RFC | NR |  |  |  |  | 2026-06-04 | 2026-06-04 | RFC | 6764-BESS-SITE-T-0050 | [41 empty] | E
214 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | AC & DC Cable Layout | Consultant | Worley | 6764-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing | 2026-01-30 |  |  | RFC | 09-06-206 | 09-06-206 | Cat. -I | 6764-BESS-SITE-T-0052 |  | 2026-06-22 | 2026-06-22 | RFC | 6764-BESS-SITE-T-0065 | [41 empty] | E
215 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | AC & DC Cable Layout | Consultant | Worley | 6764-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing | 2026-01-30 |  |  | RFC | 09-06-206 | 09-06-206 | Cat. -I | 6764-BESS-SITE-T-0052 |  | 2026-06-22 | 2026-06-22 | RFC | 6764-BESS-SITE-T-0065 |  | NR |  |  |  |  | 2026-07-21 | 2026-07-21 | RFC | 6764-BESS-SITE-T-0076 | [31 empty] | E
216 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | AC & DC Cable Layout | Consultant | Worley | 6764-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document | 2026-01-30 |  |  | Cat. -IV | 09-06-206 | 09-06-206 | Cat. -I | 6764-BESS-SITE-T-0052 |  | 2026-06-15 | 2026-06-16 | Cat. -IV | 6764-BESS-SITE-T-0058 | [41 empty] | E
217 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT-FO Cable | Consultant | Worley | 6764-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing | 2026-02-04 |  |  | RFC | 16-03-2026 08-04-2026 | 17-03-2026 08-04-2026 | RFC | 6764-BESS-SITE-T-0030 6764-BESS-SITE-T-0033 |  | 02-04-2026 26-06-2026 | 02-04-2026 26-06-2026 | RFC | 6764-BESS-SITE-T-0032 6764-BESS-SITE-T-0069 | [41 empty] | E
218 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT-FO Cable | Consultant | Worley | 6764-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing | 2026-01-29 |  |  | RFC | 16-03-2026 08-04-2026 | 17-03-2026 08-04-2026 | RFC | 6764-BESS-SITE-T-0030 6764-BESS-SITE-T-0033 |  | 2026-06-26 | 2026-06-26 | RFC | 6764-BESS-SITE-T-0069 | [41 empty] | E
219 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT-FO Cable | Consultant | Worley | 6764-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document | 2026-02-06 |  |  | Cat. -IV | 2026-04-10 | 2026-04-10 | Cat. -I | 6764-BESS-SITE-T-0036 |  | 2026-06-15 | 2026-06-16 | Cat. -IV | 6764-BESS-SITE-T-0058 | [41 empty] | E
220 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | HT-FO Cable | Consultant | Worley | 6764-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document | 2026-02-12 |  |  | Cat. -I | 2026-04-28 | 2026-04-28 | Cat. -I | 6764-BESS-SITE-T-0040 | [46 empty] | E
221 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Cable Sizing | Consultant | Worley | 6764-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) |  |  | 2026-02-04 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
222 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Equipment Sizing | Consultant | Worley | 6764-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation |  |  | 2026-02-04 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
223 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control & Auxillary Cable | Consultant | Worley | 6764-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) |  |  | 2026-02-09 |  |  | RFC | 2026-04-29 | 2026-04-29 | RFC | 6764-BESS-SITE-T-0042 |  | 2026-06-25 | 2026-06-25 | RFC | 6764-BESS-SITE-T-0068 | [41 empty] | E
224 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control & Auxillary Cable | Consultant | Worley | 6764-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) |  |  | 2026-02-11 |  |  | RFC | 2026-04-29 | 2026-04-29 | RFC | 6764-BESS-SITE-T-0042 |  | 2026-07-11 | 2026-07-11 | RFC | 6764-BESS-SITE-T-0072 |  | 2026-07-21 | 2026-07-21 | RFC | 6764-BESS-SITE-T-0076 | [36 empty] | E
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control & Auxillary Cable | Consultant | Worley | 6764-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6764-BESS-SITE-T-0072 | [46 empty] | E
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control & Auxillary Cable | Consultant | Worley | 6764-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6764-BESS-SITE-T-0072 | [46 empty] | E
225 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Control & Auxillary Cable | Consultant | Worley | 6764-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document | 2026-02-11 |  |  | RFC | 2026-04-29 | 2026-04-29 | Cat. -I | 6764-BESS-SITE-T-0041 |  | 2026-06-18 | 2026-06-18 | Cat. -IV | 6764-BESS-SITE-T-0060 |  | 2026-07-22 | 2026-07-22 | RFC | 6764-BESS-SITE-T-0077 | [36 empty] | E
226 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Consultant | Worley | 6764-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. |  |  | 2026-02-11 |  |  | RFC | 2026-04-30 | 2026-04-30 | RFC | 6764-BESS-SITE-T-0044 | [46 empty] | E
227 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | MV SGR Platform | Consultant | Worley | 6764-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR |  |  | 2026-02-10 |  |  | RFC | 2026-04-27 | 2026-04-27 | Cat. -I | 6764-BESS-SITE-T-0039 |  | 2026-05-18 | 2026-05-18 | RFC | 6764-BESS-SITE-T-0047 | [41 empty] | E
228 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | LCR Platform | Consultant | Worley | 6764-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR |  |  | 2026-01-29 |  |  | Cat. -I | 2026-04-09 | 2026-04-09 | Cat. -I | 6764-BESS-SITE-T-0034 | [46 empty] | E
229 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | CSS | Consultant | Worley | 6764-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS |  |  | 2026-02-16 |  |  | Cat. -I | 2026-05-02 | 2026-05-02 | Cat. -I | 6764-BESS-SITE-T-0045 | [46 empty] | E
230 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Consultant | Worley | 6764-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document | 2026-02-20 |  |  | RFC | 2026-06-05 | 2026-06-05 | Cat. -I | 6764-BESS-SITE-T-0051 |  | 2026-07-16 | 2026-06-17 | RFC | 6764-BESS-SITE-T-0075 | [41 empty] | E
231 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Consultant | Worley | 6764-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document | 2026-02-23 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6764-BESS-SITE-T-0072 | [46 empty] | E
232 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Harmonic Filter | Consultant | Worley | 6764-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document | 2026-02-26 |  |  | Not Submitted | [50 empty] | E
233 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification |  |  | 2026-02-19 |  |  | RFC | 2026-06-09 | 2026-06-10 | RFC | 6764-BESS-SITE-T-0054 | [46 empty] | E
234 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). |  |  | 2026-02-24 |  |  | Not Submitted | [50 empty] | E
235 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Existing PSS Modification | Consultant | Worley | 6764-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing |  |  | 2026-02-24 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
236 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  | 2026-02-10 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
237 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  | 2026-02-24 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
238 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  | 2026-02-26 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
239 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  | 2026-02-28 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
240 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  | 2026-02-16 |  |  | Not Submitted | [50 empty] | I
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS |  |  | 2026-04-06 |  |  | Cat. -I_Star | NR |  |  |  |  | NR |  |  |  |  | NR | 2026-08-10 | Cat. -I_Star | 6764-BESS-SITE-T-0083 | [36 empty] | I
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV | 2026-05-19 | 2026-05-19 | RFC | 6764-BESS-SITE-T-0048 |  | NR |  |  |  |  | 2026-06-23 | 2026-06-24 | Cat. -IV | 6764-BESS-SITE-T-0066 |  | 2026-07-28 | 2026-07-29 | Cat. -IV | 6764-BESS-SITE-T-0080 | [31 empty] | I
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | EMS | Consultant | Worley | 6764-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | NR |  |  |  |  | 2026-06-26 | 2026-06-26 | Cat. -IV_Star | 6764-BESS-SITE-T-0070 | [41 empty] | I
241 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Fire Fighting | Consultant | Worley | 6764-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 12 BESS PLANT | Approval |  |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
242 | PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Road | Consultant | Worley | 6764-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-04-04 |  |  | Cat. -I | NR |  |  |  |  | NR |  |  |  |  | 2026-05-07 | 2026-05-07 | Cat. -I | 6764-BESS-SITE-T-0046 | [36 empty] | C
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Coupling Transformer | Consultant | Worley | 6764-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Fire Fighting | Vendor | ATPL | 6764-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | NR | 2026-06-18 | RFC | 6764-BESS-SITE-T-0059 | [46 empty] | E
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Fire Fighting | Vendor | ATPL | 6764-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS12_Adani Green Energy 27 C Limited (AGE27CL) | Fire Fighting | Vendor | ATPL | 6764-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | RFC | NR | 2026-06-22 | RFC | 6764-BESS-SITE-T-0064 | [46 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 0 | 0%
[5 empty] | RFC |  | 45 | 22.5%
[5 empty] | Cat. -I |  | 30 | 15%
[5 empty] | Cat. -I_Star |  | 12 | 6%
[5 empty] | Cat. -II |  | 4 | 2%
[5 empty] | Cat. -III |  | 0 | 0%
[5 empty] | Cat. -IV |  | 45 | 22.5%
[5 empty] | Cat. -IV_Star |  | 1 | 0.5%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 137 | 68.5%
[5 empty] | Not Submitted |  | 63 | 31.5%
[5 empty] | Grand Total |  | 200 | 100%

## PSS11
PSS11_Adani Green Energy 27 B Limited (AGE27BL) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10 | ACC
1 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-G-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | ACC | [40 empty] | E | DONE
2 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-G-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | ACC | [40 empty] | E | DONE
3 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-G-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Cat. -I | NR |  |  |  |  | NR | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | ACC | [40 empty] | E | DONE
4 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-G-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
5 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-G-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
6 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | NR |  |  |  |  | 2026-01-27 | 2026-02-02 | Cat. -I | 51N2-BESS-SITE-T-0021 | ACC | [40 empty] | E | DONE
7 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Vendor | Ornet | 6074-ORNT-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Cat. -IV | NR | 2026-02-26 | Cat. -IV | XXXX-BESS-SITE-T-0001 | ACC | [45 empty] | E | DONE
8 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
9 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
10 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-01-30 | 2026-09-30 |  | Not Submitted | [50 empty] | E
11 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
12 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
13 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
14 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
15 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
16 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Kunal on 23.06.2026 | [45 empty] | E
17 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
18 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
19 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
20 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 09.07.2026 | [45 empty] | E
21 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
22 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
23 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
24 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
25 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
26 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
27 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
28 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
29 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
30 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
31 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
32 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
33 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
34 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | M
35 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | M
36 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
37 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunal on 17.03.2026 | [45 empty] | E
38 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
39 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
40 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
41 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
42 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
43 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
44 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 02.03.2026 | [45 empty] | E
45 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
46 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
47 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery | Vendor | CATL | 6074-CATL-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
48 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
49 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
50 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
51 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
52 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Tinkle Khalasi_18.04.2026 | [45 empty] | E
53 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
54 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
55 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
56 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
57 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
58 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
59 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
60 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
61 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
62 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
63 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunal on 01.05.2026 | [45 empty] | E
64 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 23.02.2026 |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 16.04.2026 | [40 empty] | I
65 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
66 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | I
67 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | I
68 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | I
69 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
70 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
71 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
72 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
73 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunal on 01.05.2026 | [45 empty] | E
74 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
75 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
76 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
77 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
78 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunal on 28.02.2026 | [45 empty] | E
79 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 28.02.2026 | [45 empty] | E
80 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
81 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS | Vendor | Hopewind | 6074-HOPW-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
82 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery Container | In-House | In-house | 6074-ADNI-CDN-BCN-DC-V-0001 | 51H2-E-CIV-BCN-DC-V-I-0001 | Precast foundation drawing for Battery container-SVOLT | Approval | Drawing |  |  |  | RFC | 2025-12-15 | 2025-12-15 | RFC | 6074-BESS-SITE-T-0001 | ACC | 2025-12-19 | 2025-12-19 | RFC | 6074-BESS-SITE-T-0005 | ACC | [40 empty] | C | DONE
83 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery Container | In-House | In-house | 6074-ADNI-CDN-BCN-DC-H-0001 | 51H2-E-CIV-BCN-DC-H-I-0001 | Fabrication drawing for Precast foundation drawing for Battery container | Approval | Drawing |  |  |  | Cat. -I | 2026-01-09 | 2026-01-09 | RFC | 6074-BESS-SITE-T-0008 | ACC | 2026-02-18 | 2026-02-18 | Cat. -I | 6074-BESS-SITE-T-0025 | ACC | [40 empty] | C | DONE
84 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Overall-FDN | In-House | In-house | 6074-ADNI-CDN-CIV-DC-V-0001 | 51H2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | RFC | NR |  |  |  | ACC | 2025-12-17 | 2025-12-18 | RFC | 6074-BESS-SITE-T-0004 | ACC | 2025-12-22 | 2025-12-22 | RFC | 6074-BESS-SITE-T-0006 | ACC | [35 empty] | C | DONE
85 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | ROAD,Drain & Fencing | In-House | In-house | 6074-ADNI-CDN-ROD-DC-L-0001 | 51H2-E-CIV-ROD-DC-L-I-0001 | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | RFC | 2025-12-29 | 2025-12-29 | RFC | 6074-BESS-SITE-T-0007 | ACC_Tracker_IN REV.01 | [45 empty] | C | DONE
86 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer Station | In-House | In-house | 6074-ADNI-CDN-CTF-DC-V-0001 | 51H2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details-Ornet | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 6074-BESS-SITE-T-0009 | ACC | 2026-01-21 | 2026-01-21 | RFC | 6074-BESS-SITE-T-0011 | ACC | 2026-02-09 | 2026-02-10 | RFC | 6074-BESS-SITE-T-0021 | ACC | 2026-02-14 | 2026-02-14 | RFC | 6074-BESS-SITE-T-0023 | ACC | [30 empty] | C | DONE
87 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer Station | In-House | In-house | 6074-ADNI-CDN-CTF-DC-V-0007 |  | Coupling Transformer Foundation Layout and RC Details-Tesla | Approval | Drawing |  |  |  | RFC | 2026-01-12 | 2026-01-13 | RFC | 6074-BESS-SITE-T-0009 | ACC_Tracker_IN REV.01 | [45 empty] | C | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer Station | In-House | In-house | 6074-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS11) TYPICAL FOOTING, PRECAST DRAWING | [5 empty] | RFC | 2026-03-16 | 2026-03-16 | RFC | 6074-BESS-SITE-T-0035 | ACC_Tracker_IN REV.01 | [45 empty] | C | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer Station | In-House | In-house | 6074-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval |  |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 6074-BESS-SITE-T-0080 | [46 empty] | C
88 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer Station | In-House | In-house | 6074-ADNI-CDN-CTF-DC-V-0005 | 51H2-E-CIV-CTF-DC-V-I-0005 | HT-LT PANEL SUPPORTING PLATFROM R.C.C DETAILS / LAYOUT FOR PCS ROOM FOUNDATION PLAN & SECTION DETAIL | Approval | Drawing | 2025-12-17 |  |  | RFC | 2025-12-17 | 2025-12-18 | RFC | 6074-BESS-SITE-T-0004 | ACC | 2026-01-29 | 2026-01-30 | RFC | 6074-BESS-SITE-T-0014 | ACC | [40 empty] | C | DONE
89 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Local Control Room | In-House | In-house | 6074-ADNI-CDN-LCR-DC-L-0001 | 51H2-E-CIV-LCR-DC-L-I-0001 | Foundation beam Layout for Local Control Room | Approval | Drawing |  |  |  | RFC | 2025-12-17 | 2025-12-17 | RFC | 6074-BESS-SITE-T-0003 | ACC_Tracker_IN REV.01 | [45 empty] | C | DONE
90 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT SGR Buildng | In-House | In-house | 6074-ADNI-CDN-HGR-DC-L-0001 | 51H2-E-CIV-SGR-DC-L-I-0001 | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | RFC | 2025-12-16 | 2025-12-16 | RFC | 6074-BESS-SITE-T-0002 | ACC | 2025-12-17 | 2025-12-17 | RFC | 6074-BESS-SITE-T-0003 | ACC | [40 empty] | C | DONE
173 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | SECURITY BARRACK | In-House | In-house | 6074-ADNI-CDN-SEB-DC-V-0001 |  | TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m (BESS PLANT AREA)-PSS11 | Approval | Document |  |  |  | RFC | 2026-06-20 | 2026-06-22 | RFC | 6074-BESS-SITE-T-0071 | [46 empty] | C
91 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Overall-FDN | Consultant | Worley | 6074-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
92 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Shed | Consultant | Worley | 6074-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-11 | Approval | Drawing | 2026-01-15 |  |  | Cat. -IV | 2026-01-22 | 2026-01-22 | RFC | 6074-BESS-SITE-T-0012 | 4 SHEETS | 29-01-2026 11-02-2026 | 30-01-2026 11-02-2026 | Cat. -IV | 6074-BESS-SITE-T-0014_Sht.04 6074-BESS-SITE-T-0022_Sht.01 t0 3 |  | 2026-03-05 | 2026-03-05 | Cat. -IV | 6074-BESS-SITE-T-0034 | [36 empty] | S
93 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Platform | Consultant | Worley | 6074-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing | 2026-01-23 |  |  | Cat. -I_Star | 2026-01-21 | 2026-01-21 | RFC | 6074-BESS-SITE-T-0010 |  | 2026-01-29 | 2026-01-29 | RFC | 6074-BESS-SITE-T-0013 |  | NR | 2026-02-07 | Cat. -I | 6074-BESS-SITE-T-0018 |  | NR |  |  |  |  | 2026-02-25 | 2026-02-25 | Cat. -I_Star | 6074-BESS-SITE-T-0030 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 6074-BESS-SITE-T-0085 | [21 empty] | C
94 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Foundation | Consultant | Worley | 6074-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing | 2026-01-17 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
95 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Platform | Consultant | Worley | 6074-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing | 2026-01-20 |  |  | Not Submitted | [50 empty] | C
96 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Platform | Consultant | Worley | 6074-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) |  |  | 2026-01-15 |  |  | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 6074-BESS-SITE-T-0090 | [46 empty] | C
97 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing | 2026-01-23 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
99 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DC-V-0003 6074-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing | 2026-01-30 |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | [5 empty] | Cat. -I_Star | NR |  |  |  |  | 2026-02-14 | 2026-02-16 | Cat. -I | 6074-BESS-SITE-T-0024 |  | nr |  |  |  |  | 2026-07-11 | 2026-07-11 | Cat. -I | 6074-BESS-SITE-T-0079 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 6074-BESS-SITE-T-0086 | [26 empty] | C | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform-Shed | Consultant | Worley | 6074-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-11 | [5 empty] | Not Submitted | [50 empty] | S
100 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing | 2026-01-30 |  |  | RFC | NR |  |  |  |  | 2026-06-26 | 2026-06-27 | RFC | 6074-BESS-SITE-T-0077 | [41 empty] | C | DONE
101 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room |  |  | 2026-01-17 |  |  | RFC | 2026-07-25 | 2026-07-25 | RFC | 6074-BESS-SITE-T-0083 | [46 empty] | C | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform-Shed | Consultant | Worley | 6074-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-11 | [5 empty] | Cat. -I | 2026-02-07 | 2026-02-09 | Cat. -IV | 6074-BESS-SITE-T-0020 |  | 2026-02-25 | 2026-02-25 | Cat. -I | 6074-BESS-SITE-T-0029 |  | 2026-02-27 | 2026-02-27 | Cat. -I | 6074-BESS-SITE-T-0032 | [36 empty] | S | DONE
102 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform | Consultant | Worley | 6074-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing | 2026-01-30 |  |  | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 6074-BESS-SITE-T-0017 |  | NR |  |  |  |  | 2026-06-09 | 2026-06-09 | Cat. -I | 6074-BESS-SITE-T-0061 | [36 empty] | C | DONE
98 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform | Consultant | Worley | 6074-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing | 2026-01-23 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
103 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform | Consultant | Worley | 6074-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room |  |  | 2026-01-17 |  |  | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 6074-BESS-SITE-T-0091 | [46 empty] | C | DONE
104 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform | Consultant | Worley | 6074-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing | 2026-01-30 |  |  | RFC | NR |  |  |  |  | 2026-06-26 | 2026-06-27 | RFC | 6074-BESS-SITE-T-0077 | [41 empty] | C | DONE
105 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | CSS | Consultant | Worley | 6074-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing | 2026-01-23 |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 6074-BESS-SITE-T-0016 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 6074-BESS-SITE-T-0028 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 6074-BESS-SITE-T-0045 | [36 empty] | C | DONE
106 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Battery Container-CATL | Consultant | Worley | 6074-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing | 2026-01-23 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
107 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Consultant | Worley | 6074-WRLY-OEN-CTF-DC-U-0001 |  | Cable support near coupling transformer area | Approval | Drawing | 2026-05-13 |  |  | Not Submitted | [50 empty] | C
108 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Consultant | Worley | 6074-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS |  |  | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
109 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Consultant | Worley | 6074-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 6074-BESS-SITE-T-0026 | [46 empty] | C | DONE
109 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | ROAD,Drain & Fencing | Consultant | Worley | 6074-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
110 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | SECURITY BARRACK | Consultant | Worley | 6074-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing | 2026-01-30 |  |  | delete |  |  | delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
111 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | High Mast | Consultant | Worley | 6074-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing | 2026-02-20 |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Rupak, not in worley scope._21.02.2026 | [45 empty] | C
112 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room |  |  | 2026-02-27 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
113 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room |  |  | 2026-02-27 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
114 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room |  |  | 2026-02-27 |  |  | Cat. -IV | 13-06-2026 29-08-2026 | 13-06-2026 31-08-2026 | Cat. -IV | 6074-BESS-SITE-T-0066 6074-BESS-SITE-T-0094 | [46 empty] | C | DONE
115 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Consultant | Worley | 6074-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document | 2026-02-20 |  |  | delete |  |  | delete | [47 empty] | C
116 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Overall SLD | Consultant | Worley | 6074-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing | 2026-01-27 |  |  | RFC | 2026-02-27 | 2026-02-27 | RFC | 6074-BESS-SITE-T-0033 |  | 2026-06-10 | 2026-06-10 | RFC | 6074-BESS-SITE-T-0063 | [41 empty] | E | DONE
117 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Aux Plant SLD | Consultant | Worley | 6074-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD |  |  | 2026-01-28 |  |  | Cat. -I | 2026-03-16 | 2026-03-17 | Cat. -I | 6074-BESS-SITE-T-0036 |  | 2026-04-01 | 2026-04-02 | Cat. -I | 6074-BESS-SITE-T-0037 | [41 empty] | E | DONE
118 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Ovearall Layout - Electrical | Consultant | Worley | 6074-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing | 2026-01-27 |  |  | RFC | 07-02-2026 24-06-2026 | 07-02-2026 24-06-2026 | RFC | 6074-BESS-SITE-T-0019 6074-BESS-SITE-T-0076 | Due to crane pad implementation at site | NR |  |  |  |  | 2026-03-16 | 16-03-2026_Cat.I |  | 6074-BESS-SITE-T-0036 | [36 empty] | E | DONE
119 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Ovearall Layout - Electrical | Consultant | Worley | 6074-WRLY-OEN-BES-DE-L-0002 |  | Layout Options |  |  | 2026-02-05 |  |  | Not Submitted | [50 empty] | E
120 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Overall Equipment Layout - Electrical | Consultant | Worley | 6074-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) |  |  | 2026-02-02 |  |  | RFC | 2026-06-10 | 2026-06-11 | RFC | 6074-BESS-SITE-T-0064 |  | 2026-07-14 | 2026-07-14 | RFC | 6074-BESS-SITE-T-0081 | [41 empty] | E | DONE
121 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Plant Earthing Layout | Consultant | Worley | 6074-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing | 2026-02-14 |  |  | RFC | 2026-04-23 | 2026-04-23 | RFC | 6074-BESS-SITE-T-0046 |  | 2026-06-18 | 2026-06-18 | RFC | 6074-BESS-SITE-T-0070 | [41 empty] | E | DONE
122 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Plant Earthing Design | Consultant | Worley | 6074-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation |  |  | 2026-01-31 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
123 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Plant Lightning Layout | Consultant | Worley | 6074-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing | 2026-02-20 |  |  | RFC | 2026-04-16 | 2026-04-16 | RFC | 6074-BESS-SITE-T-0043 |  | 2026-06-18 | 2026-06-18 | RFC | 6074-BESS-SITE-T-0070 | [41 empty] | E | DONE
124 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Plant Lightning design | Consultant | Worley | 6074-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation |  |  | 2026-02-10 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
125 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Illumination | Consultant | Worley | 6074-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing | 2026-02-24 |  |  | RFC | 2026-04-21 | 2026-04-21 | RFC | 6074-BESS-SITE-T-0044 |  | 2026-06-18 | 2026-06-18 | RFC | 6074-BESS-SITE-T-0070 | [41 empty] | E | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Illumination | Consultant | Worley | 6074-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | RFC | NR |  |  |  |  | 2026-06-18 | 2026-06-18 | RFC | 6074-BESS-SITE-T-0070 | [41 empty] | E | DONE
126 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PCS Platform | Consultant | Worley | 6074-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS |  |  | 2026-02-05 |  |  | RFC | NR |  |  |  |  | 2026-06-04 | 2026-06-04 | RFC | 6074-BESS-SITE-T-0060 | [41 empty] | E
127 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | AC & DC Cable Layout | Consultant | Worley | 6074-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing | 2026-01-30 |  |  | RFC | 02-04-2026 10-04-2026 | 02-04-2026 10-04-2026 | Cat. -I | 6074-BESS-SITE-T-0038 6074-BESS-SITE-T-0042 |  | 2026-06-22 | 2026-06-22 | RFC | 6074-BESS-SITE-T-0073 | [41 empty] | E | DONE
128 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | AC & DC Cable Layout | Consultant | Worley | 6074-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing | 2026-01-30 |  |  | RFC | 2026-04-10 | 2026-04-11 | Cat. -I | 6074-BESS-SITE-T-0042 |  | 2026-06-22 | 2026-06-22 | RFC | 6074-BESS-SITE-T-0073 | [41 empty] | E | DONE
129 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | AC & DC Cable Layout | Consultant | Worley | 6074-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document | 2026-01-30 |  |  | Cat. -IV | 2026-04-02 | 2026-04-02 | Cat. -I | 6074-BESS-SITE-T-0038 |  | 2026-06-15 | 2026-06-16 | Cat. -IV | 6074-BESS-SITE-T-0067 | [41 empty] | E | DONE
130 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT-FO Cable | Consultant | Worley | 6074-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing | 2026-02-04 |  |  | RFC | 16-03-2026 07-04-2026 | 17-03-2026 07-04-2026 | Cat. -I | 6074-BESS-SITE-T-0036 6074-BESS-SITE-T-0039 |  | 02-04-2026 20-05-2026 | 02-04-2026 20-05-2026 | RFC | 6074-BESS-SITE-T-0038 6074-BESS-SITE-T-0055 |  | 2026-06-22 | 2026-06-23 | RFC | 6074-BESS-SITE-T-0074 | [36 empty] | E | DONE
131 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT-FO Cable | Consultant | Worley | 6074-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing | 2026-01-29 |  |  | RFC | 16-03-2026 07-04-2026 | 17-03-2026 07-04-2026 | Cat. -I | 6074-BESS-SITE-T-0036 6074-BESS-SITE-T-0039 |  | 02-04-2026 20-05-2026 | 02-04-2026 20-05-2026 | RFC | 6074-BESS-SITE-T-0038 6074-BESS-SITE-T-0055 |  | 2026-06-22 | 2026-06-23 | RFC | 6074-BESS-SITE-T-0074 | [36 empty] | E | DONE
132 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT-FO Cable | Consultant | Worley | 6074-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document | 2026-02-06 |  |  | RFC | 2026-04-10 | 2026-04-10 | Cat. -I | 6074-BESS-SITE-T-0041 |  | 2026-06-12 | 2026-06-12 | RFC | 6074-BESS-SITE-T-0065 | [41 empty] | E | DONE
133 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT-FO Cable | Consultant | Worley | 6074-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document | 2026-02-12 |  |  | RFC | 2026-04-24 | 2026-04-24 | RFC | 6074-BESS-SITE-T-0047 |  | NR |  |  |  |  | 2026-05-21 | 2026-05-21 | RFC | 6074-BESS-SITE-T-0056 | [36 empty] | E | DONE
134 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Cable Sizing | Consultant | Worley | 6074-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) |  |  | 2026-02-04 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
135 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Equipment Sizing | Consultant | Worley | 6074-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation |  |  | 2026-02-04 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
136 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control & Auxillary Cable | Consultant | Worley | 6074-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) |  |  | 2026-02-09 |  |  | RFC | 02-04-2026 24-04-2026 | 02-04-2026_Cat.I 24-04-2026 | RFC | 6074-BESS-SITE-T-0038 6074-BESS-SITE-T-0048 |  | 2026-06-22 | 2026-06-23 | RFC | 6074-BESS-SITE-T-0074 | [41 empty] | E | DONE
137 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control & Auxillary Cable | Consultant | Worley | 6074-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) |  |  | 2026-02-11 |  |  | RFC | 02-04-2026 24-04-2026 | 02-04-2026_Cat.I 24-04-2026 | RFC | 6074-BESS-SITE-T-0038 6074-BESS-SITE-T-0048 |  | 2026-06-22 | 2026-06-23 | RFC | 6074-BESS-SITE-T-0074 | [41 empty] | E | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control & Auxillary Cable | Consultant | Worley | 6074-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6074-BESS-SITE-T-0078 | [46 empty] | E | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control & Auxillary Cable | Consultant | Worley | 6074-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6074-BESS-SITE-T-0078 | [46 empty] | E | DONE
138 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control & Auxillary Cable | Consultant | Worley | 6074-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document | 2026-02-11 |  |  | RFC | 2026-04-02 | 2026-04-02 | Cat. -I | 6074-BESS-SITE-T-0038 |  | 2026-04-28 | 2026-04-28 | Cat. -I | 6074-BESS-SITE-T-0049 |  | 2026-06-12 | 2026-06-12 | RFC | 6074-BESS-SITE-T-0065 |  | 2026-07-22 | 2026-07-22 | RFC | 6074-BESS-SITE-T-0082 |  | 2026-08-12 | 2026-08-12 | RFC | 6074-BESS-SITE-T-0093 | [26 empty] | E | DONE
139 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Consultant | Worley | 6074-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. |  |  | 2026-02-11 |  |  | RFC | 2026-04-30 | 2026-04-30 | RFC | 6074-BESS-SITE-T-0051 | [46 empty] | E | DONE
140 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | MV SGR Platform | Consultant | Worley | 6074-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR |  |  | 2026-02-10 |  |  | RFC | 2026-03-16 | 2026-03-17 | Cat. -I | 6074-BESS-SITE-T-0036 |  | NR |  |  |  |  | NR |  |  |  |  | 2026-06-18 | 2026-06-18 | RFC | 6074-BESS-SITE-T-0053 | [31 empty] | E | DONE
141 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LCR Platform | Consultant | Worley | 6074-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR |  |  | 2026-01-29 |  |  | Cat. -I | 2026-03-16 | 2026-03-17 | Cat. -I | 6074-BESS-SITE-T-0036 | [46 empty] | E | DONE
142 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | CSS | Consultant | Worley | 6074-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS |  |  | 2026-02-16 |  |  | Cat. -I | 2026-03-16 | 2026-03-17 | Cat. -I | 6074-BESS-SITE-T-0036 | [46 empty] | E | DONE
143 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Consultant | Worley | 6074-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document | 2026-02-20 |  |  | RFC | 2026-06-01 | 2026-06-01 | Cat. -I | 6074-BESS-SITE-T-0057 |  | 2026-07-11 | 2026-07-11 | RFC | 6074-BESS-SITE-T-0078 | [41 empty] | E | DONE
144 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Consultant | Worley | 6074-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document | 2026-02-23 |  |  | Cat. -IV | 2026-07-11 | 2026-07-11 | RFC | 6074-BESS-SITE-T-0078 |  | 2026-07-28 | 2026-07-28 | Cat. -IV | 6074-BESS-SITE-T-0087 | [41 empty] | E | DONE
145 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Consultant | Worley | 6074-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document | 2026-02-26 |  |  | RFC | 2026-07-11 | 2026-07-11 | RFC | 6074-BESS-SITE-T-0078 | [46 empty] | E | DONE
146 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification |  |  | 2026-02-19 |  |  | RFC | 2026-06-09 | 2026-06-10 | RFC | 6074-BESS-SITE-T-0062 | [46 empty] | E | DONE
147 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). |  |  | 2026-02-24 |  |  | Not Submitted | [50 empty] | E
148 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Existing PSS Modification | Consultant | Worley | 6074-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing |  |  | 2026-02-24 |  |  | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
149 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  | 2026-02-10 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
150 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  | 2026-02-24 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
151 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  | 2026-02-26 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
152 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  | 2026-02-28 |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
153 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  | 2026-02-16 |  |  | Not Submitted | [50 empty] | I
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS | Approval |  | 2026-04-06 |  |  | Cat. -I_Star | NR |  |  |  |  | NR |  |  |  |  | NR | 2206-08-10 | Cat. -I_Star | 6074-BESS-SITE-T-0092 | [36 empty] | I | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS | Approval |  | 2026-04-06 |  |  | Cat. -IV | 2026-04-30 | 2026-04-30 | Cat. -I | 6074-BESS-SITE-T-0050 |  | NR |  |  |  |  | 2026-06-23 | 2026-06-24 | Cat. -IV | 6074-BESS-SITE-T-0075 |  | NR |  |  |  |  | 2026-07-28 | 2026-07-29 | Cat. -IV | 6074-BESS-SITE-T-0089 | [26 empty] | I | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Consultant | Worley | 6074-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS | Approval |  | 2026-04-06 |  |  | Cat. -IV_Star | 2026-06-02 | 2026-06-02 | Cat. -IV | 6074-BESS-SITE-T-0058 |  | 2026-06-02 | 2026-06-03 | Cat. -IV | 6074-BESS-SITE-T-0059 |  | 2026-07-27 | 2026-07-27 | Cat. -IV_Star | 6074-BESS-SITE-T-0084 | [36 empty] | I | DONE
154 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Fire Fighting | Consultant | Worley | 6074-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 11 BESS PLANT | Approval |  |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | ROAD | Consultant | Worley | 6074-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-04-04 |  |  | Cat. -I | 2026-04-04 |  | Under Review |  |  | NR |  |  |  |  | 2026-05-07 | 2026-05-07 | Cat. -I | 6074-BESS-SITE-T-0052 | [36 empty] | C | DONE
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Coupling Transformer | Consultant | Worley | 6074-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
154 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | CSS | Vendor | Akshar | 6074-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing |  |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
156 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT Panel-Outdoor | Vendor | Trisqure | 6074-TSQR-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | NR | 2026-04-30 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.14 | NR | 2026-05-30 | Cat. -I |  | Rev.15 | NR | 2026-06-10 | Cat. -I |  | Rev.16 | NR | 2206-07-31 | Cat. -I |  | Rev.20 | [30 empty] | E
157 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | ACDB | Vendor | Prima Automation | 6074-PRMA-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) |  |  | 2026-01-28 |  |  | Cat. -I | NR | 2026-06-24 | Cat. -I |  |  | NR | 2026-07-03 | Cat. -I |  | Rev.07 | [40 empty] | E
158 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Vendor | 6074-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
159 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT Cable | Vendor | Vendor | 6074-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
160 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | HT Cable | Vendor | Vendor | 6074-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
161 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LT Cable | Vendor | Vendor | 6074-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
162 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | LT Cable | Vendor | Vendor | 6074-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
163 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Control Cable | Vendor | Vendor | 6074-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
164 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Opteical fiber cable | Vendor | Vendor | 6074-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
165 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PEB Building | Vendor | Vendor | 6074-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
166 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PEB Building | Vendor | Vendor | 6074-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
167 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PEB Building | Vendor | Vendor | 6074-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
168 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | PEB Building | Vendor | Vendor | 6074-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
169 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) |  | In-House | In-house | 6074-ADNI-CDN-HGR-DC-Q-0001 | 51H2-E-CIV-HGR-DC-Q-I-0001 | architectural drawings- Outdoor switchgear room(LOCAL SWITCHGEAR ROOM GENERAL ARRANGEMENT DRAWING) | [5 empty] | Not Submitted | [50 empty] | C
170 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Local Control Room | In-House | In-house | 6074-ADNI-CDN-LCR-DC-Q-0001 | 51H2-E-CIV-LCR-DC-Q-I-0001 | architectural drawings- Local control room | [5 empty] | Not Submitted | [50 empty] | C
171 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) |  | In-House | In-house | 6074-ADNI-CDN-PCS-DC-Q-0001 | 51H2-E-CIV-PCS-DC-Q-I-0001 | Architectural drawings- PCS room(GA drawing) | [5 empty] | Not Submitted | [50 empty] | C
172 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | High Mast | In-House | In-house | 6074-ADNI-CDN-HML-DC-L-0001 | 51H2-E-CIV-HML-DC-L-I-0001 | High Mast - Foundation layout and drawing | Approval | Drawing | 2025-12-26 |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 6074-BESS-SITE-T-0027 | ACC_Tracker_IN REV.01 | [45 empty] | C
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | High Mast | In-House | In-house | 6074-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 6074-BESS-SITE-T-0031 |  | 2026-04-10 | 2026-04-10 | RFC | 6074-BESS-SITE-T-0040 | [41 empty] | E
173 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | In-House | In-house | 6074-ADNI-CDN-HFL-DC-V-0001 | 51H2-E-CIV-HFL-DC-V-I-0001 | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document | 2026-05-19 |  |  | RFC | 2026-05-19 | 2026-05-20 | RFC | 6074-BESS-SITE-T-0054 | [46 empty] | C
174 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0001 |  | General Arrangement Layout Drawing | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
175 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0002 | 51H2-E-HFL-HFL-DE-G-V-0001 | Drawing and GTP for Series Reactors | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
176 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0003 | 51H2-E-HFL-HFL-DE-G-V-0002 | Drawing and GTP for Off Load Isolator | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
177 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0004 | 51H2-E-HFL-HFL-DE-G-V-0003 | Drawing and GTP for NCT | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
178 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0005 | 51H2-E-HFL-HFL-DE-G-V-0004 | Drawing and GTP for Lightning Arrestor | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
179 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0006 | 51H2-E-HFL-HFL-DE-D-V-0001 | Drawing and GTP for MV Capacitors | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
180 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-G-0007 | 51H2-E-HFL-HFL-DE-E-V-0001 | Drawing and GTP for Damping Resistor | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
181 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-D-0001 | 51H2-E-HFL-HFL-DE-D-V-0002 | Data sheet for Termination kit | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
182 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-D-0002 | 51H2-E-HFL-HFL-DE-G-V-0005 | Data sheet for Control Cable | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
183 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-D-0003 | 51H2-E-HFL-HFL-DE-C-V-0001 | Data sheet for DWC pipe | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
184 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-D-0004 | 51H2-E-HFL-HFL-DE-G-V-0006 | Drawing & Data sheet for Earth Pit & Earth Flats | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | E
184 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-D-0005 | 51H2-E-HFL-HFL-DE-G-V-0006 | DATA SHEET FOR FRP/GRP LIGHTING POLES | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
185 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-E-0001 | 51H2-E-HFL-HFL-DE-G-V-0007 | Single Line Diagram | Approval | Document | 2026-04-28 |  |  | Cat. -I | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
186 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DE-C-0001 |  | Design Calculation sheet for Harmonic Filter | Approval | Document | 2026-04-28 |  |  | delete | NR | 2026-04-25 | Cat. -I | XXXX-BESS-SITE-T-0001 |  |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [40 empty] | E
187 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DC-L-0001 |  | Equipment Foundation Layout Drawing | Approval | Document | 2026-04-28 |  |  | Not Submitted | [50 empty] | C
188 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Harmonic Filter | Vendor | Hitachi | 6074-HTHI-HFL-GEN-DC-C-0001 | 51H2-E-HFL-HFL-DE-D-V-0003 | Structure calculations | Approval | Document | 2026-04-28 |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
193 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0001 |  | Datasheet for Controller and its components | Approval | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
194 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0002 |  | Datasheet for I/O Module (AI/AO/DI/DO) | Approval | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
195 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0003 |  | Datasheet for Engineering Server / Operator Workstation / Monitor | Approval | Document | 2026-01-13 |  |  | Cat. -II | 2026-01-13 | 2026-01-16 | Cat. -II | [47 empty] | I
196 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0004 |  | Datasheet for Printers | I | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
197 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0005 |  | Datasheet for Cisco Network Switch | Approval | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
198 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0006 |  | Datasheet of DO Relay | Approval | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
199 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0007 |  | Datasheet of GPS | Approval | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
200 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0008 |  | Datasheet of Console Desk & Printer Table | Approval | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
201 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0009 |  | Datasheet of 55' LED | Approval | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
202 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0010 |  | Data Sheet of Link Interface Unit | I | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
203 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0011 |  | Data Sheet of Patch Panel and Patch Chords (for RJ45 and FO) | I | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
204 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0012 |  | Datasheet of DR PC and Monitor | Approval | Document | 2026-01-13 |  |  | Cat. -II | 2026-01-13 | 2026-01-16 | Cat. -II | [47 empty] | I
205 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0013 |  | Datasheet of Firewall | Approval | Document | 2026-06-01 |  |  | Under Review | 2026-01-06 |  | Under Review | [47 empty] | I
206 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0014 |  | Datasheet of Power Supply | I | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
207 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0015 |  | Datasheet of Serial Converter | Approval | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
208 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0016 |  | Datasheet of OGS/PwCS Server | Approval | Document | 2026-01-13 |  |  | Cat. -II | 2026-01-13 | 2026-01-16 | Cat. -II | [47 empty] | I
209 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0017 |  | Datasheet of NAS | Approval | Document | 2026-01-15 |  |  | Cat. -II | 2026-01-13 | 2026-01-16 | Cat. -II | [47 empty] | I
210 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0018 |  | Datasheet of KVM | I | Document | 2026-05-01 |  |  | Cat. -II | 2026-01-05 | 2026-01-15 | Cat. -II | [47 empty] | I
211 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0019 |  | Datasheet of Industrial Switch | Approval | Document | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
212 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-Q-0001 |  | System Architecture | Approval | DRAWING | 2026-02-02 |  |  | Not Submitted | [50 empty] | I
213 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-G-0001 |  | EMS Control Cabinet Drawings (GA/IA) | Approval | DRAWING | 2026-05-02 |  |  | Not Submitted | [50 empty] | I
214 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-O-0001 |  | EMS Cabinet Power Consumption and Heat Dissipation | I | Document | 2026-05-02 |  |  | Not Submitted | [50 empty] | I
215 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-E-0001 |  | Wiring Scheme for IO Signals | Approval | DRAWING | 2026-06-01 |  |  | Cat. -II | 2026-01-06 | 2026-01-15 | Cat. -II | [47 empty] | I
216 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-B-0001 |  | Bill of Quantity (H/w + S/w) | Approval | Document | 2026-02-19 |  |  | Not Submitted | [50 empty] | I
217 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-E-0002 |  | Panel Grounding Scheme | I | DRAWING | 2026-09-01 |  |  | Cat. -II | 2026-01-13 | 2026-01-16 | Cat. -II | [47 empty] | I
218 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-D-0020 |  | I/O List | Approval | Document | 2026-04-02 |  |  | Not Submitted | [50 empty] | I
219 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-M-0001 |  | Operation and Maintenance Manual | I | Document | 2026-04-30 |  |  | Not Submitted | [50 empty] | I
220 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-GEN-DI-I-0001 |  | Interconnection Detail drawing | Approval | Document | 2026-02-28 |  |  | Not Submitted | [50 empty] | I
221 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-S-0001 |  | Functional Design Specification | Approval | Document | 28/02/2026 |  |  | Not Submitted | [50 empty] | I
222 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-E-0001 |  | Signal exchange signal | Approval | Document | 2026-02-15 |  |  | Not Submitted | [50 empty] | I
223 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-I-0001 |  | Control Logic PDF | I | Document | 10-03-2026 |  |  | Not Submitted | [50 empty] | I
224 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-O-0001 |  | SCADA HMI Screens PDF | Approval | Document | 16-03-2026 |  |  | Not Submitted | [50 empty] | I
225 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-O-0002 |  | FAT Procedure | Approval | Document | 27-02-2026 |  |  | Not Submitted | [50 empty] | I
226 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-O-0003 |  | SAT Procedure | Approval | Document | 15-03-2026 |  |  | Not Submitted | [50 empty] | I
227 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-M-0001 |  | Software Manuals (Softcopy) | I | Document | 2026-01-29 |  |  | Not Submitted | [50 empty] | I
228 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-O-0004 |  | Pre-Commissioning and Commissioning Test Procedure | Approval | Document | 2026-01-30 |  |  | Not Submitted | [50 empty] | I
229 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-SCD-DI-D-0001 |  | IP List | I | Document | 20-03-2026 |  |  | Not Submitted | [50 empty] | I
230 | PSS11_Adani Green Energy 27 B Limited (AGE27BL) | EMS | Vendor | Emerson | 6074-EMSN-EMS-OTH-DI-S-0001 |  | Cyber Security specifciation | Approval | Document | 2026-01-26 |  |  | Not Submitted | [50 empty] | I
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Fire Fighting | Vendor | ATPL | 6074-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | NR | 2026-06-18 | RFC | 6074-BESS-SITE-T-0068 |  | 2026-07-29 | 2026-07-29 | RFC | 6074-BESS-SITE-T-0088 | [41 empty] | E
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Fire Fighting | Vendor | ATPL | 6074-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS11_Adani Green Energy 27 B Limited (AGE27BL) | Fire Fighting | Vendor | ATPL | 6074-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | RFC | NR | 2026-06-22 | RFC | 6074-BESS-SITE-T-0072 | [46 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 1 | 0.4762%
[5 empty] | RFC |  | 44 | 20.95%
[5 empty] | Cat. -I |  | 42 | 20%
[5 empty] | Cat. -I_Star |  | 10 | 4.762%
[5 empty] | Cat. -II |  | 24 | 11.43%
[5 empty] | Cat. -III |  | 0 | 0%
[5 empty] | Cat. -IV |  | 47 | 22.38%
[5 empty] | Cat. -IV_Star |  | 1 | 0.4762%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 169 | 80.48%
[5 empty] | Not Submitted |  | 41 | 19.52%
[5 empty] | Grand Total |  | 210 | 100%

## MDL PSS Summary
STATUS AS ON DATE | [7 empty] | STATUS AS ON DATE |  | 01.01.2025
KHAVDA- BESS PSS MDL STATUS | [7 empty] | KHAVDA PSS MDL STATUS-PHASE-3 | [5 empty] | Approval Status
1 | PSS-05B |  | Civil | Electrical | Total |  | REMARKS | 3 | PSS-11 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 29 | 113 | 142 | 63.68% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 8 | 42.11% | Hyosung-19 | 34 | 45 | 10 | 5 | 0 | 47 | 1 | 0
|  | Not Submitted | 5 | 76 | 81 | 36.32% |  |  |  | Not Submitted | 11 | 57.89%
|  | Total | 34 | 189 | 223 |  |  |  |  | Total | 19
2 | PSS-08B |  | Civil | Electrical | Total |  | REMARKS | 3 | PSS-11 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 22 | 114 | 136 | 56.9% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 8 | 42.11% | Hyosung-19 | 30 | 35 | 19 | 5 | 2 | 42 | 2 | 1
|  | Not Submitted | 2 | 101 | 103 | 43.1% |  |  |  | Not Submitted | 11 | 57.89%
|  | Total | 24 | 215 | 239 |  |  |  |  | Total | 19
3 | PSS-09 |  | Civil | Electrical | Total |  | REMARKS | 3 | PSS-11 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 32 | 120 | 152 | 66.96% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 8 | 42.11% | Hyosung-19 | 37 | 53 | 11 | 4 | 0 | 43 | 2 | 2
|  | Not Submitted | 0 | 75 | 75 | 33.04% |  |  |  | Not Submitted | 11 | 57.89%
|  | Total | 32 | 195 | 227 |  |  |  |  | Total | 19
4 | PSS-10B |  | Civil | Electrical | Total |  | REMARKS | 1 | PSS-6 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 31 | 133 | 164 | 70.39% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 14 | 56% | Hyosung-19 added-offline submitted docu. | 41 | 54 | 12 | 4 | 0 | 50 | 1 | 2
|  | Not Submitted | 5 | 64 | 69 | 29.61% |  |  |  | Not Submitted | 11 | 44%
|  | Total | 36 | 197 | 233 |  |  |  |  | Total | 25
5 | PSS-11 |  | Civil | Electrical | Total |  | REMARKS | 2 | PSS-7 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 26 | 143 | 169 | 80.48% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 9 | 47.37% | Hyosung-19 | 44 | 42 | 10 | 24 | 0 | 47 | 1 | 1
|  | Not Submitted | 6 | 35 | 41 | 19.52% |  |  |  | Not Submitted | 10 | 52.63%
|  | Total | 32 | 178 | 210 |  |  |  |  | Total | 19
6 | PSS-12 |  | Civil | Electrical | Total |  | REMARKS | 3 | PSS-11 |  |  |  | REMARKS | RFC | Cat. -I | Cat. -I_Star | Cat. -II | Cat. -III | Cat. -IV | Cat. -IV_Star | UR
| CIVIL/ELECT COMBINED (PSS) | Submitted | 27 | 110 | 137 | 68.5% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | 8 | 42.11% | Hyosung-19 | 45 | 30 | 12 | 4 | 0 | 45 | 1 | 0
|  | Not Submitted | 2 | 61 | 63 | 31.5% |  |  |  | Not Submitted | 11 | 57.89%
|  | Total | 29 | 171 | 200 |  |  |  |  | Total | 19
Grand Total |  | Submitted | 84 | 386 | 470 | 73.09% |  |  | CIVIL/ELECT COMBINED (PSS) | Submitted | #REF! | #REF!
|  | Not Submitted | 13 | 160 | 173 | 26.91% |  |  |  | Not Submitted | #REF! | #REF!
|  | Total | 97 | 546 | 643 |  |  |  |  | Total | #REF!
|  | PSS-05B | 29 | 109
|  |  | 5 | 74
|  | PSS-08B | 22 | 109
|  |  | 2 | 99
|  | PSS-09 | 32 | 116
|  |  | 0 | 73
|  | PSS-10B | 31 | 128
|  |  | 5 | 62
|  | PSS-11 | 26 | 139
|  |  | 6 | 33
|  | PSS-12 | 27 | 106
|  |  | 2 | 59

## Status Summary (hidden)
PSS05B | [6 empty] | PSS09 | [6 empty] | PSS11
In-house/Vendor Name2 | All | [5 empty] | In-house/Vendor Name2 | (All) | [5 empty] | In-house/Vendor Name2 | All
Civil | [6 empty] | Civil | [6 empty] | Civil
Count of New_Drawing / Document Number | Column Labels | [5 empty] | Count of New_Drawing / Document Number | Column Labels | [5 empty] | Count of New_Drawing / Document Number | Column Labels
Row Labels | (blank) | E | I | M | S | Grand Total | Row Labels | E | I | M | S | (blank) | Grand Total | Row Labels | (blank) | E | I | M | S | Grand Total
(blank) |  | 1 |  |  |  | 1 | Cat. -I | 41 |  |  | 1 |  | 42 | (blank) | 1 |  |  |  |  | 1
Cat. -I | 8 | 36 |  |  |  | 44 | Cat. -I_Star | 6 | 2 |  |  |  | 8 | Cat. -I |  | 41 | 1 |  | 1 | 43
Cat. -I_Star |  | 6 |  |  |  | 6 | Cat. -II | 4 |  |  |  |  | 4 | Cat. -I_Star |  | 5 |  |  |  | 5
Cat. -II |  | 3 | 1 |  |  | 4 | Cat. -IV | 32 | 3 | 2 | 1 |  | 38 | Cat. -II |  | 3 | 21 |  |  | 24
Cat. -IV | 1 | 32 | 4 | 2 |  | 39 | Cat. -IV_Star |  | 2 |  |  |  | 2 | Cat. -IV |  | 32 | 5 | 2 | 1 | 40
Delete |  | 8 |  | 1 |  | 9 | Delete | 30 |  | 1 |  |  | 31 | Delete |  | 5 |  | 1 |  | 6
Not Submitted | 8 | 57 | 32 | 1 |  | 98 | Not Submitted | 35 | 56 | 1 | 1 |  | 93 | Not Submitted |  | 29 | 24 | 1 | 1 | 55
RFC | 15 | 8 |  |  | 1 | 24 | RFC | 13 |  |  |  |  | 13 | RFC |  | 17 |  |  |  | 17
Under Review |  | 1 |  |  |  | 1 | Under Review | 2 |  |  |  |  | 2 | Under Review |  | 1 | 1 |  |  | 2
Grand Total | 32 | 152 | 37 | 4 | 1 | 226 | (blank) |  |  |  |  | 1 | 1 | Grand Total | 1 | 133 | 52 | 4 | 3 | 193
[7 empty] | Grand Total | 163 | 63 | 4 | 3 | 1 | 234
PSS08B | [6 empty] | PSS10B | [6 empty] | PSS12
In-house/Vendor Name2 | All | [5 empty] | In-house/Vendor Name2 | All | [5 empty] | In-house/Vendor Name2 | All
Civil | [6 empty] | Civil | [6 empty] | Civil
Count of New_Drawing / Document Number | Column Labels | [5 empty] | Count of New_Drawing / Document Number | Column Labels | [5 empty] | Count of New_Drawing / Document Number | Column Labels
Row Labels | (blank) | E | I | M | S | Grand Total | Row Labels | (blank) | E | I | M | S | Grand Total | Row Labels | (blank) | E | I | M | S | Grand Total
(blank) | 1 |  |  |  |  | 1 | (blank) | 1 |  |  |  |  | 1 | Cat. -I |  | 29 |  |  | 1 | 30
Cat. -I |  | 27 |  |  | 2 | 29 | Cat. -I |  | 48 |  |  | 1 | 49 | Cat. -I_Star |  | 6 | 2 |  |  | 8
Cat. -I_Star |  | 5 | 2 |  |  | 7 | Cat. -I_Star |  | 6 | 3 |  |  | 9 | Cat. -II |  | 4 |  |  |  | 4
Cat. -II |  | 5 |  |  |  | 5 | Cat. -II |  | 4 |  |  |  | 4 | Cat. -IV |  | 31 | 3 | 2 | 1 | 37
Cat. -III |  | 2 |  |  |  | 2 | Cat. -IV |  | 38 | 3 | 3 | 1 | 45 | Delete |  | 29 |  | 1 |  | 30
Cat. -IV |  | 30 | 1 | 3 |  | 34 | Cat. -IV_Star |  |  | 1 |  |  | 1 | Not Submitted | 1 | 43 | 37 | 1 | 1 | 83
Cat. -IV_Star |  |  | 2 |  |  | 2 | Delete |  | 1 |  |  |  | 1 | RFC | 1 | 14 | 1 |  |  | 16
delete |  | 1 |  |  |  | 1 | Not Submitted |  | 45 | 31 | 1 | 1 | 78 | Under Review |  | 2 |  |  |  | 2
Not Submitted |  | 69 | 33 | 1 | 1 | 104 | RFC |  | 14 |  |  |  | 14 | Grand Total | 2 | 158 | 43 | 4 | 3 | 210
RFC |  | 16 |  |  |  | 16 | Under Review |  | 4 |  |  |  | 4
Under Review |  | 11 |  |  |  | 11 | Grand Total | 1 | 160 | 38 | 4 | 3 | 206
Grand Total | 1 | 166 | 38 | 4 | 3 | 212

## PSS05B
PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | [13 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | New_Drawing / Document Number | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | Schedule Date | FORECAST DATE | Weightage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09 | Remarks_10
62 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
61 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
61 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
60 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-V-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing |  |  |  | Delete |  |  | Delete | [47 empty] | E
60 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-V-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
62 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
63 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Ornet | 51I4-ORNT-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document |  |  |  | Cat. -I | 2026-02-10 | 2026-02-26 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
56 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-V-0005 | 51H2-E-SEP-IDT-DE-G-V-0005 | CTR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing | 2026-01-28 |  |  | Cat. -I | 2026-01-31 | 2026-03-21 | Cat. -I | 51I4-BESS-SITE-T-0021 | [46 empty] | E
57 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-V-0004 | 51H2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing | 2026-01-28 |  |  | Not Submitted | [50 empty] | E
57 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-V-0003 | 51H2-E-SEP-IDT-DE-G-V-0003 | EMR NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing | 2026-01-28 |  |  | Not Submitted | [50 empty] | E
58 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-V-0002 | 51H2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing | 2026-01-28 |  |  | Cat. -I | 2026-01-31 | 2026-02-26 | Cat. -II |  |  | NR | 2026-03-06 | Cat. -I | 51I4-BESS-SITE-T-0021 | [41 empty] | E
58 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-V-0001 | 51H2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing | 2026-01-28 |  |  | Cat. -I | 2026-01-31 | 2026-02-26 | Cat. -II |  |  | NR | 2026-03-06 | Cat. -I_Star | 51I4-BESS-SITE-T-0021 |  | NR | 2026-05-21 | Cat. -I | XXXX-BESS-SITE-T-0001 | [36 empty] | E
59 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-M-0001 | 51H2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document | 2026-01-28 |  |  | Cat. -IV | 2026-01-31 | 2026-03-21 | Cat. -IV | 51I4-BESS-SITE-T-0021 | [46 empty] | E
59 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Vendor | Shilchar | 51I4-SICR-CTF-GEN-DE-D-0001 | 51H2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document | 2026-01-28 |  |  | Cat. -I | 2026-01-31 |  | Under Review |  |  | NR | 2026-03-06 | Cat. -I | 51I4-BESS-SITE-T-0021 | [41 empty] | E
75 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DI-Q-0001 | 51H2-E-PCS-PCS-DE-M-V-0001 | PCS Control and Communication Architecture | Approval | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | I
76 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DI-N-0001 | 51H2-E-PCS-PCS-DE-Q-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 23.02.2026 |  |  | Cat. -II |  | Document received by Mr. Samrej Vahora on 16.04.2206\ | [40 empty] | I
76 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DI-D-0003 | 51H2-E-PCS-PCS-DE-I-V-0002 51H2-E-PCS-PCS-DE-I-V-0003 | IO list and Data addresses for PCS to BMS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | I
77 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DI-D-0002 | 51H2-E-PCS-PCS-DE-M-V-0003 | Input Output list for EMS interface | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | I
77 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DI-D-0001 | 51H2-E-PCS-PCS-DE-M-V-0002 | PCS controller Function, Datasheet and Specification | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | I
78 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-R-0005 | 51H2-E-PCS-PCS-DE-B-V-0001 | Power Quality Test Resport | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
78 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-R-0004 | 51H2-E-PCS-PCS-DE-E-V-0001 | Certification summary along with certificates | Information | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunal on 01.05.2026 | [45 empty] | E
79 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-R-0003 | 51H2-E-PCS-PCS-DE-L-V-0002 | CEA test Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
79 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-R-0002 | 51H2-E-PCS-PCS-DG-L-V-0002 | Benchmarking Report | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
80 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-R-0001 | 51H2-E-PCS-PCS-DE-L-V-0001 | PCS Desing Basis Report | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail by Mr. Tinkle Khalasi_18.04.2026 | [45 empty] | E
80 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0007 | 51H2-E-PCS-PCS-DE-O-V-0004 | PSCAD Model |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
81 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0006 | 51H2-E-PCS-PCS-DE-M-V-0004 | PSSE Model |  | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
81 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0005 | 51H2-E-PCS-PCS-DE-B-V-0002 | Detailed Lock-out Procedure and Equipment safety Procedure | Information | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
82 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0004 | 51H2-E-PCS-PCS-DE-O-V-0002 | PCS Charge and Discharge Efficiency detail | Information | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
82 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0003 | 51H2-E-PCS-GEN-DE-G-V-0004 | PCS performance Detail | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
83 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0002 | 51H2-E-PCS-PCS-DE-I-V-0001 51H2-E-PCS-PCS-DE-I-V-0002 | System level thermal profile as per site condition | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
83 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-O-0001 | 51H2-E-PCS-GEN-DE-G-V-0001 | PCS 3D Model | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
84 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-N-0002 | 51H2-E-PCS-PCS-DE-R-V-0001 | Control and Operation Philoshophy | Approval | Drawing |  |  |  | Cat. -II |  |  | Cat. -II |  | Document received by Mr. Krunal on 01.05.2026 | [45 empty] | E
84 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-N-0001 | 51H2-E-PCS-GEN-DE-N-V-0001 | System & Function Descriptions of PCS | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
85 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-M-0004 | 51H2-E-PCS-PCS-DE-N-V-0001 | Training manuals | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
85 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-M-0003 | 51H2-E-PCS-PCS-DG-L-V-0001 | PSCAD Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
86 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-M-0002 | 51H2-E-PCS-PCS-DE-E-V-0002 | PSSE Guide / User Manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
86 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-M-0001 | 51H2-E-PCS-GEN-DE-G-V-0002 | O & M manual | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
87 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-L-0002 | 51H2-E-PCS-PCS-DE-O-V-0003 | 3D Drawing |  | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 28.02.2026 | [45 empty] | E
87 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-L-0001 | 51H2-E-PCS-PCS-DE-I-V-0004 | 2D drawing |  | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Krunal on 28.02.2026 | [45 empty] | E
88 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-J-0001 | 51H2-E-PCS-PCS-DE-D-V-0001 | PQ, QU Curve | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
88 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-I-0001 | 51H2-E-PCS-PCS-DE-O-V-0001 | Interconnection Drawings | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
89 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-G-0003 | 51H2-E-PCS-PCS-DE-J-V-0001 | Construction and installation drawing | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
89 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-G-0001 | 51H2-E-PCS-GEN-DE-N-V-0003 | General Arrangements Drawing – PCS | Approval | Drawing |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
90 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-E-0002 | 51H2-E-PCS-PCS-BE-R-V-0001 | PCS schematic wiring drawings | Approval | Document |  |  |  | Cat. -I_Star |  |  | Cat. -I_Star |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
90 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-D-0002 | 51H2-E-PCS-PCS-DE-I-V-0003 51H2-E-PCS-PCS-DE-I-V-0001 | PCS Component Spare List | Information | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 06.03.2026 | [45 empty] | E
91 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-D-0001 | 51H2-E-PCS-GEN-DE-N-V-0002 | GTP of PCS | Approval | Drawing |  |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
91 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-B-0002 | 51H2-E-PCS-GEN-DE-G-V-0003 | Maintenance schedule and activity plan | Approval | Drawing |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
92 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS | Vendor | Hopewind | 51I4-HOPW-PCS-GEN-DE-B-0001 | 51H2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document |  |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | E
96 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-LCO-DE-R-0001 | 51H2-E-BTR-GEN-DE-L-V-0001 | Certification summary along with certificates including model numbers Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
97 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-LCO-DE-G-0001 | 51H2-E-BTR-GEN-DE-O-V-0001 | GA(cooling Unit) & piping layout, showing the routing, connections, and integration of cooling lines inside the container Liquid Cooling | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
97 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-LCO-DE-D-0002 | 51H2-E-BTR-GEN-DE-M-V-0001 | Coolant Datasheet and MSDS for Liquid Cooling | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
98 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-LCO-DE-D-0001 | 51H2-E-BTR-GEN-DE-D-V-0001 | GTP (Technical Paramater detail) as per given format | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
98 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-HVA-DE-R-0001 | 51H2-E-BTR-LCO-BE-R-V-0001 | Certification including model numbers and compliance data for HVAC | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
99 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-HVA-DE-G-0001 | 51H2-E-BTR-LCO-DE-G-V-0001 | GA for HVAC | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
99 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-HVA-DE-D-0001 | 51H2-E-BTR-LCO-DE-D-V-0001 | GTP (Technical Paramater detail) for HVAC | Approval | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
100 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DM-L-0002 | 51H2-E-BTR-GEN-DE-O-V-0002 | 3D Model (Parasolid(x_t and .x_b)/.stp/.iges) | Information | Drawing | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | M
100 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DM-L-0001 | 51H2-E-BTR-GEN-DE-B-V-0001 | 2D Layout (Auto CAD file) | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 24.03.2026 | [45 empty] | M
101 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DM-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0003 | Container Paint/Coating datasheet and procedure | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | M
101 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-R-0001 | 51H2-E-BTR-GEN-DE-D-V-0004 | Certification Summary | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
102 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-O-0005 | 51H2-E-BTR-BAR-DE-D-V-0101 | Modbus mapping register with complete description for all parameters. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
102 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-O-0004 | 51H2-E-BTR-GEN-DE-D-V-0003 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval |  | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
103 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-O-0003 | 51H2-E-BTR-GEN-DE-E-V-0002 | Electrical Load Flow, Arc Flash, and Short Circuit Simulation Report (ETAP Model) & Protection Study for BESS | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
103 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-O-0002 | 51H2-E-BTR-GEN-DE-D-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
104 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-O-0001 | 51H2-E-BTR-GEN-DE-O-V-0004 | Battery Sizing Model | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Krunal on 17.03.2026 | [45 empty] | E
104 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-N-0001 | 51H2-E-BTR-BAR-DE-G-V-0101 | BMS control philoshophy (Fail secnerios, mode of operation, Setpoints, Moderate/ mild/Severe alarm actions ) | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
105 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-M-0001 | 51H2-E-BTR-GEN-DE-O-V-0006 | O&M Manual and Installation & Transportation Manual | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
105 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-E-0002 | 51H2-E-BTR-GEN-DE-E-V-0001 | Auxilliary Power Supply (SLD) showing electrical connections and protection devices (component) with Rating: Include all electrical connections, distribution of auxiliary loads, and integration points. | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
106 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-E-0001 | 51H2-E-BTR-GEN-DE-L-V-0002 | Single Line Diagram (SLD) showing electrical connections and protection devices (component) with Rating: 1- Battery Pack 2- HV Box 3- Container | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
106 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-D-0003 | 51H2-E-BTR-BAR-BE-R-V-0101 | BMS make and technical datasheet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
107 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-D-0002 | 51H2-E-BTR-BCL-DE-R-V-0101 | Details of BMS ethernet port for interface with EMS. | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Krunal on 02.03.2026 | [45 empty] | E
107 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-D-0001 | 51H2-E-BTR-GEN-DE-O-V-0005 | BESS Container Communication Interface & Scheme, Port details | Information |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
108 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-GEN-DE-B-0001 | 51H2-E-BTR-GEN-DE-N-V-0001 | BOQ and spare parts list (all component list pack level, HV box, rack level, container level,etc..) | Approval |  | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
108 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-FSS-DE-R-0001 | 51H2-E-BTR-DCA-BE-R-V-0001 | FSS Certification and test report, including model numbers,compliance data and design calculation of aerosol and venting area for FSS | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 09.07.2026 | [45 empty] | E
109 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-FSS-DE-G-0001 | 51H2-E-BTR-DCA-DE-D-V-0001 | GA FOR FSS | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
109 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-FSS-DE-D-0002 | 51H2-E-BTR-DCA-DE-G-V-0001 | FSS component details as per given format for FSS | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
110 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-FSS-DE-D-0001 | 51H2-E-BTR-FSS-BE-R-V-0001 | GTP (Technical Paramater detail) for FSS | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
110 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-DCA-DE-R-0001 | 51H2-E-BTR-HVA-BE-R-V-0001 | DC cable Termination component (Fuse, Breaker,SPD) Certification and test report, including model numbers and compliance data for DC Cable Termination Cabinet | Information | Document | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
111 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-DCA-DE-G-0001 | 51H2-E-BTR-HVA-DE-G-V-0001 | GA for DC Cable Termination Cabinet 1- CAD file & PDF 2- Terminal busbar drawing include hole size and position with lug integrated (shared by adani) 3-Detailed layout showing cable entry points and termination locations | Approval | Drawing | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
111 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-DCA-DE-D-0001 | 51H2-E-BTR-HVA-DE-D-V-0001 | GTP (Technical Paramater detail) for DC Cable Termination Cabinet | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
112 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCN-DE-R-0001 | 51H2-E-BTR-FSS-DE-G-V-0001 | BESS container Certification and test report, including model numbers and compliance data for Container | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Kunal on 23.06.2026 | [45 empty] | E
112 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCN-DE-G-0001 | 51H2-E-BTR-FSS-DE-D-V-0001 | General Arrangement (GA) drawing in PDF and CAD formats, including detailed footing dimensions for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 26.02.2026 | [45 empty] | E
113 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCN-DE-D-0001 | 51H2-E-BTR-BCN-BE-R-V-0001 | GTP (Technical Paramater detail) for Container | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
113 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCL-DE-R-0001 | 51H2-E-BTR-BAR-DE-G-V-0001 | Battery cell certification and compliance report, including detailed model numbers and test results for cell | Information | Drawing | 2026-01-30 | 2026-09-30 |  | Not Submitted | [50 empty] | E
114 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCL-DE-G-0001 | 51H2-E-BTR-BAR-DE-D-V-0001 | General Arrangement (GA) drawing for cell | Information | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
114 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BCL-DE-D-0001 | 51H2-E-BTR-BCL-BE-R-V-0001 | GTP (Technical Paramater detail) for cell | Information | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
115 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BAR-DE-R-0001 | 51H2-E-BTR-BCN-DE-G-V-0001 | Certification and test report for battery rack, including model numbers and compliance data for rack | Information | Drawing | 2026-01-30 |  |  | Cat. -IV |  |  | Cat. -IV |  | Document received by Mr. Samrej Vahora on 27.06.2026 | [45 empty] | E
115 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BAR-DE-G-0001 | 51H2-E-BTR-BCN-DE-D-V-0001 | GA Drawing (PDF &CAD file ) showing component layout and dimensions for rack 1- Battery Pack 2- HV box with Rack Frame | Approval | Document | 2026-01-30 |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Aditya Pratap Singh_02.02.2026 | [45 empty] | E
116 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery | Vendor | CATL | 51I4-CATL-BTR-BAR-DE-D-0001 | 51H2-E-BTR-BAR-BE-R-V-0001 | GTP (Technical Paramater detail) (Pack, HV box and rack ) for rack | Approval | Document | 2026-01-30 |  |  | Cat. -I |  |  | Cat. -I |  | Document received by Mr. Samrej Vahora on 23.02.2026 | [45 empty] | E
1 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PEB Building | Vendor | Vendor | 51I4-XXXX-PEB-LCR-DC-G-0002 | 51H2-E-PEB-LCR-DC-G-V-0002 | Anchor Bolt for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
2 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PEB Building | Vendor | Vendor | 51I4-XXXX-PEB-LCR-DC-G-0001 | 51H2-E-PEB-LCR-DC-G-V-0001 | PEB details for Local Control Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
2 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PEB Building | Vendor | Vendor | 51I4-XXXX-PEB-HGR-DC-G-0002 | 51H2-E-PEB-SGR-DC-G-V-0002 | Anchor Bolt for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
3 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PEB Building | Vendor | Vendor | 51I4-XXXX-PEB-HGR-DC-G-0001 | 51H2-E-PEB-SGR-DC-G-V-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
3 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Opteical fiber cable | Vendor | Vendor | 51I4-XXXX-OFC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0002 | 12F G.652D MT DS ARMOURED Optical Fiber Cable | [5 empty] | Not Submitted | [50 empty] | E
4 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LT Cable | Vendor | Vendor | 51I4-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
4 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LT Cable | Vendor | Vendor | 51I4-XXXX-LTC-GEN-DE-D-0001 | 51H2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 3.5Cx300 sq mm, 3.5Cx50 sq mm LT CABLE | [5 empty] | Not Submitted | [50 empty] | E
5 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT Cable | Vendor | Vendor | 51I4-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
5 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT Cable | Vendor | Vendor | 51I4-XXXX-HTC-GEN-DE-D-0001 | 51H2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [5 empty] | Not Submitted | [50 empty] | E
6 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DI-D-0001 | 51H2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document |  |  |  | Not Submitted | [50 empty] | I
6 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-S-0002 | 51H2-E-EMS-EMS-DE-S-V-0002 | Cyber Security Specification | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
7 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-S-0001 | 51H2-E-EMS-EMS-DE-S-V-0001 | Functional Design Specification (FDS) | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
7 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-Q-0002 | 51H2-E-EMS-EMS-DE-Q-V-0002 | FIT Testing panel System architecture | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
8 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-Q-0001 | 51H2-E-EMS-EMS-DE-Q-V-0001 | EMS SCADA System Architecture Drawing | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
8 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-O-0004 | 51H2-E-EMS-EMS-DE-O-V-0004 | Document Dosier | Information | Drawing |  |  |  | Not Submitted | [50 empty] | E
9 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-O-0003 | 51H2-E-EMS-EMS-DE-O-V-0003 | Factory Integrated Test (FIT) Procedure | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
9 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-O-0002 | 51H2-E-EMS-EMS-DE-O-V-0002 | SAT Procedure | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
10 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-O-0001 | 51H2-E-EMS-EMS-DE-O-V-0001 | Factory Acceptance Test (FAT) Procedure | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
10 |  | EMS |  | Vendor | 51I4-XXXX-EMS-GEN-DE-N-0001 | 51H2-E-EMS-EMS-DE-N-V-0001 | Complete Documentation of Implemented Protocols Between Various Elements | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
11 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-M-0001 | 51H2-E-EMS-EMS-DE-M-V-0001 | EMS O&M Manual | Information | Document |  |  |  | Not Submitted | [50 empty] | E
11 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-I-0005 | 51H2-E-EMS-EMS-DE-I-V-0005 | FIT Testing panel wiring diagram | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
12 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-I-0004 | 51H2-E-EMS-EMS-DE-I-V-0004 | EMS Screens & Report Format | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
12 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-I-0003 | 51H2-E-EMS-EMS-DE-I-V-0003 | Interconnection Detailed Drawing | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
13 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-I-0002 | 51H2-E-EMS-EMS-DE-I-V-0002 | Logic Diagram for EMS | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
13 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-I-0001 | 51H2-E-EMS-EMS-DE-I-V-0001 | EMS Panel Drawing for Central Control Room, Network Panel, Site Level RTU RIO Panel, PCS Plateform RIO Panel, Junction Box for Ethernet Switches & LIUs | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
14 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-E-0002 | 51H2-E-EMS-EMS-DE-E-V-0002 | Panel Grounding Scheme | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
14 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-E-0001 | 51H2-E-EMS-EMS-DE-E-V-0001 | Wiring Detailed Drawing | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | E
15 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0007 | 51H2-E-EMS-EMS-DE-D-V-0006 | EMS System Datasheet - Enclosures Accessories Components | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
15 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0006 | 51H2-E-EMS-EMS-DE-D-V-0005 | EMS System Datasheet - IT Hardware Components | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
16 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0005 | 51H2-E-EMS-EMS-DE-O-V-0005 | Detailed Erection; Pre-Commissioning and Commissioning Procedure | Information | Drawing |  |  |  | Not Submitted | [50 empty] | E
16 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0004 | 51H2-E-EMS-EMS-DE-D-V-0004 | IP List | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
17 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0003 | 51H2-E-EMS-EMS-DE-D-V-0003 | Input Output List/Summary | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
17 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0002 | 51H2-E-EMS-EMS-DE-D-V-0002 | Project BOM (Bill of Materials) - Includes Hardware and Software | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
18 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-D-0001 | 51H2-E-EMS-EMS-DE-D-V-0001 | EMS System Components Datasheet - Including all equipments | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
18 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Vendor | Vendor | 51I4-XXXX-EMS-GEN-DE-C-0001 | 51H2-E-EMS-EMS-DE-C-V-0001 | Heat Dissipation & Load Calculation | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
19 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control Cable | Vendor | Vendor | 51I4-XXXX-CIC-GEN-DE-D-0001 | 51H2-E-HLC-CIC-DE-D-V-0001 | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [5 empty] | Not Submitted | [50 empty] | E
56 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT Panel-Outdoor | Vendor | Symatic | 51I4-SYMC-OHP-HGR-DE-G-0001 | 51H2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing(SLD& Scheme) with BOM (With Foundation Drawing) |  |  | 2026-04-30 |  |  | Cat. -I | 2026-05-21 | 2026-05-21 | Cat. -I | XXXX-BESS-SITE-T-0001 |  | 2026-08-11 | 2026-08-11 | Cat. -I | [42 empty] | E
63 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-O-0001 |  | TYPICAL MOUNTING DETAILS FOR DEVICES & MODULES | Information | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
64 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-L-0002 |  | Complete Layout Drawing of FIRE EXTINGUISHER System- PSS 5 | Approval | 19.01.2026 |  |  |  | Not Submitted | [50 empty] | I
64 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-L-0001 |  | Complete Layout Drawing of FDA System- PSS 5 | Approval | 15.01.2026 |  |  |  | Not Submitted | [50 empty] | I
65 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-I-0001 |  | Cause & Effect Diagram | Information | 25.01.2026 |  |  |  | Not Submitted | [50 empty] | I
65 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-G-0001 |  | G.A of Fire Alarm Panel | Information | 15.01.2026 |  |  |  | Not Submitted | [50 empty] | I
66 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-E-0001 |  | Schematic Diagram of fire alarm system - PSS 5 | Approval | 15.01.2026 |  |  |  | Not Submitted | [50 empty] | I
66 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0017 |  | Technical Datasheet for Fire Extinguisher 9 Kgs.CO2 type Trolley arrangement (Portable ) | Approval | 16.01.2026 |  |  |  | Not Submitted | [50 empty] | I
67 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0016 |  | Technical Datasheet for Fire Extinguisher 6 Kgs .ABC type (Portable ) | Approval | 16.01.2026 |  |  |  | Not Submitted | [50 empty] | I
67 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0015 |  | Technical Datasheet for Power Cable - 3 core * 2.5sq.mm ARM | Approval | 16.01.2026 |  |  |  | Not Submitted | [50 empty] | I
68 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0014 |  | Technical Datasheet for Fire Alarm Cable - 2 core * 1.5sq.mm FRLS ARM | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
68 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0013 |  | Technical Datasheet for Isolator Module | Approval | 14.01.2026 |  |  |  | Not Submitted | [50 empty] | I
69 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0012 |  | Technical Datasheet for Network Switch | Approval | 16.01.2026 |  |  |  | Not Submitted | [50 empty] | I
69 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0011 |  | Technical Datasheet for Weatherproof Hooter cum strobe (outdoor) | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
70 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0010 |  | Technical Datasheet for Addressable Hooter cum strobe (Indoor) | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
70 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0009 |  | Technical Datasheet for Addressable Control Module | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
71 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0008 |  | Technical Datasheet for Addressable Monitor Module | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
71 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0007 |  | Technical Datasheet for Weatherproof Manual Call Point (Outdoor) | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
72 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0006 |  | Technical Datasheet for Addressable Manual Call Point (Indoor) | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
72 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0005 |  | Technical Datasheet for Smoke Detector with Base | Approval | 13.01.2026 |  |  |  | Not Submitted | [50 empty] | I
73 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0004 |  | Technical Datasheet of Main Fire Alarm Panel (MFAP) | Approval | 14.01.2026 |  |  |  | Not Submitted | [50 empty] | I
73 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0003 |  | Technical Datasheet of Local Fire Alarm Panel (LFAP) | Approval | Drawing | 2026-01-14 |  |  | Not Submitted | [50 empty] | I
74 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0002 |  | Technical Datasheet for Repeater Alarm Panel (RAP). | Approval | 14.01.2026 |  |  |  | Not Submitted | [50 empty] | I
74 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-D-0001 |  | Technical Datasheet for GUI for Fire Detection System with workstation | Approval |  |  |  |  | Not Submitted | [50 empty] | I
75 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Deection |  | Johnson Controls | 51I4-JHCI-FDS-FAS-DI-B-0001 |  | Cable Schedule - PSS 5 | Information | 18.01.2026 |  |  |  | Not Submitted | [50 empty] | I
116 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | CSS | Vendor | Akshar | 51I4-AKSR-CSS-GEN-DE-G-0001 | 51H2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing | 2026-01-31 |  |  | Cat. -II | NR |  |  |  |  | NR | 2026-02-05 | Cat. -II | [42 empty] | E
124 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | ACDB | Vendor | Active Engineers | 51I4-ACTE-ACD-GEN-DE-G-0001 | 51H2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) | [5 empty] | Cat. -I | NR |  |  |  |  | NR | 2026-01-22 | Cat. -I | 51I4-BESS-SITE-T-0003 |  | NR |  |  |  |  | NR | 2026-07-03 | Cat. -I |  |  | 2026-07-31 | 2026-07-31 | Cat. -I | [27 empty] | E
92 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-G-0004 | 51H2-E-HFL-HFL-DE-G-V-0003 | Drawing and GTP for Damping Resistor | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-04-28 | 2026-05-01 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
93 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-G-0003 | 51H2-E-HFL-HFL-DE-G-V-0002 | Drawing and GTP for MV Capacitors | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.01 | [45 empty] | E
93 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-G-0002 | 51H2-E-HFL-HFL-DE-G-V-0001 | Drawing and GTP for Series Reactors | Approval | Document | 2026-05-04 |  |  | Cat. -I | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
94 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-G-0001 |  | General Arrangement Layout Drawing | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-05-08 | 2026-05-08 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
94 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-E-0001 | 51H2-E-HFL-HFL-DE-G-V-0004 | Single Line Diagram | Approval | Document | 2026-05-04 |  |  | Cat. -I | 2026-05-08 | 2026-05-08 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
95 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-C-0001 | 51H2-E-HFL-HFL-DE-D-V-0001 | Design Calculation sheet for Harmonic Filter | Approval | Document | 2026-05-04 |  |  | delete | NR | 2026-04-28 | Cat. -I | XXXX-BESS-SITE-T-0001 | Rev.01 |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [40 empty] | E
95 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DC-L-0001 | 51H2-E-HFL-HFL-DE-E-V-0001 | Equipment Foundation Layout Drawing | Approval | Document | 2026-05-04 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
96 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DC-C-0001 | 51H2-E-HFL-HFL-DE-D-V-0002 | Structure calculations | Approval | Document | 2026-05-04 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Vendor | Clerient | 51I4-CPSL-HFL-GEN-DE-D-0001 |  | Drawing & Data sheet for Earth Pit & Earth Flats | [5 empty] | Cat. -I | 2026-05-14 | 2026-05-14 | Cat. -I | XXXX-BESS-SITE-T-0001 | [46 empty] | E
117 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | High Mast |  | In-house | 51I4-ADNI-EDN-HML-DE-L-0001 |  | High Mast - Cable routing layout | Approval | Drawing | 2026-02-23 |  |  | RFC | 2026-02-26 | 2026-02-26 | RFC | 51I4-BESS-SITE-T-0016 | [46 empty] | E
117 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Sraircase |  | In-house | 51I4-ADNI-CDN-STC-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR STAIRCASE-BCF PSS-5B | [5 empty] | Cat. -I | 2026-02-06 | 2026-02-06 | Cat. -I | 51N2-BESS-SITE-T-0015 | [46 empty] | C
118 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | ROAD,Drain & Fencing | Consultant | In-house | 51I4-ADNI-CDN-ROD-DC-L-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing | 2026-02-20 |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
118 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | ROAD,Drain & Fencing |  | In-house | 51I4-ADNI-CDN-ROD-DC-L-0001 |  | BESS APPROACH ROAD AND CROSS SECTION | Approval | Drawing | 2026-02-20 |  |  | RFC | 2026-02-21 | 2026-02-21 | RFC | 51I4-BESS-SITE-T-0013 | [46 empty] | C
119 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform |  | In-house | 51I4-ADNI-CDN-LCR-DC-V-0001 |  | LAYOUT FOR LOCAL CONTROL ROOM / ELECTRICAL ROOM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51I4-BESS-SITE-T-0005 | [46 empty] | C
119 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | High Mast |  | In-house | 51I4-ADNI-CDN-HML-DC-L-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | RFC | 2026-02-20 | 2026-02-21 | RFC | 51I4-BESS-SITE-T-0012 | [46 empty] | C
120 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform |  | In-house | 51I4-ADNI-CDN-HGR-DC-V-0001 |  | LAYOUT FOR OUTDOOR SWITCHGEAR ROOM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51I4-BESS-SITE-T-0005 | [46 empty] | C
122 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-V-0001 | 51H2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details-Ornet | Approval | Drawing |  |  |  | RFC | 2026-02-02 | 2026-02-03 | RFC | 51I4-BESS-SITE-T-0004 |  | 2026-02-03 | 2026-02-04 | RFC | 51I4-BESS-SITE-T-0005 |  | 2026-04-02 | 2026-04-02 | RFC | 51I4-BESS-SITE-T-0024 | [36 empty] | C
121 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-V-0002 | 51H2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details-Silchar | Approval | Drawing |  |  |  | RFC | NR |  |  |  | Submitted wrong dawing number | 2026-05-18 | 2026-05-18 | RFC | 51I4-BESS-SITE-T-0030 | [41 empty] | C
121 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station |  | In-house | 51I4-ADNI-CDN-CTF-DC-V-0005 |  | LAYOUT FOR HT-LT PANEL (PCS) SUPPORTING PLATFROM – FOUNDATION PLAN & SECTION DETAILS | Approval | Drawing | 2026-02-03 |  |  | RFC | 2026-02-03 | 2026-02-04 | RFC | 51I4-BESS-SITE-T-0005 | [46 empty] | C
120 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-V-0008 |  | NIFPS FOUNDATION(PSS05B) TYPICAL FOOTING, PRECAST DRAWING | Approval | Drawing |  |  |  | RFC | 2026-03-16 | 2026-03-16 | RFC | 51I4-BESS-SITE-T-0020 | [46 empty] | C
120 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-V-0009 |  | COUPLING TRANSFORMER FENCING DETAILS | Approval | Drawing |  |  |  | RFC | 2026-07-11 | 2026-07-13 | RFC | 51I4-BESS-SITE-T-0050 | [46 empty] | C
122 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-H-0001 |  | TYPICAL PRECAST DRAWING FOR NIFPS PSS-5B | [5 empty] | Cat. -I | 2026-02-04 | 2026-02-04 | Cat. -I | 51N2-BESS-SITE-T-0005 | [46 empty] | C
122 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-H-0002 |  | COUPLING TRANSFORMER FOUNDATION (ORNET) LAYOUT AND RC DETAILS (PSS 5B |  |  | 2026-05-15 |  |  | Cat. -IV | 2026-05-20 | 2026-05-20 | Cat. -IV | 51N2-BESS-SITE-T-0032 | [46 empty] | C
122 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer Station | In-House | In-house | 51I4-ADNI-CDN-CTF-DC-H-0003 |  | COUPLING TRANSFORMER FOUNDATION (SILCHAR ) LAYOUT AND RC DETAILS (PSS 5B |  |  | 2026-06-18 |  |  | Cat. -IV | 2026-06-18 | 2026-06-18 | Cat. -IV | 51I4-BESS-SITE-T-0044 | [46 empty] | C
123 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Overall-FDN | In-house | In-house | 51I4-ADNI-CDN-CIV-DC-V-0001 | 51H2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing | 2025-12-23 |  |  | RFC | 2025-12-26 | 2025-12-27 | RFC | 51I4-BESS-SITE-T-0001 | [46 empty] | C
123 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery Container | In-house | In-house | 51I4-ADNI-CDN-BCN-DC-V-0001 | 51H2-E-CIV-BCN-DC-V-I-0001 | Precast foundation drawing for Battery container | Approval | Drawing | 2025-12-23 |  |  | RFC | 2025-12-26 | 2025-12-27 | RFC | 51I4-BESS-SITE-T-0001 | [46 empty] | C
124 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery Container | In-house | In-house | 51I4-ADNI-CDN-BCN-DC-H-0001 | 51H2-E-CIV-BCN-DC-H-I-0001 | Fabrication drawing for Precast foundation drawing for Battery container | Approval | Drawing |  |  |  | Cat. -I | 2026-01-09 | 2026-01-09 | RFC | 51I4-BESS-SITE-T-0002 |  | 2026-02-18 | 2026-02-18 | Cat. -I | 51I4-BESS-SITE-T-0010 | [41 empty] | C
173 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | SECURITY BARRACK | In-House | In-house | 51I4-ADNI-CDN-SEB-DC-V-0001 |  | TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m (BESS PLANT AREA)-PSS05B | Approval | Document |  |  |  | RFC | 2026-06-20 | 2026-06-22 | RFC | 51I4-BESS-SITE-T-0046 | [46 empty] | C
19 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Overall Equipment Layout - Electrical | Consultant | Worley | 51I4-WRLY-OEN-YEQ-DE-L-0001 |  | Overall Equipment Layout (showing all the equipments dimensions, coordinate and placement) | [5 empty] | RFC | 2026-08-05 | 2026-08-05 | RFC | 51I4-BESS-SITE-T-0058 | [46 empty] | E
20 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Equipment Sizing | Consultant | Worley | 51I4-WRLY-OEN-YEQ-DE-C-0001 |  | Auxiliary Transformer Sizing Calculation | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
20 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-YEQ-DC-L-0001 |  | Civil cutout details for EMS and other equipment in existing room | [5 empty] | Not Submitted | [50 empty] | C
21 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | SECURITY BARRACK | Consultant | Worley | 51I4-WRLY-OEN-SEB-DC-V-0001 |  | Foundation Drawing of security container(TYPICAL FOUNDATION DETAIL OF PORTA CABIN (20' x 10' ) - 6.096M x 3.040m) | Approval | Drawing |  |  |  | delete |  |  | delete |  | It is not in woley scope as per discussed with Mr. Rupak_22.06.2026 | [45 empty] | C
21 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | ROAD,Drain & Fencing | Consultant | Worley | 51I4-WRLY-OEN-ROD-DC-V-0002 |  | ROAD LAYOUT & Cross Section Details,DRAIN LAYOUT and Details & Typical detail of Plant Fencing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Punith, not in worley scope._20.02.2026 | [45 empty] | C
22 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Shed | Consultant | Worley | 51I4-WRLY-OEN-PCS-DS-U-0001 |  | PCS shed for PSS-05 | Approval | Drawing |  |  |  | Cat. -IV | 2026-02-11 | 2026-02-11 | Cat. -IV | 51I4-BESS-SITE-T-0008 |  | 2026-03-05 | 2026-03-05 | Cat. -IV | 51I4-BESS-SITE-T-0019 | [41 empty] | S
22 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Platform | Consultant | Worley | 51I4-WRLY-OEN-PCS-DE-L-0001 |  | Electrical Equipment Layout for PCS | [5 empty] | Not Submitted | [50 empty] | E
23 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Foundation | Consultant | Worley | 51I4-WRLY-OEN-PCS-DC-V-0002 |  | Pile cap with Column details (insert plates, foundation bolts etc) | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
23 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Platform | Consultant | Worley | 51I4-WRLY-OEN-PCS-DC-V-0001 |  | LAYOUT FOR PCS ROOM SLAB BEAM PLAN & SECTION DETAIL (including handrail, cut out, staircase arrangement etc.) | Approval | Drawing |  |  |  | Cat. -I_Star | NR |  |  |  |  | 2026-02-25 | 2026-02-25 | Cat. -I_Star | 51I4-BESS-SITE-T-0015 |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51I4-BESS-SITE-T-0054 | [36 empty] | C
24 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Platform | Consultant | Worley | 51I4-WRLY-OEN-PCS-DC-Q-0001 |  | Architectural drawings- PCS room(GA drawing) | [5 empty] | Cat. -I_Star | 2026-07-30 | 2026-07-30 | Cat. -I_Star | 51I4-BESS-SITE-T-0057 | [46 empty] | C
24 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | PCS Platform | Consultant | Worley | 51I4-WRLY-OEN-PCS-DC-G-0001 |  | Typical cable tray support below & above PCS platform | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 51I4-BESS-SITE-T-0049 | [46 empty] | C
25 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT-FO Cable | Consultant | Worley | 51I4-WRLY-OEN-OFC-DE-B-0001 |  | FO Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-28 | 2026-05-28 | RFC | 51I4-BESS-SITE-T-0038 | [46 empty] | E
25 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Plant Lightning Layout | Consultant | Worley | 51I4-WRLY-OEN-LPS-DE-L-0001 |  | BESS Lightning Arrested LAYOUT | Approval | Drawing |  |  |  | RFC | 2026-05-30 | 2026-05-30 | RFC | 51I4-BESS-SITE-T-0040 | [46 empty] | E
26 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Plant Lightning design | Consultant | Worley | 51I4-WRLY-OEN-LPS-DE-C-0001 |  | Plant Lightning sizing calculation | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
26 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DS-U-0001 |  | LCR Platform shed for PSS-5B | [5 empty] | Not Submitted | [50 empty] | S
27 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DE-L-0001 |  | Electrical Equipment Layout for LCR | [5 empty] | Cat. -I | 2026-04-09 | 2026-04-09 | Cat. -I | 51I4-BESS-SITE-T-0025 | [46 empty] | E
27 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DC-V-0003 |  | LCR PLATFORM SHED- LAYOUT AND RC DETAILS OF LCR PLATFORM | [5 empty] | Cat. -I_Star | NR |  |  |  |  | 2026-02-14 | 2026-02-16 | Cat. -I | 51I4-BESS-SITE-T-0009 |  | 2026-04-21 | 2026-04-21 | Cat. -I | 51I4-BESS-SITE-T-0026 |  | NR |  |  |  |  | 2026-07-27 | 2026-07-27 | Cat. -I_Star | 51I4-BESS-SITE-T-0056 | [26 empty] | C
28 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DC-V-0002 |  | Slab & beam Details for Local Control Room, cut out, staircase, foundation bolts. | Approval | Drawing |  |  |  | delete |  |  | delete |  | As discussed with Mr. Rupak | [45 empty] | C
28 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DC-V-0001 |  | Foundation & beam Layout for Local Control Room | Approval | Drawing |  |  |  | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
29 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DC-Q-0001 |  | architectural drawings- Local control room | [5 empty] | RFC | 2026-07-25 | 2026-07-25 | RFC | 51I4-BESS-SITE-T-0053 | [46 empty] | C
29 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | LCR Platform | Consultant | Worley | 51I4-WRLY-OEN-LCR-DC-G-0001 |  | Typical cable tray support below & above LCR platform | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | C
30 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Illumination | Consultant | Worley | 51I4-WRLY-OEN-ILS-DE-L-0001 |  | Illumination Layout for Complete Plot & Buildings | Approval | Drawing |  |  |  | RFC | 2026-05-20 | 2026-05-20 | RFC | 51I4-BESS-SITE-T-0033 | [46 empty] | E
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Illumination | Consultant | Worley | 51I4-WRLY-OEN-ILS-DE-B-0001 |  | Illumination Cable Schedule | Approval | Document | 2026-05-08 |  |  | Not Submitted | [50 empty] | E
30 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT-FO Cable | Consultant | Worley | 51I4-WRLY-OEN-HTC-DE-L-0001 |  | HT & FO Cable Routing Layout | Approval | Drawing |  |  |  | RFC | 02-04-2026 19-05-2026 | 02-04-2026_I 19-05-2026 | RFC | 51I4-BESS-SITE-T-0023 51I4-BESS-SITE-T-0031 |  | 2026-08-05 | 2026-08-05 | RFC | 51I4-BESS-SITE-T-0058 | [41 empty] | E
31 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT-FO Cable | Consultant | Worley | 51I4-WRLY-OEN-HTC-DE-G-0001 |  | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing |  |  |  | RFC | 2026-05-19 | 2026-05-19 | RFC | 51I4-BESS-SITE-T-0031 |  | 2026-08-05 | 2026-08-05 | RFC | 51I4-BESS-SITE-T-0058 | [41 empty] | E
31 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | HT-FO Cable | Consultant | Worley | 51I4-WRLY-OEN-HTC-DE-B-0001 |  | HT Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-30 | 2026-05-30 | RFC | 51I4-BESS-SITE-T-0040 |  | 2026-06-19 | 2026-06-19 | RFC | 51I4-BESS-SITE-T-0045 | [41 empty] | E
32 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | High Mast | Consultant | Worley | 51I4-WRLY-OEN-HML-DC-V-0001 |  | High Mast - Foundation layout and drawing | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As discusssed with Mr. Rupak, not in worley scope._21.02.2026 | [45 empty] | C
34 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control & Auxillary Cable | Consultant | Worley | 51I4-WRLY-OEN-HLC-DE-L-0001 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | [5 empty] | RFC | 22-05-2026 29-05-2026 | 22-05-2026 29-05-2026 | RFC | 51I4-BESS-SITE-T-0037 51I4-BESS-SITE-T-0039 | [46 empty] | E
33 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control & Auxillary Cable | Consultant | Worley | 51I4-WRLY-OEN-HLC-DE-L-0002 |  | Control & Auxiliary Cable typical section details (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, illumination ) | [5 empty] | RFC | 2026-05-29 | 2026-05-29 | RFC | 51I4-BESS-SITE-T-0039 | [46 empty] | E
33 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control & Auxillary Cable | Consultant | Worley | 51I4-WRLY-OEN-HLC-DE-L-0003 |  | Control & Auxiliary Cable Routing Layout (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
32 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control & Auxillary Cable | Consultant | Worley | 51I4-WRLY-OEN-HLC-DE-L-0004 |  | Control & Auxiliary Cable typical section details (Communication, EMS, RS 485) |  |  | 2026-05-01 |  |  | Not Submitted | [50 empty] | E
34 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Control & Auxillary Cable | Consultant | Worley | 51I4-WRLY-OEN-HLC-DE-B-0001 |  | Control & Auxiliary Cable Schedule (Communication, EMS, Control, ACDB, MV SGR, RS 485, BCT, LCR, NIFPS, FDAS, ) | Approval | Document |  |  |  | RFC | 2026-05-21 | 2026-05-21 | RFC | 51I4-BESS-SITE-T-0035 |  | 2026-08-05 | 2026-08-05 | RFC | 51I4-BESS-SITE-T-0058 | [41 empty] | E
35 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DS-U-0001 |  | MV SGR Platform shed for PSS-5B | Approval | Drawing |  |  |  | Cat. -I | 2026-02-09 | 2026-02-09 | Cat. -IV | 51I4-BESS-SITE-T-0007 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 51I4-BESS-SITE-T-0014 | [41 empty] | S
35 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DE-L-0001 |  | Electrical Equipment Layout for MV SGR | [5 empty] | RFC | 2026-06-03 | 2026-06-03 | RFC | 51I4-BESS-SITE-T-0042 | [46 empty] | E
36 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DC-V-0002 |  | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
36 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DC-V-0001 |  | Slab & beam Details for Outdoor Switchgear Room, cut out, staircase, foundation bolts, handrails | Approval | Drawing |  |  |  | Cat. -I_Star | NR |  |  |  | As per the received mail from Mr. punith_18.06.2026 | 2026-06-11 | 2026-06-11 | Cat. -I_Star | 51I4-BESS-SITE-T-0048 | Drawing number 51I4-WRLY-EDN-HGR-DC-V-0001 is mentioned in the drawing. As discussed with Mr. Punith, drawing number will be change in the next revision_11.07.2026 | [40 empty] | C
37 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DC-Q-0001 |  | Architectural drawings- MV switchgear room | [5 empty] | Cat. -I_Star | 2026-08-07 | 2026-08-08 | Cat. -I_Star | 51I4-BESS-SITE-T-0060 | [46 empty] | C
37 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | MV SGR Platform | Consultant | Worley | 51I4-WRLY-OEN-HGR-DC-G-0001 |  | Typical cable tray support below & above MV SGR platform | Approval | Drawing |  |  |  | Not Submitted | [50 empty] | C
38 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Consultant | Worley | 51I4-WRLY-OEN-HFL-DE-L-0002 |  | Harmonic Filter Earthing Layout-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
38 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Consultant | Worley | 51I4-WRLY-OEN-HFL-DE-L-0001 |  | Harmonic filter Equipmenr Layout-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
39 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Consultant | Worley | 51I4-WRLY-OEN-HFL-DE-B-0001 |  | Harmonic Filter Cable schedule-BESS | Approval | Document |  |  |  | Not Submitted | [50 empty] | E
39 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Harmonic Filter | Consultant | Worley | 51I4-WRLY-OEN-HFL-DC-V-0001 |  | HARMONIC FILTER FOUNDATION LAYOUT AND RC DETAILS | Approval | Document |  |  |  | Not Submitted | [50 empty] | C
40 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-GEN-DE-L-0003 |  | CT Modification, cable termination, electrical design detailing | [5 empty] | delete |  |  | delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
40 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-GEN-DE-L-0002 |  | Cabling and routing details for EMS & Battery room equipment at existing PSS (including cable schedule). | [5 empty] | Not Submitted | [50 empty] | E
41 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-GEN-DE-L-0001 |  | Equipment layout for EMS and other equipment in existing room modification | [5 empty] | Not Submitted | [50 empty] | E
41 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-GEN-DC-V-0001 |  | Foundation & beam column, slab details for battery room | [5 empty] | Not Submitted | [50 empty] | C
42 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Existing PSS Modification | Consultant | Worley | 51I4-WRLY-OEN-GEN-DC-U-0001 |  | Structure PEB design for Shed over Battery Room | [5 empty] | delete |  |  | delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
42 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Fighting | Consultant | Worley | 51I4-WRLY-OEN-FFS-DM-L-0001 |  | FIRE FIGHTING SYSTEM LAYOUT FOR PSS 05B BESS PLANT | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | M
43 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Plant Earthing Layout | Consultant | Worley | 51I4-WRLY-OEN-ETH-DE-L-0001 |  | BESS Earthing Layout | Approval | Drawing |  |  |  | RFC | 20-05-2026 30-05-2026 | 20-05-2026 30-05-2026 | RFC | 51I4-BESS-SITE-T-0034 51I4-BESS-SITE-T-0040 | [46 empty] | E
43 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Plant Earthing Design | Consultant | Worley | 51I4-WRLY-OEN-ETH-DE-C-0001 |  | Plant Earthing sizing calculation | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
44 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-S-0001 |  | Technical Specification including BoQ for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
44 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-L-0003 |  | Cable Routing Layout for Master Control Room | Approval |  |  |  |  | Not Submitted | [50 empty] | I
45 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-L-0002 |  | Cable Routing Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
45 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-L-0001 |  | Location Layout for Fire Detection and Alarm System | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
46 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-D-0001 |  | IO LIST FOR EMS |  |  | 2026-04-06 |  |  | Cat. -II | 2026-07-20 | 2026-07-23 | Cat. -II | [47 empty] | I
46 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-B-0003 |  | COMMUNICATION CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV_Star | NR |  |  |  |  | 2026-06-02 | 2026-06-03 | Cat. -IV | 51I4-BESS-SITE-T-0041 |  | 2026-07-23 | 2026-07-27 | Cat. -IV_Star | 51I4-BESS-SITE-T-0055 | [36 empty] | I
47 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-B-0002 |  | CONTROL CABLE SCHEDULE FOR EMS |  |  | 2026-04-06 |  |  | Cat. -IV | NR |  |  |  |  | 2026-07-20 | 2026-07-27 | Cat. -IV | 51I4-BESS-SITE-T-0055 | [41 empty] | I
47 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | EMS | Consultant | Worley | 51I4-WRLY-OEN-EMS-DI-B-0001 |  | Interconnection Schedule for EMS | Approval |  |  |  |  | Delete |  |  | Delete |  | As per the received mail by Mr. Janeshkumar_10.08.2026 | [45 empty] | I
48 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | AC & DC Cable Layout | Consultant | Worley | 51I4-WRLY-OEN-DCA-DE-L-0001 |  | DC cabling from BESS to PCS & AC Cable from PCS to Coupling Transformer- layout | Approval | Drawing |  |  |  | RFC | 20-05-2026 21-05-2026 | 20-05-2026 22-05-2026 | RFC | 51I4-BESS-SITE-T-0034 51I4-BESS-SITE-T-0036 |  | 2026-07-16 | 2026-07-16 | RFC | 51I4-BESS-SITE-T-0051 | [41 empty] | E
48 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | AC & DC Cable Layout | Consultant | Worley | 51I4-WRLY-OEN-DCA-DE-G-0001 |  | AC & DC cable typical Section drawing | Approval | Drawing |  |  |  | RFC | 20-05-2026 21-05-2026 | 20-05-2026 22-05-2026 | RFC | 51I4-BESS-SITE-T-0034 51I4-BESS-SITE-T-0036 |  | 2026-07-16 | 2026-07-16 | RFC | 51I4-BESS-SITE-T-0051 | [41 empty] | E
49 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Cable Sizing | Consultant | Worley | 51I4-WRLY-OEN-DCA-DE-C-0001 |  | All Cable sizing calculation (DC, AC, HT, LT, Aux) | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Janeshkumar & Mr. Kaushal Patel_18.06.2026 | [45 empty] | E
49 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | AC & DC Cable Layout | Consultant | Worley | 51I4-WRLY-OEN-DCA-DE-B-0001 |  | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Cable Schedule | Approval | Document |  |  |  | RFC | 2026-05-19 | 2026-05-19 | RFC | 51I4-BESS-SITE-T-0031 |  | 2206-06-22 | 2206-06-22 | RFC | 51I4-BESS-SITE-T-0047 | [41 empty] | E
50 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Consultant | Worley | 51I4-WRLY-OEN-CTF-DE-L-0001 |  | Electrical Equipment Layout for CT, NIFPS, BOT etc. | [5 empty] | Not Submitted | [50 empty] | E
51 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Consultant | Worley | 51I4-WRLY-OEN-CTF-DC-U-0001 |  | Cable support near coupling transformer area | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 51I4-BESS-SITE-T-0049 | [46 empty] | C
51 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Consultant | Worley | 51I4-WRLY-OEN-CTF-DC-V-0001 |  | COUPLING TRANSFORMER FENCING DETAILS | [5 empty] | Delete |  |  | Delete |  | As per the discussed with Mr. Punit _08.08.2026 | [45 empty] | C
50 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Consultant | Worley | 51I4-WRLY-OEN-CTF-DC-V-0003 |  | Burn Oil Pit- Typical Precaszt Drawing | [5 empty] | RFC | 2026-02-19 | 2026-02-19 | RFC | 51I4-BESS-SITE-T-0011 | [46 empty] | C
52 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | CSS | Consultant | Worley | 51I4-WRLY-OEN-CSS-DE-L-0001 |  | Electrical Equipment Layout for CSS | [5 empty] | RFC | 2026-05-02 | 2026-05-02 | Cat. -I | 51I4-BESS-SITE-T-0028 |  | 2026-08-12 | 2026-08-12 | RFC | 51I4-BESS-SITE-T-0061 | [41 empty] | E
52 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | CSS | Consultant | Worley | 51I4-WRLY-OEN-CSS-DC-V-0001 |  | Foundation for CSS | Approval | Drawing |  |  |  | Cat. -I | 2026-02-05 | 2026-02-05 | RFC | 51I4-BESS-SITE-T-0006 |  | 2026-02-24 | 2026-02-25 | Cat. -I | 51I4-BESS-SITE-T-0014 |  | 2026-04-22 | 2026-04-23 | Cat. -I | 51I4-BESS-SITE-T-0027 | [36 empty] | C
53 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Overall-FDN | Consultant | Worley | 51I4-WRLY-OEN-CIV-DC-V-0001 |  | Overall Foundation layout for BESS | Approval | Drawing |  |  |  | Delete |  |  | Delete |  | As per the received mail from Mr. punith_18.06.2026 | [45 empty] | C
53 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Ovearall Layout - Electrical | Consultant | Worley | 51I4-WRLY-OEN-BES-DE-L-0002 |  | Layout Options | [5 empty] | Not Submitted | [50 empty] | E
54 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Ovearall Layout - Electrical | Consultant | Worley | 51I4-WRLY-OEN-BES-DE-L-0001 |  | Overall Plant Layout of BESS (including all details of Electrical and Civil superimposed for both UG & OG) | Approval | Drawing |  |  |  | RFC | 2026-07-16 | 2026-07-17 | RFC | 51I4-BESS-SITE-T-0052 | Due to crane pad implementation at site . So, not required new revision | 2026-02-26 | 2026-02-26 |  | 51I4-BESS-SITE-T-0017 | [41 empty] | E
54 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Aux Plant SLD | Consultant | Worley | 51I4-WRLY-OEN-BES-DE-E-0002 |  | Auxiliary Power Distribution -SLD | [5 empty] | Cat. -I | 2026-04-01 | 2026-04-02 | Cat. -I | 51I4-BESS-SITE-T-0022 | [46 empty] | E
55 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Overall SLD | Consultant | Worley | 51I4-WRLY-OEN-BES-DE-E-0001 |  | Ovearlla SLD (AC, DC, HT, Harmonic filter) | Approval | Drawing |  |  |  | RFC | 2026-03-02 | 2026-03-02 | Cat. -I | 51I4-BESS-SITE-T-0018 |  | 2026-06-10 | 2026-06-10 | RFC | 51I4-BESS-SITE-T-0043 | [41 empty] | E
55 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Battery Container-CATL | Consultant | Worley | 51I4-WRLY-OEN-BCN-DC-V-0001 |  | Typical details of cable tray support below Battery container foundation/precast. | Approval | Drawing |  |  |  | Cat. -I | 2026-07-11 | 2026-07-11 | Cat. -I | 51I4-BESS-SITE-T-0049 | [46 empty] | C
125 | PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | ROAD | Consultant | Worley | 51I4-WRLY-OEN-ROD-DC-L-0001 |  | Road layout for crane crawler movement | Approval |  | 2026-05-05 |  |  | Cat. -I | NR |  |  |  |  | 2026-05-09 | 2026-05-11 | Cat. -I | 51I4-BESS-SITE-T-0029 | [41 empty] | C
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Coupling Transformer | Consultant | Worley | 51I4-WRLY-OEN-CTF-DS-U-0001 |  | ELECTRICAL ROOM NIFPS PANEL SUPPORTING ARRANGEMENT | Approval |  | 2026-06-26 |  |  | Not Submitted | [50 empty] | S
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Fighting | Vendor | ATPL | 51I4-ATPL-FDS-GEN-DE-B-0001 |  | Cable Schedule | Approval |  | 2026-06-10 |  |  | RFC | NR |  |  |  |  | 2026-08-07 | 2026-08-07 | RFC | 51I4-BESS-SITE-T-0059 | [41 empty] | E
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Fighting | Vendor | ATPL | 51I4-ATPL-FDS-GEN-DE-G-0001 |  | General arrangements of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
| PSS05B_Adani Renewable Energy 44 Limited (ARE44L) | Fire Fighting | Vendor | ATPL | 51I4-ATPL-FDS-GEN-DE-L-0001 |  | Cable route layout of fire detection system | Approval |  | 2026-06-19 |  |  | Not Submitted | [50 empty] | E
[5 empty] | Approval Code |  | No. Of Documens | Percentage
[5 empty] | Under Review |  | 0 | 0%
[5 empty] | RFC |  | 34 | 15.25%
[5 empty] | Cat. -I |  | 45 | 20.18%
[5 empty] | Cat. -I_Star |  | 10 | 4.484%
[5 empty] | Cat. -II |  | 5 | 2.242%
[5 empty] | Cat. -III |  | 0 | 0%
[5 empty] | Cat. -IV |  | 47 | 21.08%
[5 empty] | Cat. -IV_Star |  | 1 | 0.4484%
[5 empty] | AB |  | 0 | 0%
[5 empty] | Total |  | 142 | 63.68%
[5 empty] | Not Submitted |  | 81 | 36.32%
[5 empty] | Grand Total |  | 223 | 100%

## Summary
Description | Overall Completion | Total | Overall Status up to Jul’26
|  | Docs. | Docs. Cum. Received | Documents Approved |  |  |  |  | Documents Under Review | Cum. Total approved | Approved % | Remarks
|  |  |  | Cat I | Cat II | Cat III | Cat IV | Cat IV*
A | Dates | B | C | D | E | F | G | H | I | J = D + E + F | k = j / b
+ G + H
PSS-11 | 13-Apr-26 | 210 | 169 | 96 | 24 | 0 | 47 | 1 | 1 | 168 | 80% | -
PSS-12 | 13-Apr-26 | 200 | 137 | 87 | 4 | 0 | 45 | 1 | - | 137 | 68.5% | -
PSS-10B | 13-Apr-26 | 233 | 164 | 107 | 4 | 0 | 50 | 1 | 2 | 162 | 69.53% | -
PSS-08B | 20-Apr-26 | 239 | 136 | 84 | 5 | 2 | 42 | 2 | 1 | 135 | 56.49% | -
PSS-09 | 20-Apr-26 | 227 | 152 | 101 | 4 | 0 | 43 | 2 | 2 | 150 | 66.08% | -
PSS-05B | 20-Apr-26 | 223 | 142 | 89 | 5 | 0 | 47 | 1 | - | 142 | 63.68% | -

## PSS8-old (hidden)
PSS8_Adani Renewable Energy Thirty-Six Limited (ARE36L) | [14 empty] | Rev.00 |  |  |  |  | Rev.01 |  |  |  |  | Rev.02 |  |  |  |  | Rev.03 |  |  |  |  | Rev.04/0E |  |  |  |  | Rev.05/0F |  |  |  |  | Rev.06/0G |  |  |  |  | Rev.07/0H |  |  |  |  | Rev.08/0I |  |  |  |  | Rev.09/0J
Sr. No. | Project | Package | In-house/Vendor | In-house/Vendor Name2 | Drawing / Document Number | Document Title | Document Category | DOCUMENT TYPE | SUBMISSION STATUS | Schedule Date | FORECAST DATE | Weightage | Design Stage | Status | Recd Date_00 | Comment date_00 | Status_00 | XMTL No._00 | Remarks_00 | Recd Date_01 | Comment date_01 | Status_01 | XMTL No._01 | Remarks_01 | Recd Date_02 | Comment date_02 | Status_02 | XMTL No._02 | Remarks_02 | Recd Date_03 | Comment date_03 | Status_03 | XMTL No._03 | Remarks_03 | Recd Date_04 | Comment date_04 | Status_04 | XMTL No._04 | Remarks_04 | Recd Date_05 | Comment date_05 | Status_05 | XMTL No._05 | Remarks_05 | Recd Date_06 | Comment date_06 | Status_06 | XMTL No._06 | Remarks_06 | Recd Date_07 | Comment date_07 | Status_07 | XMTL No._07 | Remarks_07 | Recd Date_08 | Comment date_08 | Status_08 | XMTL No._08 | Remarks_08 | Recd Date_09 | Comment date_09 | Status_09 | XMTL No._09 | Remarks_09
1 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-G-V-0001 | GA Drawings with List of Fittings for IDT | Approval | Drawing | [5 empty] | A2 | NR |  |  |  |  | 2025-05-21 | 2025-06-16 | A2 | 51B2-BESS-SITE-T-0002
2 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-G-V-0002 | GA OF MARSHALLING BOX & WIRING DIAGRAM and SCHEMATIC DIAGRAM OF COOLING SYSTEM | Approval | Drawing | [5 empty] | A2 | 2025-05-21 | 2025-06-16 | A2 | 51B2-BESS-SITE-T-0002
3 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-G-V-0003 | NIFPS (Nitrogen Injection & Fire Protection System) Drawings | Approval | Drawing | [5 empty] | Not Submitted
4 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-D-V-0001 | GTP of IDT | Approval | Document | [5 empty] | A1 | 2025-05-21 | 2025-06-16 | A1 | 51B2-BESS-SITE-T-0002
5 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-M-V-0001 | O&M Manual of IDT | Approval | Document | [5 empty] | I | 2025-05-21 | 2025-06-16 | I | 51B2-BESS-SITE-T-0002
6 |  | IDT Transformer | Vendor | Tesla | 51B2-E-SEP-IDT-DE-G-V-0004 | ONLINE DRYING SYSTEM DRAWING WITH GUARANRTEED TECHNICAL PARTICULARS | Approval | Drawing | [5 empty] | I | 2025-05-21 | 2025-06-16 | I | 51B2-BESS-SITE-T-0002
7 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCL-BE-R-V-0001 | Certification summary along with certificates including model numbers for Battery Cell | Approval | Document | [5 empty] | Not Submitted
8 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-DE-D-V-0001 | GTP for Battery Rack | Approval | Document | [5 empty] | Not Submitted
9 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-DE-G-V-0001 | GA for Battery Rack | Approval | Drawing | [5 empty] | Not Submitted
10 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-BE-R-V-0001 | Certification summary along with certificates including model numbers for Battery Rack | Approval | Document | [5 empty] | Not Submitted
11 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-DE-D-V-0001 | GTP for Battery Container | Approval | Document | [5 empty] | Not Submitted
12 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-DE-G-V-0001 | GA for Battery Container | Approval | Drawing | [5 empty] | Not Submitted
13 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-BE-R-V-0001 | Certification summary along with certificates including model numbers for Battery Container | Approval | Document | [5 empty] | Not Submitted
14 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-DE-D-V-0001 | GTP for FSS | Approval | Document | [5 empty] | Not Submitted
15 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-DE-G-V-0001 | GA for FSS | Approval | Drawing | [5 empty] | Not Submitted
16 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-BE-R-V-0001 | Certification summary along with certificates including model numbers for FSS | Approval | Document | [5 empty] | Not Submitted
17 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-DE-D-V-0001 | GTP for DC Cable Termination Cabinet | Approval | Document | [5 empty] | Not Submitted
18 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-DE-G-V-0001 | GA for DC Cable Termination Cabinet | Approval | Drawing | [5 empty] | Not Submitted
19 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-BE-R-V-0001 | Certification summary along with certificates including model numbers for DC Cable Termination Cabinet | Approval | Document | [5 empty] | Not Submitted
20 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-DE-D-V-0001 | GTP for HVAC | Approval | Document | [5 empty] | Not Submitted
21 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-DE-G-V-0001 | GA for HVAC | Approval | Drawing | [5 empty] | Not Submitted
22 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-BE-R-V-0001 | Certification summary along with certificates including model numbers for HVAC | Approval | Document | [5 empty] | Not Submitted
23 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-DE-D-V-0001 | GTP for Liquid Cooling | Approval | Document | [5 empty] | Not Submitted
24 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-DE-G-V-0001 | GA for Liquid Cooling | Approval | Drawing | [5 empty] | Not Submitted
25 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-BE-R-V-0001 | Certification summary along with certificates including model numbers for Liquid Cooling | Approval | Document | [5 empty] | Not Submitted
26 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0001 | Control Architecture with equipment list | Approval | Document | [5 empty] | Not Submitted
27 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-M-V-0001 | Maintenance & Installation manual | Approval | Document | [5 empty] | Not Submitted
28 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0001 | Battery Sizing Model | Approval | Drawing | [5 empty] | Not Submitted
29 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-L-V-0001 | 2D Layout | Approval | Drawing | [5 empty] | Not Submitted
30 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-L-V-0002 | 3D Layout | Approval | Drawing | [5 empty] | Not Submitted
31 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-E-V-0001 | SLD - BESS Container | Approval | Drawing | [5 empty] | Not Submitted
32 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-E-V-0002 | Auxilliary Power Supply SLD - BESS Container | Approval | Drawing | [5 empty] | Not Submitted
33 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-B-V-0001 | BoQ | Approval | Document | [5 empty] | Not Submitted
34 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0002 | Model for System Design and Aux Calculation based on Ambient. | Approval | Drawing | [5 empty] | Not Submitted
35 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0003 | Electrical Load spec with protection. | Approval | Drawing | [5 empty] | Not Submitted
36 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0004 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval | Drawing | [5 empty] | Not Submitted
37 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0002 | Quotation including completed proposal pricing sheets and technical datasheets, and all required attachments. | Approval | Document | [5 empty] | Not Submitted
38 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0003 | Input Output list for EMS interface | [7 empty] | Not Submitted
39 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0005 | Modbus mapping register | [7 empty] | Not Submitted
40 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0006 | Wiring details for EMS interface | [7 empty] | Not Submitted
41 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-N-V-0001 | BMS control philoshophy | [7 empty] | Not Submitted
42 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0004 | BMS make and technical datasheet | [7 empty] | Not Submitted
43 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCL-BE-R-V-0101 | Certification summary along with certificates including model numbers for Battery Cell | Approval | Document | [5 empty] | Not Submitted
44 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-DE-D-V-0101 | GTP for Battery Rack | Approval | Document | [5 empty] | Not Submitted
45 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-DE-G-V-0101 | GA for Battery Rack | Approval | Drawing | [5 empty] | Not Submitted
46 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BAR-BE-R-V-0101 | Certification summary along with certificates including model numbers for Battery Rack | Approval | Document | [5 empty] | Not Submitted
47 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-DE-D-V-0101 | GTP for Battery Container | Approval | Document | [5 empty] | Not Submitted
48 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-DE-G-V-0101 | GA for Battery Container | Approval | Drawing | [5 empty] | Not Submitted
49 |  | Battery | Vendor | Vendor | 51B2-E-BTR-BCN-BE-R-V-0101 | Certification summary along with certificates including model numbers for Battery Container | Approval | Document | [5 empty] | Not Submitted
50 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-DE-D-V-0101 | GTP for FSS | Approval | Document | [5 empty] | Not Submitted
51 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-DE-G-V-0101 | GA for FSS | Approval | Drawing | [5 empty] | Not Submitted
52 |  | Battery | Vendor | Vendor | 51B2-E-BTR-FSS-BE-R-V-0101 | Certification summary along with certificates including model numbers for FSS | Approval | Document | [5 empty] | Not Submitted
53 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-DE-D-V-0101 | GTP for DC Cable Termination Cabinet | Approval | Document | [5 empty] | Not Submitted
54 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-DE-G-V-0101 | GA for DC Cable Termination Cabinet | Approval | Drawing | [5 empty] | Not Submitted
55 |  | Battery | Vendor | Vendor | 51B2-E-BTR-DCA-BE-R-V-0101 | Certification summary along with certificates including model numbers for DC Cable Termination Cabinet | Approval | Document | [5 empty] | Not Submitted
56 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-DE-D-V-0101 | GTP for HVAC | Approval | Document | [5 empty] | Not Submitted
57 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-DE-G-V-0101 | GA for HVAC | Approval | Drawing | [5 empty] | Not Submitted
58 |  | Battery | Vendor | Vendor | 51B2-E-BTR-HVA-BE-R-V-0101 | Certification summary along with certificates including model numbers for HVAC | Approval | Document | [5 empty] | Not Submitted
59 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-DE-D-V-0101 | GTP for Liquid Cooling | Approval | Document | [5 empty] | Not Submitted
60 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-DE-G-V-0101 | GA for Liquid Cooling | Approval | Drawing | [5 empty] | Not Submitted
61 |  | Battery | Vendor | Vendor | 51B2-E-BTR-LCO-BE-R-V-0101 | Certification summary along with certificates including model numbers for Liquid Cooling | Approval | Document | [5 empty] | Not Submitted
62 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0101 | Control Architecture with equipment list | Approval | Document | [5 empty] | Not Submitted
63 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-M-V-0101 | Maintenance & Installation manual | Approval | Document | [5 empty] | Not Submitted
64 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0101 | Battery Sizing Model | Approval | Drawing | [5 empty] | Not Submitted
65 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-L-V-0101 | 2D Layout | Approval | Drawing | [5 empty] | Not Submitted
66 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-L-V-0102 | 3D Layout | Approval | Drawing | [5 empty] | Not Submitted
67 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-E-V-0101 | SLD - BESS Container | Approval | Drawing | [5 empty] | Not Submitted
68 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-E-V-0102 | Auxilliary Power Supply SLD - BESS Container | Approval | Drawing | [5 empty] | Not Submitted
69 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-B-V-0101 | BoQ | Approval | Document | [5 empty] | Not Submitted
70 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0102 | Model for System Design and Aux Calculation based on Ambient. | Approval | Drawing | [5 empty] | Not Submitted
71 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0103 | Electrical Load spec with protection. | Approval | Drawing | [5 empty] | Not Submitted
72 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0104 | Degradation profile considering cycle per day, DoD, temperature, etc. | Approval | Drawing | [5 empty] | Not Submitted
73 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0102 | Quotation including completed proposal pricing sheets and technical datasheets, and all required attachments. | Approval | Document | [5 empty] | Not Submitted
74 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0103 | Input Output list for EMS interface | [7 empty] | Not Submitted
75 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0105 | Modbus mapping register | [7 empty] | Not Submitted
76 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-O-V-0106 | Wiring details for EMS interface | [7 empty] | Not Submitted
77 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-N-V-0101 | BMS control philoshophy | [7 empty] | Not Submitted
78 |  | Battery | Vendor | Vendor | 51B2-E-BTR-GEN-DE-D-V-0104 | BMS make and technical datasheet | [7 empty] | Not Submitted
79 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-N-V-0001 | System description document (Overview) | Approval | Drawing | [5 empty] | Not Submitted
80 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-N-V-0002 | Functional description document | Approval | Drawing | [5 empty] | Not Submitted
81 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-N-V-0003 | System configuration document (Mode of operation and control philosophy) | Approval | Drawing | [5 empty] | Not Submitted
82 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-G-V-0001 | Construction and installation drawing – General Arrangement | Approval | Drawing | [5 empty] | Not Submitted
83 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-L-V-0001 | Equipment drawings and specifications | Approval | Drawing | [5 empty] | Not Submitted
84 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-I-V-0001 | Wiring diagrams – Control system | Approval | Drawing | [5 empty] | Not Submitted
85 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-BE-R-V-0001 | Certification summary along with certificates including model numbers | Approval | Document | [5 empty] | Not Submitted
86 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-B-V-0001 | Bill of material | Approval | Document | [5 empty] | Not Submitted
87 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0001 | Degradation profile temperature vs DC voltage, AC voltage, DC current, Power | Approval | Drawing | [5 empty] | Not Submitted
88 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-J-V-0001 | PQ curve | Approval | Drawing | [5 empty] | Not Submitted
89 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-G-V-0002 | General arrangements drawing – PCS | Approval | Drawing | [5 empty] | Not Submitted
90 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-G-V-0003 | General arrangements drawing – DC Box | Approval | Drawing | [5 empty] | Not Submitted
91 |  | PCS | Vendor | Vendor | 51B2-E-PCS-GEN-DE-G-V-0004 | General arrangements drawing – AC box. | Approval | Drawing | [5 empty] | Not Submitted
92 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0002 | System level thermal profile as per site condition | Approval | Drawing | [5 empty] | Not Submitted
93 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-D-V-0001 | GTP | Approval | Document | [5 empty] | Not Submitted
94 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-R-V-0001 | Component /PCB / Controller and Certification report | Approval | Drawing | [5 empty] | Not Submitted
95 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-Q-V-0001 | Control architecture with equipment that would be used, basis on (Section 7: SLD) | Approval | Drawing | [5 empty] | Not Submitted
96 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-M-V-0001 | Maintenance & installation manual | Approval | Document | [5 empty] | Not Submitted
97 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-M-V-0002 | O & M manual | Approval | Document | [5 empty] | Not Submitted
98 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-M-V-0003 | Installation Drawings | Approval | Document | [5 empty] | Not Submitted
99 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-I-V-0002 | Interconnection Drawings | Approval | Drawing | [5 empty] | Not Submitted
100 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-E-V-0002 | Electrical and schematic Drawings | Approval | Drawing | [5 empty] | Not Submitted
101 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DG-L-V-0001 | 2D Layout | Approval | Drawing | [5 empty] | Not Submitted
102 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DG-L-V-0002 | 3D Layout | Approval | Drawing | [5 empty] | Not Submitted
103 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-L-V-0002 | Preliminary electrical Layout | Approval | Drawing | [5 empty] | Not Submitted
104 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-E-V-0001 | Electrical SLD | Approval | Drawing | [5 empty] | Not Submitted
105 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-B-V-0001 | Cable schedules | Approval | Document | [5 empty] | Not Submitted
106 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-N-V-0001 | Interconnection protection philosophy and concept | Approval | Drawing | [5 empty] | Not Submitted
107 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-I-V-0003 | Data Communication Diagrams | Approval | Drawing | [5 empty] | Not Submitted
108 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-B-V-0002 | Maintenance Manual and Schedule | Approval | Document | [5 empty] | Not Submitted
109 | 84 | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-I-V-0004 | Software documentation inclusive of data dictionary and error message list, if applicable | Approval | Drawing | [5 empty] | Not Submitted
110 | 85 | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0003 | Alarm settings | Approval | Drawing | [5 empty] | Not Submitted
111 | 86 | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-M-V-0004 | Training manuals | Approval | Document | [5 empty] | Not Submitted
112 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0004 | System Native files | Approval | Drawing | [5 empty] | Not Submitted
113 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-D-V-0002 | Input Output list for EMS interface | [7 empty] | Not Submitted
114 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0005 | Control and monitoring signals mapping register for EMS | [7 empty] | Not Submitted
115 |  | PCS | Vendor | Vendor | 51B2-E-PCS-PCS-DE-O-V-0006 | Connection details for EMS interface | [7 empty] | Not Submitted
116 |  | CSS | Vendor | Akshar | 51B2-E-SGR-AUT-DE-O-V-0001 | Detailed drawings for 2500KVA, 33 KV CSS (Auxilary Transformer) with Civil foundation | Approval | Drawing | [5 empty] | A1 | 2025-05-16 | 2025-06-03 | A1 |  |  | 2025-06-02 | 2025-06-03 | Under Review |  |  | 2025-06-09 | 2025-06-14 | A1 | 51C2-BESS-SITE-T-0015
117 |  | HT Panel-Outdoor | Vendor | Symatic | 51B2-E-SGR-HGR-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) | [7 empty] | Under Review | 2025-05-17 |  | Under Review
118 |  | ACDB | Vendor | Trisqure | 51B2-E-SGR-ACD-DE-G-V-0001 | GA and Electrical drawing with BOM (With Foundation Drawing) | [7 empty] | Not Submitted
|  | EMS |  | Delton | 51B2-E-CNI-EMS-DE-D-V-0001 | Control and communication data sheet |  | Document | [5 empty] | A1 | 2025-05-27 | 2025-05-28 | A1
|  | HT Cable |  | Diacab | 51B2-E-HLC-HTC-DE-D-V-0001 | GTP FOR 3C X 400 SQMM HT CABLE. | [7 empty] | A1 | 2025-06-03 | 2025-06-03 | A1 | 51B2-BESS-SITE-T-0001
|  | HT Cable |  | Vendor | 51B2-E-HLC-HTC-DE-D-V-0002 | GTP FOR 3C X 400 SQMM HT CABLE. | [7 empty] | Not Submitted
|  | LT Cable |  | Vendor | 51B2-E-HLC-LTC-DE-D-V-0001 | GTP FOR 1CX400 SQQM LT CABLE | [7 empty] | Not Submitted
|  | LT Cable |  | Vendor | 51B2-E-HLC-LTC-DE-D-V-0002 | GTP FOR 1CX400 SQQM LT CABLE | [7 empty] | Not Submitted
|  | Control Cable |  | Paramount |  | GTP of LT 1.1 kV YWY CONTROL CABLE (3C X 2.5 SQ.MM., 5C X 2.5 SQ.MM., 7C X 2.5 SQ.MM., & 4C X 6 SQ.MM.) & A2XFY POWER CABLE (4CX25 SQ.MM.) | [7 empty] | A1 |  |  | A1 |  | For all PSS
119 |  | Battery Container- | In-House | In-house | 51B2-E-CIV-BCN-DC-V-I-0001 | Typical precast foundation ,column, beam detail | Approval | Drawing | [5 empty] | Not Submitted
120 |  | Battery Container- | In-House |  | 51B2-E-CIV-BCN-DC-V-I-0002 | Typical precast foundation ,column, beam detail | Approval | Drawing | [5 empty] | Not Submitted
121 |  | Overall-FDN | In-House | In-house | 51B2-E-CIV-CIV-DC-V-I-0001 | Overall Foundation layout for BESS | Approval | Drawing | [5 empty] | Not Submitted
122 |  | ROAD | In-House | In-house | 51B2-E-CIV-ROD-DC-L-I-0001 | ROAD LAYOUT & Cross Section Details | Approval | Drawing | [5 empty] | Not Submitted
123 | 123 | Drain | In-House | In-house | 51B2-E-CIV-DRN-DC-L-I-0001 | DRAIN LAYOUT and Details | Approval | Drawing | [5 empty] | Not Submitted
124 | 124 | Coupling Transformer Station | In-House | In-house | 51B2-E-CIV-CTF-DC-V-I-0001 | Coupling Transformer Foundation Layout and RC Details | Approval | Drawing | [5 empty] | Not Submitted
125 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-CIV-CTF-DC-V-I-0002 | GA & RC DETAILS OF BURNT OIL PIT FOR Coupling Transformer | Approval | Drawing | [5 empty] | Not Submitted
126 |  | Coupling Transformer Station | In-House | In-house | 51B2-E-CIV-CTF-DC-V-I-0003 | GA & RCC Details for NIFPS System | Approval | Drawing | [5 empty] | Not Submitted
127 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-CIV-CTF-DC-V-I-0004 | Coupling Transformer STATION HT-LT PANEL PLATFROM - R.C.C DETAILS SLAB & BEAM LAYOUT AND TYPICAL DETAILS | Approval | Drawing | [5 empty] | Not Submitted
128 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-CIV-CTF-DC-V-I-0005 | HT-LT PANEL SUPPORTING PLATFROM R.C.C DETAILS | Approval | Drawing | [5 empty] | Not Submitted
129 |  | Battery | In-House | In-house | 51B2-E-CIV-CRK-DC-G-I-0001 | Typical precast detail of cable tray support | Approval | Drawing | [5 empty] | Not Submitted
130 |  | Battery | In-House | In-house | 51B2-E-CIV-CRK-DC-G-I-0002 | Structural Steel/GI for cable support | [7 empty] | Not Submitted
131 |  | Staircase | In-House | In-house | 51B2-E-CIV-STC-DC-G-I-0001 | Typical precast detail of Staircase | Approval | Drawing | [5 empty] | Not Submitted
132 |  | Fencing | In-House | In-house | 51B2-E-CIV-FNG-DC-G-I-0001 | Typical detail of Plant Fencing | Approval | Drawing | [5 empty] | Not Submitted
133 |  | MCR Building | In-House | In-house | 51B2-E-CIV-LCR-DC-L-I-0001 | Foundation beam Layout for Local Control Room | Approval | Drawing | [5 empty] | Not Submitted
134 |  | SGR Buildng | In-House | In-house | 51B2-E-CIV-SGR-DC-L-I-0001 | Foundation beam Layout for Outdoor Switchgear Room | Approval | Drawing | [5 empty] | Not Submitted
135 |  | MCR Building | In-House | In-house | 51B2-E-CIV-LCR-DC-G-I-0001 | Slab Details for Local Control Room | Approval | Drawing | [5 empty] | Not Submitted
136 |  | SGR Buildng | In-House | In-house | 51B2-E-CIV-SGR-DC-G-I-0001 | Slab Details for Outdoor Switchgear Room | Approval | Drawing | [5 empty] | Not Submitted
137 |  | PEB Building | In-House | In-house | 51B2-E-PEB-LCR-DC-G-I-0001 | PEB details for Local Control Room | Approval | Drawing | [5 empty] | Not Submitted
138 |  | PEB Building | In-House | In-house | 51B2-E-PEB-SGR-DC-G-I-0001 | PEB details for Outdoor Switchgear Room | Approval | Drawing | [5 empty] | Not Submitted
139 |  | CSS | In-House | In-house | 51B2-E-CIV-AUT-DC-V-I-0001 | Foundation for CSS | [7 empty] | Not Submitted
140 | 250MW KADAPA | Ovearall Layout | In-House | In-house | 51B2-E-SEP-BES-DE-L-I-0001 | Overall Plant Layout of BESS | Approval | Drawing | [5 empty] | Not Submitted
141 |  | Plant Earthihg Layout | In-House | In-house | 51B2-E-SEP-ETH-DE-L-I-0001 | BESS Earthing Layout | Approval | Drawing | [5 empty] | Not Submitted
142 |  | DC Cableing | In-House | In-house | 51B2-E-SEP-DCA-DE-G-I-0001 | DC cable typical Section drawing | Approval | Drawing | [5 empty] | Not Submitted
143 |  | AC & DC Cable | In-House | In-house | 51B2-E-SEP-DCA-DE-L-I-0001 | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- layout | Approval | Drawing | [5 empty] | Not Submitted
144 |  | BESS yard - AC & DC Cable | In-House | In-house | 51B2-E-SEP-DCA-DE-B-I-0001 | DC cabling from BESS to PCS & AC Cabeling from PCS to Coupling Transformer- Schedule | Approval | Document | [5 empty] | Not Submitted
145 |  | BESS yard - HT-FO Cable | In-House | In-house | 51B2-E-SEP-HTC-DE-L-I-0001 | HT & FO Cable Routing Layout | Approval | Drawing | [5 empty] | Not Submitted
146 |  | BESS yard - HT-FO Cable | In-House | In-house | 51B2-E-SEP-HTC-DE-G-I-0001 | HT Cable TYPICAL SECTION DETAILS DRAWING | Approval | Drawing | [5 empty] | Not Submitted
147 |  | BESS yard - HT-FO Cable | In-House | In-house | 51B2-E-SEP-HTC-DE-B-I-0001 | HT Cable Schedule | Approval | Document | [5 empty] | Not Submitted
148 |  | BESS yard - HT-FO Cable | In-House | In-house | 51B2-E-SEP-OFC-DE-B-I-0001 | FO Cable Schedule | Approval | Document | [5 empty] | Not Submitted
149 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-L-I-0001 | Equipment Layout of Coupling Transformer & Control Room Station-Type-BB (33KV Switchgear) | Approval | Drawing | [5 empty] | Not Submitted
150 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-L-I-0002 | Illumination Layout of Coupling Transformer & Control Room Station Type-BB(33KV Switchgear) | Approval | Drawing | [5 empty] | Not Submitted
151 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-L-I-0003 | Cable route layout of Coupling Transformer & Control Room Station -Type-BB (33KV Switchgear) | Approval | Drawing | [5 empty] | Not Submitted
152 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-L-I-0004 | Earthing Layout of Coupling Transformer & Control Room Station -Type-BB | Approval | Drawing | [5 empty] | Not Submitted
153 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-E-I-0001 | Auxiliary Power Distribution -SLD | Approval | Drawing | [5 empty] | Not Submitted
154 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-B-I-0001 | Control & Auxiliary Cable Schedule of Coupling Transformer & Control Room Station | Approval | Document | [5 empty] | Not Submitted
155 | 250MW KADAPA | Coupling Transformer Station | In-House | In-house | 51B2-E-SEP-CTF-DE-C-I-0001 | Relay Setting of Outdoor HT panel/LT panel at Coupling Transformer & Control Room station | Approval | Document | [5 empty] | Not Submitted
|  | Approval Code |  | No. Of Documens | Percentage
|  | Under Review |  | 1 | 0.6211%
|  | RFC |  | 0 | 0%
|  | A1 |  | 5 | 3.106%
|  | A2 |  | 2 | 1.242%
|  | A3 |  | 0 | 0%
|  | I |  | 2 | 1.242%
|  | AB |  | 0 | 0%
|  | Total |  | 10 | 6.211%
|  | Not Submitted |  | 151 | 93.79%
|  | Grand Total |  | 161 | 100%