## Project Breakdown
Project ID | Project Name | Type | Total Capacity (MW) | Trial Run Done (MW) | COD Done (MW) | Remaining Capacity (MW)
- | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | 137.5 | 125 | 137.5 | 0
- | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | 162.5 | 50 | 112.5 | 50
- | MANDVI | Wind | 247.5 | 0 | 0 | 247.5
- | ARE55L_S10_HSAT_50 MW_PPA | Solar | 62.5 | 0 | 0 | 62.5
- | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | 162.5 | 150 | 162.5 | 0
- | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | 112.5 | 100 | 112.5 | 0
- | AGE25CL_A06_FT_425MW_PPA | Solar | 437.5 | 425 | 275 | 12.5
- | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | 62.5 | 50 | 62.5 | 0
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | 162.5 | 150 | 162.5 | 0
- | APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | 37.5 | 0 | 0 | 37.5
- | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | 37.5 | 25 | 37.5 | 0
- | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | 50 | 37.5 | 50 | 0
- | AGE25BL_BANDHA_FT_500MW_PPA | Solar | 512.5 | 137.5 | 150 | 362.5
- | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | 650 | 262.5 | 275 | 375
- | ASEJ6PL_S07_FT_300MW | Solar | 312.5 | 0 | 0 | 312.5
- | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | 312.5 | 0 | 0 | 312.5
- | ACL_A01_HSAT_50MW_Group_NEW | Solar | 62.5 | 0 | 0 | 62.5
- | ARE41L_A15b_HSAT_50MW | Solar | 62.5 | 0 | 0 | 62.5
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | 162.5 | 0 | 0 | 162.5
- | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | 100 | 0 | 0 | 100
- | ARE55L_A02_HSAT_125MW | Solar | 137.5 | 0 | 0 | 137.5
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | 262.5 | 0 | 0 | 262.5
- | AGE24L_A03_HSAT_250 MW | Solar | 12.5 | 0 | 0 | 12.5
- | ASEJ6PL_S07_FT_300MW_PPA | Solar | 312.5 | 0 | 0 | 312.5
- | NHPC EPC 200 MW Khavda-Internal | Solar | 212.5 | 0 | 0 | 212.5
- | AGE26AL_S06A_FT_234MW | Solar | 250 | 0 | 0 | 250
- | AGEL_S2A_175_MW_HSAT | Solar | 187.5 | 0 | 0 | 187.5
- | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | 75 | 75 | 75 | 0
- | AGE26AL_A16_FT_200MW_PPA | Solar | 212.5 | 150 | 162.5 | 50
- | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | 62.5 | 50 | 62.5 | 0
- | AGEL_S1_100_MW_HSAT | Solar | 112.5 | 0 | 0 | 112.5
- | AGEL_S2A_50_MW_HSAT | Solar | 62.5 | 0 | 0 | 62.5
- | AE2L_S03_HSAT_150MW_MERCHANT | Solar | 162.5 | 0 | 0 | 162.5
- | AGEL_S1_200_MW_HSAT | Solar | 200 | 0 | 0 | 200
- | AGEL_S2B_112.5_MW_HSAT | Solar | 125 | 0 | 0 | 125
- | AGEL_S1_75_MW_HSAT | Solar | 87.5 | 0 | 0 | 87.5
- | AGEL_SE14_HSAT_500MW_HILD | Solar | 512.5 | 0 | 0 | 512.5
- | AGEL_S10_287.5_MW_HSAT | Solar | 300 | 0 | 0 | 300
- | NHPC EPC 400 MW Khavda-Internal | Solar | 400 | 0 | 0 | 400
- | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | 62.5 | 0 | 0 | 62.5
- | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | 512.5 | 0 | 0 | 512.5
- | AGE26AL_A16C_FT_167MW_PPA | Solar | 187.5 | 50 | 112.5 | 75
- | AGE26AL_A16_FT_333MW_PPA | Solar | 350 | 100 | 162.5 | 187.5
- | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | 312.5 | 300 | 312.5 | 0
- | ARE57L_A12_HSAT_350MW_PPA | Solar | 362.5 | 0 | 0 | 362.5
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | 260 | 254.8 | 260 | 0
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | 250 | 0 | 0 | 250
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | 457.6 | 150.8 | 156 | 301.6
- | AHEJ5L PSS-05 (39 Loc.) | Wind | 208 | 202.8 | 208 | 0
- | ARE3L PSS-08 (05 Loc.) | Wind | 31.2 | 26 | 31.2 | 0
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | 67.6 | 62.4 | 67.6 | 0
TOTAL | - | - | 10596.9 | 2934.3 | 3147.8 | 7299.1

## Yearly Totals
Financial Year | Solar Trial Run (MW) | Wind Trial Run (MW) | Solar COD (MW) | Wind COD (MW)
FY25 | 2112.5 | 696.8 | 2425 | 722.8
FY26 | 125 | 0 | 0 | 0
TOTAL | 2237.5 | 696.8 | 2425 | 722.8