## Project Breakdown
Project ID | Project Name | Type | Total Capacity (MW) | Total Blocks/WTGs | Trial Run Only - Blocks/WTGs | Trial Run Only - MW | COD Done - Blocks/WTGs | COD Done - MW | Remaining Capacity (MW)
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | 125 | 10 | 0 | 0 | 11 | 137.5 | 0
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | 150 | 12 | 0 | 0 | 9 | 112.5 | 37.5
- | MANDVI | Wind | 3.3 | 1 | 0 | 0 | 0 | 0 | 3.3
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | 50 | 4 | 0 | 0 | 0 | 0 | 50
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | 150 | 12 | 0 | 0 | 13 | 162.5 | 0
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | 100 | 8 | 0 | 0 | 9 | 112.5 | 0
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | 425 | 34 | 12 | 150 | 22 | 275 | 0
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | 50 | 4 | 0 | 0 | 5 | 62.5 | 0
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | 150 | 12 | 0 | 0 | 13 | 162.5 | 0
FY26-P02 | APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | 25 | 2 | 0 | 0 | 0 | 0 | 25
FY25-P01 | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | 25 | 2 | 0 | 0 | 3 | 37.5 | 0
FY25-P02 | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | 35 | 3 | 0 | 0 | 4 | 50 | 0
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | 500 | 40 | 0 | 0 | 12 | 150 | 350
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | 600 | 48 | 0 | 0 | 22 | 275 | 325
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | 300 | 24 | 0 | 0 | 0 | 0 | 300
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | 300 | 24 | 0 | 0 | 0 | 0 | 300
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | 50 | 4 | 0 | 0 | 0 | 0 | 50
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | 50 | 4 | 0 | 0 | 0 | 0 | 50
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | 150 | 12 | 0 | 0 | 0 | 0 | 150
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | 150 | 12 | 0 | 0 | 0 | 0 | 150
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | 125 | 10 | 0 | 0 | 0 | 0 | 125
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | 250 | 20 | 0 | 0 | 0 | 0 | 250
FY26-P12 | AGE24L_A03_HSAT_250 MW | Solar | 250 | 20 | 0 | 0 | 0 | 0 | 250
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | 300 | 24 | 0 | 0 | 0 | 0 | 300
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | 200 | 16 | 0 | 0 | 0 | 0 | 200
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | 234 | 19 | 0 | 0 | 0 | 0 | 234
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | 175 | 14 | 0 | 0 | 0 | 0 | 175
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | 75 | 6 | 0 | 0 | 6 | 75 | 0
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | 200 | 16 | 0 | 0 | 13 | 162.5 | 37.5
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | 50 | 4 | 0 | 0 | 5 | 62.5 | 0
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | 100 | 8 | 0 | 0 | 0 | 0 | 100
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | 50 | 4 | 0 | 0 | 0 | 0 | 50
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | 150 | 12 | 0 | 0 | 0 | 0 | 150
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | 200 | 16 | 0 | 0 | 0 | 0 | 200
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | 112.5 | 9 | 0 | 0 | 0 | 0 | 112.5
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | 75 | 6 | 0 | 0 | 0 | 0 | 75
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | 500 | 40 | 0 | 0 | 0 | 0 | 500
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | 287.5 | 23 | 0 | 0 | 0 | 0 | 287.5
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | 400 | 32 | 0 | 0 | 0 | 0 | 400
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | 50 | 4 | 0 | 0 | 0 | 0 | 50
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | 500 | 40 | 0 | 0 | 0 | 0 | 500
- | AGE26AL_A16C_FT_167MW_PPA | Solar | 167 | 13 | 0 | 0 | 9 | 112.5 | 54.5
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | 333 | 27 | 0 | 0 | 13 | 162.5 | 170.5
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | 292 | 23 | 0 | 0 | 25 | 312.5 | 0
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | 350 | 28 | 0 | 0 | 0 | 0 | 350
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | 5.2 | 1 | 0 | 0 | 50 | 260 | 0
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | 5 | 1 | 0 | 0 | 0 | 0 | 5
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | 5.2 | 1 | 0 | 0 | 30 | 156 | 0
- | AHEJ5L PSS-05 (39 Loc.) | Wind | 5.2 | 1 | 0 | 0 | 40 | 208 | 0
- | ARE3L PSS-08 (05 Loc.) | Wind | 5.2 | 1 | 0 | 0 | 6 | 31.2 | 0
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | 5.2 | 1 | 0 | 0 | 13 | 67.6 | 0
TOTAL | - | - | 8845.3 | 712 | 12 | 150 | 333 | 3147.8 | 6367.3

## Yearly Totals
Financial Year | Solar TR (MW) | Wind TR (MW) | Solar COD (MW) | Wind COD (MW)
FY25 | 25 | 0 | 2425 | 722.8
FY26 | 125 | 0 | 0 | 0
TOTAL | 150 | 0 | 2425 | 722.8