## Block-Level Verification
Project ID | Project Name | Type | Block/WTG | MW | Status | Trial Run Start | Trial Run Finish | COD Start | COD Finish
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY26-P06 | ACL_A01_HSAT_50MW_Group_NEW | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ACL_A01_HSAT_50MW_Group_NEW | Solar | 5 blocks/WTGs | 50 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-05
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-05
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-05 | 12.5 | COD | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-05
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-06 | 12.5 | COD | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-05
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-07 | 12.5 | COD | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-08 | 12.5 | COD | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-09 | 12.5 | COD | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | BLOCK-10 | 12.5 | COD | 2025-12-24 | 2025-12-26 | 2025-12-24 | 2025-12-26
FY25-P08 | ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | Unknown | 0 | COD | - | - | 2025-12-26 | 2025-12-26
| >>> TOTAL: ACL_A1_FT_125 MW_GROUP_Commissioned | Solar | 11 blocks/WTGs | 125 | COD: 11 (125.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P21 | AE2L_S03_HSAT_150MW_MERCHANT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AE2L_S03_HSAT_150MW_MERCHANT | Solar | 13 blocks/WTGs | 150 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 150.0 MW
FY26-P12 | AGE24L_A03_HSAT_250 MW | Solar | Unknown | 250 | Pending | - | - | - | -
| >>> TOTAL: AGE24L_A03_HSAT_250 MW | Solar | 1 blocks/WTGs | 250 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 250.0 MW
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-05 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-06 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-07 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-08 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-09 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-10 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-11 | 12.5 | COD | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | BLOCK-12 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P07 | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | Unknown | 0 | COD | - | - | 2026-03-18 | 2026-03-18
| >>> TOTAL: AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | Solar | 13 blocks/WTGs | 150 | COD: 13 (150.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-02 | 12.5 | COD | - | - | 2026-03-26 | 2026-03-26
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-04 | 12.5 | COD | - | - | 2026-03-26 | 2026-03-26
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-07 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-08 | 12.5 | COD | - | - | 2026-03-26 | 2026-03-26
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-09 | 12.5 | COD | - | - | 2026-03-26 | 2026-03-26
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-10 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-11 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | BLOCK-12 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21
FY25-P06 | AGE24L_S05_HSAT_150MW_MERCHANT | Solar | Unknown | 0 | COD | - | - | 2026-03-19 | 2026-03-19
| >>> TOTAL: AGE24L_S05_HSAT_150MW_MERCHANT | Solar | 13 blocks/WTGs | 150 | COD: 9 (100.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY25-P18&19&20 | AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE25BL_A15a_HSAT_50 MW_MERCHANT | Solar | 5 blocks/WTGs | 50 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-01 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-02 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-03 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-05 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-06 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-07 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-08 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-09 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-10 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-15 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-20 | 12.5 | COD | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-25 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-26 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-27 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-28 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-29 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-30 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-31 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-32 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-33 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-34 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-35 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-36 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-37 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-38 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-39 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY25-BANDHA_500MW | AGE25BL_BANDHA_FT_500MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE25BL_BANDHA_FT_500MW_PPA | Solar | 41 blocks/WTGs | 500 | COD: 11 (137.5 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 362.5 MW
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | Unknown | 5.2 | COD | - | - | 2026-03-28 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 1-354 | 5.2 | COD | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 10-353 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 11-432 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 12-380 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 13-404 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 14-329 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 15-403 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 16-431 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 17-429 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 18-328 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-14
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 19-456 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 2-382 | 5.2 | COD | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 20-481 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 21-455 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 22-505 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 23-504 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 24-479 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 25-233A | 5.2 | COD | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 26-524 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 27-454 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 28-480 | 5.2 | COD | 2026-02-19 | 2026-02-19 | 2026-02-20 | 2026-02-22
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 29-503 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 3-407 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 30-482 | 5.2 | COD | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 31-430 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 32-523 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 33-502 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 34-501 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 35-522 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 36 457 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 37-473 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 38-474 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 39-399 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 4-433 | 5.2 | COD | 2026-02-10 | 2026-02-10 | 2026-02-11 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 40-448 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 41-398 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 42-424 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 43-373 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 44-449 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 45-425 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 46-423 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 47-450 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 48-532 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 49 516 | 5.2 | COD | 2026-03-27 | 2026-03-28 | 2026-03-27 | 2026-03-28
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 5-381 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 6-406 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 7-405 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 8-379 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
- | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | WTG 9-378 | 5.2 | COD | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-16
| >>> TOTAL: AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | Wind | 50 blocks/WTGs | 260 | COD: 50 (260.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | Unknown | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 1 - KH584 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 10 - KH537 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 11 - KH543 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 12 - KH542 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 13 - KH536 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 14 - KH548 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 15 - KH567 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 16 - KH568 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 17 - KH569 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 18 - KH572 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 19 - KH573 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 2 - KH563 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 20 - KH585 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 21 - KH574 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 22 - KH593 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 23 - KH594 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 24 - KH586 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 25 - KH602 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 26 - KH601 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 27 - KH609 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 28 - KH616 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 29 - KH610 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 3 - KH562 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 30 - KH577 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 31 - KH587 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 32 - KH595 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 33 - KH578 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 34 - KH603 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 35 - KH576 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 36 - KH571 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 37 - KH566 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 38 - KH575 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 39 - KH570 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 4 - KH561 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 40 - KH545 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 41 - KH546 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 42 - KH547 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 43 - KH564 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 44 - KH565 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 45 - KH535 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 46 - KH534 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 47 - KH533 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 48 - KH540 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 49 - KH541 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 5 - KH559 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 6 - KH560 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 7 - KH558 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 8 - KH544 | 5 | Pending | - | - | - | -
- | AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | WTG 9 - KH549 | 5 | Pending | - | - | - | -
| >>> TOTAL: AGE25CL PSS-18 (49 Loc.) - Phase-4 | Wind | 50 blocks/WTGs | 250 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 250.0 MW
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-07 | 12.5 | COD | 2026-02-04 | 2026-02-04 | 2026-02-06 | 2026-02-10
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-08 | 12.5 | COD | 2026-02-04 | 2026-02-06 | 2026-02-06 | 2026-02-10
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-09 | 12.5 | COD | 2026-02-04 | 2026-02-06 | 2026-02-06 | 2026-02-10
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-10 | 12.5 | COD | 2026-02-04 | 2026-02-06 | 2026-02-06 | 2026-02-10
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-11 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-12 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-13 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-14 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-15 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-16 | 12.5 | COD | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-17 | 12.5 | Trial Run | 2026-02-28 | 2026-02-28 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-18 | 12.5 | Trial Run | 2026-02-28 | 2026-02-28 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-19 | 12.5 | COD | 2026-02-28 | 2026-02-28 | 2026-03-24 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-20 | 12.5 | COD | 2026-02-28 | 2026-02-28 | 2026-03-24 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-21 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-22 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-23 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-24 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-25 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-26 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-27 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-28 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-29 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-30 | 12.5 | COD | 2026-03-29 | 2026-03-29 | 2026-03-30 | 2026-03-30
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-31 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-29 | 2026-03-30
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-32 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-33 | 12.5 | Trial Run | 2026-05-05 | 2026-05-05 | - | -
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-34 | 12.5 | COD | 2026-03-29 | 2026-03-29 | 2026-03-30 | 2026-03-30
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-35 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-36 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-37 | 12.5 | COD | 2026-03-29 | 2026-03-29 | 2026-03-30 | 2026-03-30
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-38 | 12.5 | COD | 2026-03-29 | 2026-03-29 | 2026-03-30 | 2026-03-30
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-39 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | BLOCK-40 | 12.5 | COD | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-24
FY25-P15 | AGE25CL_A06_FT_425MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE25CL_A06_FT_425MW_PPA | Solar | 35 blocks/WTGs | 425 | COD: 22 (275.0 MW) ¦ TR: 12 (150.0 MW) ¦ Remaining: 0.0 MW
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-05 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
FY25-P09 | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | BLOCK-06 | 12.5 | COD | 2025-12-01 | 2025-12-01 | 2025-12-03 | 2025-12-03
| >>> TOTAL: AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | Solar | 6 blocks/WTGs | 75 | COD: 6 (75.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | Unknown | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 1 - WTG 401 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 10 - WTG 533 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 11- WTG 426 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 12-WTG 535 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 13- WTG 519 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 14- WTG 451 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 15 WTG 536 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 16 WTG 476 | 5.2 | COD | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 17 WTG-477 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 18 WTG 521 | 5.2 | COD | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 19 WTG 478 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 2 - WTG 497 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 20 WTG 520 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 21 WTG 427 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 22 WTG 452 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 23 WTG 428 | 5.2 | COD | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 24 WTG 453 | 5.2 | COD | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 25 WTG 499 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 26 WTG 500 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 27 WTG 402 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 28-KH53 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 29-KH54 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 3 - WTG 518 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 30-KH59 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 31-KH589 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 32-KH55 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 33-KH58 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 34-KH588 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 35-KH581 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 36-KH56 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 37-KH611 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 38-KH57 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 39-KH599 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 4 - WTG 496 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 40-KH604 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 41-KH592 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 42-KH612 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 43-KH606 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 44-KH596 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 45-KH597 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 46-KH617 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 47-KH605 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 48-KH613 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 49-KH591 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 5 - WTG 517 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 50-KH607 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 51-KH580 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 52-KH600 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 53-KH579 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 54-KH614 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 55-KH619 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 56-KH557 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 57-KH554 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 58-KH583 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 59-KH555 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 6 - WTG 475 | 5.2 | COD | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 60-KH608 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 61-KH615 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 62-KH34 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 63-KH620 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 64-KH509 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 65-KH621 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 66-KH590 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 67-KH618 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 68-KH556 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 69-KH52 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 7 - WTG 534 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 70-KH582 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 71-KH 598 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 72 KH 61 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 73 KH 60 | 5.2 | COD | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 74 KH 68 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 75 KH 522 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 76 KH 51 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 77 KH 552 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 78 KH 35 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 79 KH 47 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 8 - WTG 377 | 5.2 | COD | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-20
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 80 KH 508 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 81 KH 550 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 82 KH 523 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 83 KH 553 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 84 KH 551 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 85 KH 478 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 86 KH 521 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 87 KH 622 | 5.2 | Pending | - | - | - | -
- | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | WTG 9 - WTG 498 | 5.2 | COD | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20
| >>> TOTAL: AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | Wind | 88 blocks/WTGs | 457.6 | COD: 29 (150.8 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 306.8 MW
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-10-14 | 2025-10-14 | 2026-02-14 | 2026-02-14
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-10-14 | 2025-10-14 | 2026-02-14 | 2026-02-14
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14
FY25-P14 | AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | Unknown | 0 | COD | - | - | 2025-10-14 | 2025-10-14
| >>> TOTAL: AGE26AL_A10a_FT_50MW_PPA_Commissioned | Solar | 5 blocks/WTGs | 50 | COD: 5 (50.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-01 | 12.5 | COD | - | - | 2026-03-27 | 2026-03-27
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-02 | 12.5 | COD | - | - | 2026-03-27 | 2026-03-27
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-08 | 12.5 | COD | - | - | 2026-03-27 | 2026-03-27
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-09 | 12.5 | COD | - | - | 2026-03-27 | 2026-03-27
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-10 | 12.5 | COD | 2026-02-23 | 2026-02-23 | 2026-03-13 | 2026-03-13
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-11 | 12.5 | COD | 2026-02-23 | 2026-02-23 | 2026-03-13 | 2026-03-13
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-12 | 12.5 | COD | 2026-02-23 | 2026-02-23 | 2026-03-13 | 2026-03-13
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-13 | 12.5 | COD | 2026-02-23 | 2026-02-23 | 2026-03-13 | 2026-03-13
- | AGE26AL_A16C_FT_167MW_PPA | Solar | BLOCK-14 | 4.5 | Pending | - | - | - | -
- | AGE26AL_A16C_FT_167MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE26AL_A16C_FT_167MW_PPA | Solar | 15 blocks/WTGs | 167 | COD: 8 (100.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 67.0 MW
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-01 | 12.5 | COD | 2026-01-23 | 2026-01-23 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-02 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-19
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-03 | 12.5 | COD | 2026-01-23 | 2026-01-23 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-04 | 12.5 | COD | 2026-01-23 | 2026-01-23 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-05 | 12.5 | COD | 2026-01-23 | 2026-01-23 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-06 | 12.5 | COD | 2026-02-10 | 2026-02-10 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-07 | 12.5 | COD | 2026-02-10 | 2026-02-10 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-08 | 12.5 | COD | 2026-02-10 | 2026-02-10 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-11 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-19 | 2026-03-19
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-12 | 12.5 | COD | 2026-02-10 | 2026-02-10 | 2026-03-13 | 2026-03-13
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-14 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-19 | 2026-03-19
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-15 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-19 | 2026-03-19
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY25-P11 | AGE26AL_A16_FT_200MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE26AL_A16_FT_200MW_PPA | Solar | 17 blocks/WTGs | 200 | COD: 12 (150.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-01 | 12.5 | COD | 2026-03-06 | 2026-03-06 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-05 | 12.5 | COD | - | - | 2026-03-29 | 2026-03-30
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-06 | 12.5 | COD | - | - | 2026-03-29 | 2026-03-30
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-11 | 12.5 | COD | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-12 | 12.5 | COD | 2026-03-06 | 2026-03-06 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-13 | 12.5 | COD | 2026-03-06 | 2026-03-06 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-15 | 12.5 | COD | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-17 | 12.5 | COD | 2026-03-06 | 2026-03-06 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-22 | 12.5 | COD | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-25 | 12.5 | COD | - | - | 2026-03-29 | 2026-03-30
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-26 | 12.5 | COD | - | - | 2026-03-29 | 2026-03-30
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | BLOCK-27 | 8 | COD | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13
FY25-P13 | AGE26AL_A16_FT_333MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE26AL_A16_FT_333MW_PPA | Solar | 28 blocks/WTGs | 333 | COD: 12 (145.5 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 187.5 MW
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-23
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-23
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-23
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-23
FY25-P10 | AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | Unknown | 0 | COD | - | - | 2026-01-23 | 2026-01-23
| >>> TOTAL: AGE26AL_A16_FT_50MW_PPA_Commissioned | Solar | 5 blocks/WTGs | 50 | COD: 5 (50.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | BLOCK-19 | 9 | Pending | - | - | - | -
FY26-P18 | AGE26AL_S06A_FT_234MW | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE26AL_S06A_FT_234MW | Solar | 20 blocks/WTGs | 234 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 234.0 MW
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
- | AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGE26BL_A03_HSAT_250 MW_MLP T4 AP (Old Backup) | Solar | 21 blocks/WTGs | 250 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 250.0 MW
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-05 | 12.5 | COD | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-06 | 12.5 | COD | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-07 | 12.5 | COD | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-08 | 12.5 | COD | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-09 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-10 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-11 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-12 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-13 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-14 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-15 | 12.5 | COD | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-16 | 12.5 | COD | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-17 | 12.5 | COD | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-18 | 12.5 | COD | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-19 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-20 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-21 | 12.5 | COD | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-12
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-22 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-23 | 12.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | BLOCK-24 | 4.5 | COD | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18
FY25-P05 | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | Unknown | 0 | COD | - | - | 2026-03-18 | 2026-03-18
| >>> TOTAL: AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | Solar | 25 blocks/WTGs | 292 | COD: 25 (292.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-58 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-59 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-60 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-61 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-62 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-63 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-64 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-65 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-66 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-67 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-68 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-69 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-70 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-71 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-72 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-73 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-74 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-75 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-76 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-77 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-78 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-79 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | BLOCK-80 | 12.5 | Pending | - | - | - | -
FY27-P05 | AGEL_S10_287.5_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S10_287.5_MW_HSAT | Solar | 24 blocks/WTGs | 287.5 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 287.5 MW
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-28 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-29 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-30 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-31 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-32 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-33 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-34 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | BLOCK-35 | 12.5 | Pending | - | - | - | -
FY26-P19 | AGEL_S1_100_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S1_100_MW_HSAT | Solar | 9 blocks/WTGs | 100 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 100.0 MW
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-36 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-37 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-38 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-41 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-42 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-43 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-44 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-45 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-46 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-47 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-48 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-49 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-50 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK-51 | 12.5 | Pending | - | - | - | -
FY26-P22 | AGEL_S1_200_MW_HSAT | Solar | BLOCK39 | 12.5 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S1_200_MW_HSAT | Solar | 16 blocks/WTGs | 200 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 200.0 MW
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-52 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-53 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-54 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-55 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-56 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | BLOCK-57 | 12.5 | Pending | - | - | - | -
FY26-P25 | AGEL_S1_75_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S1_75_MW_HSAT | Solar | 7 blocks/WTGs | 75 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 75.0 MW
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-1 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-2 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-3 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-4 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | BLOCK-9 | 12.5 | Pending | - | - | - | -
FY26-P17 | AGEL_S2A_175_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S2A_175_MW_HSAT | Solar | 15 blocks/WTGs | 175 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 175.0 MW
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | BLOCK-5 | 12.5 | Pending | - | - | - | -
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | BLOCK-6 | 12.5 | Pending | - | - | - | -
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | BLOCK-7 | 12.5 | Pending | - | - | - | -
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | BLOCK-8 | 12.5 | Pending | - | - | - | -
FY26-P20 | AGEL_S2A_50_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S2A_50_MW_HSAT | Solar | 5 blocks/WTGs | 50 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-25 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-26 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | BLOCK-27 | 12.5 | Pending | - | - | - | -
FY26-P24 | AGEL_S2B_112.5_MW_HSAT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_S2B_112.5_MW_HSAT | Solar | 10 blocks/WTGs | 112.5 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 112.5 MW
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-25 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-26 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-27 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-28 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-29 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-30 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-31 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-32 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-33 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-34 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-35 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-36 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-37 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-38 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-39 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY27-P03&04 | AGEL_SE14_HSAT_500MW_HILD | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AGEL_SE14_HSAT_500MW_HILD | Solar | 41 blocks/WTGs | 500 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 500.0 MW
- | AHEJ5L PSS-05 (39 Loc.) | Wind | Unknown | 5.2 | COD | - | - | 2026-03-02 | 2026-03-02
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 1-131 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 10-221 | 5.2 | COD | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-29
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 11-132 | 5.2 | COD | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-26
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 12-243 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 13-244 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 14-133 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 15-200 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 16-267 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 17-553 | 5.2 | COD | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-03-02
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 18-222 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 19-291 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 2-551 | 5.2 | COD | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-03-02
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 20-154 | 5.2 | COD | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-29
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 21-223 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 22-198 | 5.2 | COD | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-29
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 23-316 | 5.2 | COD | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-24
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 24-201 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 25-176 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 26-292 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 27-177 | 5.2 | COD | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-24
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 28-245 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 29-268 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 3-314 | 5.2 | COD | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-24
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 30-197 | 5.2 | COD | 2025-11-26 | 2025-11-28 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 31-179 | 5.2 | COD | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-26
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 32-175 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 33-152 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 34-156 | 5.2 | COD | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-26
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 35-178 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 36-155 | 5.2 | COD | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-26
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 37-153 | 5.2 | COD | 2025-11-26 | 2025-11-26 | 2025-11-27 | 2025-12-01
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 38-554 | 5.2 | COD | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-29
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 39-555 | 5.2 | COD | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-03-02
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 4-002 | 5.2 | COD | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-12-26
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 5-315 | 5.2 | COD | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 6-266 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 7-552 | 5.2 | COD | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-03-02
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 8-290 | 5.2 | COD | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-30
- | AHEJ5L PSS-05 (39 Loc.) | Wind | WTG 9-199 | 5.2 | COD | 2025-11-18 | 2025-11-18 | 2025-11-19 | 2025-11-24
| >>> TOTAL: AHEJ5L PSS-05 (39 Loc.) | Wind | 40 blocks/WTGs | 208 | COD: 40 (208.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-01 | 12.5 | COD | 2026-03-12 | 2026-03-12 | 2026-03-03 | 2026-03-12
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-02 | 12.5 | COD | 2025-10-01 | 2025-10-01 | 2025-09-30 | 2025-09-30
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-03 | 12.5 | COD | 2025-10-01 | 2025-10-01 | 2025-09-30 | 2025-09-30
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-04 | 12.5 | COD | 2025-10-01 | 2025-10-01 | 2025-09-30 | 2025-09-30
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-05 | 12.5 | COD | 2025-10-01 | 2025-10-01 | 2025-09-30 | 2025-09-30
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-06 | 12.5 | COD | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-07 | 12.5 | COD | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-08 | 12.5 | COD | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-09 | 12.5 | COD | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-10 | 12.5 | COD | 2026-03-12 | 2026-03-12 | 2026-03-03 | 2026-03-12
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-11 | 12.5 | COD | 2026-03-12 | 2026-03-12 | 2026-03-03 | 2026-03-12
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | BLOCK-12 | 12.5 | COD | 2026-03-12 | 2026-03-12 | 2026-03-03 | 2026-03-12
- | AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | Unknown | 0 | COD | - | - | 2026-03-12 | 2026-03-12
| >>> TOTAL: AHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANTAHEJ5L_A15a_HSAT_150MW_MERCHANT | Solar | 13 blocks/WTGs | 150 | COD: 13 (150.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY26-P05 | AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: AHEJ5L_S04_HSAT_300 MW_MERCHANT_HYBRID | Solar | 25 blocks/WTGs | 300 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 300.0 MW
FY26-P02 | APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P02 | APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P02 | APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: APSEZ_A01- D_HSAT_25 MW_GROUP | Solar | 3 blocks/WTGs | 25 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 25.0 MW
- | ARE3L PSS-08 (05 Loc.) | Wind | Unknown | 5.2 | COD | - | - | 2025-08-30 | 2025-08-30
- | ARE3L PSS-08 (05 Loc.) | Wind | WTG 1 - 326 | 5.2 | COD | 2025-08-29 | 2025-08-30 | 2025-08-30 | 2025-08-31
- | ARE3L PSS-08 (05 Loc.) | Wind | WTG 2 - 327 | 5.2 | COD | 2025-08-29 | 2025-08-30 | 2025-08-30 | 2025-08-31
- | ARE3L PSS-08 (05 Loc.) | Wind | WTG 3 - 302 | 5.2 | COD | 2025-08-29 | 2025-08-29 | 2025-08-30 | 2025-08-31
- | ARE3L PSS-08 (05 Loc.) | Wind | WTG 4 - 351 | 5.2 | COD | 2025-08-29 | 2025-08-30 | 2025-08-30 | 2025-08-31
- | ARE3L PSS-08 (05 Loc.) | Wind | WTG 5 - 352 | 5.2 | COD | 2025-08-29 | 2025-08-30 | 2025-08-30 | 2025-08-31
| >>> TOTAL: ARE3L PSS-08 (05 Loc.) | Wind | 6 blocks/WTGs | 31.2 | COD: 6 (31.2 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY25-P01 | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-07-31 | 2025-07-31 | 2025-08-01 | 2025-08-01
FY25-P01 | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-07-31 | 2025-07-31 | 2025-08-01 | 2025-08-01
FY25-P01 | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | Unknown | 0 | COD | - | - | 2025-08-01 | 2025-08-01
| >>> TOTAL: ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | Solar | 3 blocks/WTGs | 25 | COD: 3 (25.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26- P07 | ARE41L_A15b_HSAT_50MW | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE41L_A15b_HSAT_50MW | Solar | 5 blocks/WTGs | 50 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-03 | 12.5 | COD | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-04 | 12.5 | COD | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-05 | 12.5 | COD | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-06 | 12.5 | COD | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-07 | 12.5 | COD | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | BLOCK-08 | 12.5 | COD | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30
FY25-P03 | ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | Unknown | 0 | COD | - | - | 2025-09-30 | 2025-09-30
| >>> TOTAL: ARE48L_S08_HSAT_100MW_MERCHANT_Commissioned | Solar | 9 blocks/WTGs | 100 | COD: 9 (100.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P09 | ARE55L_A01_HSAT_150MW_Group_NEW | Solar | BLOCK-16 | 62.5 | Pending | - | - | - | -
| >>> TOTAL: ARE55L_A01_HSAT_150MW_Group_NEW | Solar | 8 blocks/WTGs | 150 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 150.0 MW
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY26-P10 | ARE55L_A02_HSAT_125MW | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE55L_A02_HSAT_125MW | Solar | 11 blocks/WTGs | 125 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 125.0 MW
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-25 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-26 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-27 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-28 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-29 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-30 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-31 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-32 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-33 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-34 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-35 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-36 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-37 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-38 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-39 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY27-P01&P02 | ARE55L_S03_HSAT_500MW_MERCHANT | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE55L_S03_HSAT_500MW_MERCHANT | Solar | 41 blocks/WTGs | 500 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 500.0 MW
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P26 | ARE55L_S10_HSAT_50 MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE55L_S10_HSAT_50 MW_PPA | Solar | 5 blocks/WTGs | 50 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 50.0 MW
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-35 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-36 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-37 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-38 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-39 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-41 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-42 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-43 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-44 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-45 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-46 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-47 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-48 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-49 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-50 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-51 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-52 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-53 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-54 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-55 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | BLOCK-56 | 12.5 | Pending | - | - | - | -
FY26-P04 | ARE57L_A12_HSAT_350MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE57L_A12_HSAT_350MW_PPA | Solar | 29 blocks/WTGs | 350 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 350.0 MW
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
- | ARE8L_A02_HSAT_150MW_PPA TPL | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ARE8L_A02_HSAT_150MW_PPA TPL | Solar | 13 blocks/WTGs | 150 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 150.0 MW
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-01 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-02 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-03 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-04 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-05 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-06 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-07 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-08 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-11 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-12 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-13 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-14 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-15 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-25 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-26 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-27 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-28 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-29 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-30 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-31 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-32 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-33 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-34 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-35 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-36 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-37 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-38 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-39 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-40 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-41 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-42 | 12.5 | COD | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-43 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-44 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-45 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-46 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-47 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-48 | 12.5 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-49 | 0 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-50 | 0 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | BLOCK-51 | 0 | Pending | - | - | - | -
FY25-BAIYA_600MW | ASEB1PL_BAIYA_FT_600MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ASEB1PL_BAIYA_FT_600MW_PPA | Solar | 52 blocks/WTGs | 600 | COD: 21 (262.5 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 337.5 MW
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | Unknown | 5.2 | COD | - | - | 2026-03-28 | 2026-03-28
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 1 - 121 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 10 - 164 | 5.2 | COD | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 11 - 141 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 12 - 400 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 2 - 123 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 3 - 143 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 4 - 145 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 5 - 144 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 6 - 230 | 5.2 | COD | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 7 - 208 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 8 - 186 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
- | ASEJ6PL PSS-08 (12 Loc.) | Wind | WTG 9 - 376 | 5.2 | COD | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-18
| >>> TOTAL: ASEJ6PL PSS-08 (12 Loc.) | Wind | 13 blocks/WTGs | 67.6 | COD: 13 (67.6 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY25-P02 | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | BLOCK-01 | 12.5 | COD | 2025-07-30 | 2025-07-31 | 2025-07-31 | 2025-07-31
FY25-P02 | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | BLOCK-02 | 12.5 | COD | 2025-07-30 | 2025-07-31 | 2025-07-31 | 2025-07-31
FY25-P02 | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | BLOCK-03 | 10 | COD | 2025-07-30 | 2025-07-31 | 2025-07-31 | 2025-08-01
FY25-P02 | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | Unknown | 0 | COD | - | - | 2025-08-01 | 2025-08-01
| >>> TOTAL: ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | Solar | 4 blocks/WTGs | 35 | COD: 4 (35.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 0.0 MW
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY26-P14 | ASEJ6PL_S07_FT_300MW | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ASEJ6PL_S07_FT_300MW | Solar | 25 blocks/WTGs | 300 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 300.0 MW
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-01 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-02 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-03 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-04 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-05 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-06 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-07 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-08 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-09 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-10 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-11 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-12 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-13 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-14 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-15 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-16 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-17 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-18 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-19 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-20 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-21 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-22 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-23 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | BLOCK-24 | 12.5 | Pending | - | - | - | -
FY27-P13 | ASEJ6PL_S07_FT_300MW_PPA | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: ASEJ6PL_S07_FT_300MW_PPA | Solar | 25 blocks/WTGs | 300 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 300.0 MW
- | MANDVI | Wind | Unknown | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 1 - MP710 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 10 - MP549 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 11 - MP508 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 12 - MP160 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 13 - MP483 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 14 - MP741 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 15 - MP747 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 16 - MP155 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 17 - MP764 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 18 - MP611 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 19 - MP-P1 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 2 - MP471 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 20 - MNP29 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 21 - MP738 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 22 - MP611 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 23 - MP482 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 24 - MP733 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 25 - MP734 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 26 - MP561 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 27 - MP580 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 28 - MP612 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 29 - MP520 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 3 - MP586 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 30 - MP742 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 31 - MP509 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 32 - MP716 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 33 - MP159 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 34 - MP739 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 35 - MP740 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 36 - MP722 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 37 - MP778 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 38 - MP527 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 39 - MP770 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 4 - MP560 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 40 - MP763 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 41 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 42 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 43 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 44 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 45 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 46 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 47 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 48 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 49 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 5 - MP707 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 50 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 51 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 52 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 53 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 54 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 55 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 56 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 57 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 58 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 59 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 6 - MP705 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 60 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 61 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 62 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 63 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 64 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 65 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 66 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 67 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 68 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 69 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 7 - MP532 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 70 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 71 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 72 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 73 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 74 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 8 - MP588 | 3.3 | Pending | - | - | - | -
- | MANDVI | Wind | WTG 9 - MP496 | 3.3 | Pending | - | - | - | -
| >>> TOTAL: MANDVI | Wind | 75 blocks/WTGs | 247.5 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 247.5 MW
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 32 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 33 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 34 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 35 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 36 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 37 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 38 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 39 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 40 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 41 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 42 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 43 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 44 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 45 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 46 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | BLOCK - 48 | 12.5 | Pending | - | - | - | -
FY26-P16 | NHPC EPC 200 MW Khavda-Internal | Solar | Unknown | 0 | Pending | - | - | - | -
| >>> TOTAL: NHPC EPC 200 MW Khavda-Internal | Solar | 17 blocks/WTGs | 200 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 200.0 MW
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 01 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 02 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 03 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 04 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 05 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 06 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 07 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 08 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 09 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 10 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 11 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 12 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 13 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 14 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 15 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 16 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 17 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 18 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 19 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 20 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 21 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 22 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 23 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 24 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 25 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 26 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 27 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 28 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 29 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 30 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 31 | 12.5 | Pending | - | - | - | -
FY27-P16 | NHPC EPC 400 MW Khavda-Internal | Solar | BLOCK - 47 | 12.5 | Pending | - | - | - | -
| >>> TOTAL: NHPC EPC 400 MW Khavda-Internal | Solar | 32 blocks/WTGs | 400 | COD: 0 (0.0 MW) ¦ TR: 0 (0.0 MW) ¦ Remaining: 400.0 MW