## Sheet1
Uploaded: 19 Sep 2026, 11:46 AM ¦ Last Edited: 19 Sept 2026, 01:21 pm
Sr.no. | Name of Work | Voltage | Package Awarded by PGCIL | Scope |  | Actual Progress | Balance | SCD | ECOD | Remark | HVDC Lines | LILO Lines | LILO Line Substation | Sr.no. | Transmission Line | Others | Phase I | Phase II | Phase III | Phase IV | Phase V | Status | Length |  | Khavda Project Wise Connectivity With Phases | [6 empty] | Khavda Park - Project Allocation (02 May 2026) | [24 empty] | Sr.no | Substation | Latitude / Northing | Longitude / Easting
1 | Bhuj-I → Kps-I | 765kV | AESL | Foundation (nos.) | 0 | 0 | 0 |  | Charged |  |  |  |  | 1 | Bhuj-I → Kps-I |  | Yes |  |  |  |  | Charged | 109 | Sr.no. | KPS | Connectivity MW | Connectivity Breakup | Connectivity Phase | Project | Block | PSS | Sr.no. | KPS | Park | Voltage | Connectivity MW | Connectivity Breakup | Solar | Wind | Connectivity Phase | Likey start date of connectivity | Project | P6 project Name | SPV | Category | Block | Plot | PSS | Module | MMS | SCOD | ECOD | Financing | EPC Partner |  | Phase | 1 | Padghe (GIS) | 19°24′31.91″N | 73°12′40.40″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [6 empty] | 2 | LILO Pirana (PG) → Pirana (T) |  |  | Yes |  |  |  | Charged | 200 | 1 | KPS-I | 1000 | 50 | Phase - I | MLP T1 PPA - J&K | A16 | PSS-06 |  | AGEL PARK | [23 empty] | 2 | Padghe (PG) | 19°24′31.91″N | 73°12′40.40″E
|  |  |  | Stringing (kms) | 109.0 | 109.0 | 0.0 | [6 empty] | 3 | Kps-III → Kps-II |  |  | Yes |  |  |  | Charged | 15 | 2 | KPS-I |  | 200 | Phase - I | MLP T1 PPA - CG | A16 | PSS-06 | 1 | KPS-1 | AGEL | 400kV | 1000 | 50 | 50 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - J&K | AGE26AL_A16_FT_50MW_PPA_Commissioned | AGE26AL | PPA | A16 | A16a | PSS-06 | SEA | FT | 2026-01-21 | 2026-01-31 | PFC -3 |  | Q4 2026 | Phase I | 3 | Pirana (PG) | 22°55′39.36″N | 72°33′24.61″E
2 | LILO Pirana (PG) → Pirana (T) | 400kV | Torrent Gujrat RTM | Foundation (nos.) | 174 | 174 | 0 | - | Feb-26 | Charged |  | Yes | Ahmedabad | 4 | Ahmedabad → Navsari (NEW) |  |  | Yes |  |  |  | Charged | 294 | 3 | KPS-I |  |  | Phase - I | MLP T1 PPA - CG | A16 | PSS-06 | 2 | KPS-1 | AGEL |  |  | 200 | 50 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL_A16_FT_200MW_PPA | AGE26AL | PPA | A16 | A16b | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase I | 4 | Pirana (T) | 22°58′00.84″N | 72°35′51.00″E
|  |  |  | Erection (nos.) | 174 | 160 | 14 | [6 empty] | 5 | Banaskantha → Ahmedabad |  |  | Yes |  |  |  | Charged | 132 | 4 | KPS-I |  |  | Phase - I | MLP T1 PPA - CG | A16 | PSS-06 | 3 | KPS-1 | AGEL |  |  |  | 100 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL_A16_FT_200MW_PPA | AGE26AL | PPA | A16 | A16b | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase I | 5 | Pirana PGCIL | 22°55′42.81″N | 72°33′24.77″E
|  |  |  | Stringing (kms) | 200 | 54.7 | 145.3 | [6 empty] | 6 | Lakadia → Ahmedabad |  |  | Yes | Yes |  |  | Charged | 183 | 5 | KPS-I |  | 167 | Phase - I | MLP T1 PPA - TN | A16 | PSS-06 | 4 | KPS-1 | AGEL |  |  |  | 50 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL_A16_FT_200MW_PPA | AGE26AL | PPA | A16 | A16b | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027 | Phase I | 6 | South Olpad (GIS) | 21°56′45.61″N | 73°05′08.35″E
3 | Boisar-II (GIS) → South Olpad (GIS) | 765kV | STERLITE GUJARAT TBCB | Foundation (nos.) | 656 | 612 | 44 | Oct-26 | Mar-27 |  |  |  |  | 7 | Kps-I → Kps-II |  |  | Yes |  |  |  | Charged | 20.51 | 6 | KPS-I |  |  | Phase - I | MLP T1 PPA - TN | A16 | PSS-06 | 5 | KPS-1 | AGEL | 400kV |  | 167 | 100 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - TN | AGE26AL_A16C_FT_167MW_PPA | AGE26AL | PPA | A16 | A16c | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase I | 7 | Lakadia | 23°23′38.38″N | 70°35′51.81″E
|  |  |  | Erection (nos.) | 656 | 529 | 127 | [6 empty] | 8 | Kps-II → Lakadia |  |  | Yes |  |  |  | Charged | 177 | 7 | KPS-I |  | 333 | Phase - I | MLP T1 PPA - OR | A16 | PSS-06 | 6 | KPS-1 | AGEL |  |  |  | 12.5 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - TN | AGE26AL_A16C_FT_167MW_PPA | AGE26AL | PPA | A16 | A16c | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027 | Phase I | 8 | Halvad | 22°54′39.88″N | 71°13′50.13″E
|  |  |  | Stringing (kms) | 232 | 97 | 135 | [6 empty] | 9 | Vataman → Navsari (NEW) |  |  |  | Yes |  |  | 8 | 250 | 8 | KPS-I |  |  | Phase - I | MLP T1 PPA - OR | A16 | PSS-06 | 7 | KPS-1 | AGEL |  |  |  | 54.5 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - TN | AGE26AL_A16C_FT_167MW_PPA | AGE26AL | PPA | A16 | A16c | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027 | Phase I | 9 | Boisar-II (Sec-II) | 19°47′40.26″N | 72°47′06.02″E
4 | Ahmedabad → South Olpad (GIS) | 765kV | PGCIL (TLL / KEC) | Foundation (nos.) | 597 | 355 | 242 | Oct-26 | Oct-27 |  |  |  |  | 10 | Lakadia → Vadodara |  |  |  | Yes |  |  | Charged | 28 | 9 | KPS-I |  |  | Phase - I | MLP T1 PPA - OR | A16 | PSS-06 | 8 | KPS-1 | AGEL |  |  | 333 | 100 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - OR | AGE26AL_A16_FT_333MW_PPA | AGE26AL | PPA | A16 | A16d | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase I | 10 | Boisar-II - Pune-III | 24°12′26.58″N | 69°29′41.53″E
|  |  |  | Erection (nos.) | 597 | 249 | 348 | [6 empty] | 11 | Halvad → Vataman |  |  |  | Yes |  |  | 10 | 127.2 | 10 | KPS-I |  | 0 | Phase - I | Input Solar - BESS | SE8 | PSS-06 | 9 | KPS-1 | AGEL |  |  |  | 58 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - OR | AGE26AL_A16_FT_333MW_PPA | AGE26AL | PPA | A16 | A16d | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase I | 11 | KHAVDA-I PS | 24°06′01.00″N | 69°20′13.26″E
|  |  |  | Stringing (kms) | 250 | 6 | 244 | [6 empty] | 12 | Kps-II → Halvad |  |  |  | Yes |  |  | In Progress | 259.77 | 11 | KPS-I |  | 250 | Phase - I | MLP T4 PPA - AP | A3 | PSS-06 | 10 | KPS-1 | AGEL |  |  |  | 175 | 0 | Phase I | 2024-02-18 | MLP T1 PPA - OR | AGE26AL_A16_FT_333MW_PPA | AGE26AL | PPA | A16 | A16d | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027 | Phase I | 12 | KHAVDA-II PS | 24°04′56.96″N | 69°31′01.32″E
5 | Ghandhar → Hazira | 400kV | PGCIL (KPIL) | Foundation (nos.) | 12 | 0 | 12 | Oct-26 | Oct-27 |  |  | Yes | South Olpad (GIS) | 13 | Navsari (NEW) → Padghe (PG) |  |  |  |  | Yes |  | Charged | 26 | 12 | [7 empty] | 11 | KPS-1 | AGEL |  |  | 250 | 50 | 0 | Phase I | 2024-02-18 | MLP T4 PPA - AP | AGE26BL_A03_HSAT_250 MW_MLP T4 AP NEW | AGE26BL | PPA | A3 | A03 | PSS-06 | China | HSAT | 2027-03-07 | 2026-12-31 | REC | Bondada | Q3 2027 | Phase I | 13 | KHAVDA-III PS | 24°04′01.79″N | 69°28′27.63″E
|  |  |  | Erection (nos.) | 12 | 0 | 12 | [6 empty] | 14 | Babhaleswar → Padghe (M) |  |  |  |  | Yes |  | 14 | 259.77 | 13 | KPS-I | 417 | 250 | Phase - II | MLP T4 PPA - AP | A3 | PSS-06 | 12 | KPS-1 | AGEL |  |  |  | 200 | 0 | Phase I | 2024-02-18 | MLP T4 PPA - AP | AGE26BL_A03_HSAT_250 MW_MLP T4 AP NEW | AGE26BL | PPA | A3 | A03 | PSS-06 | China | HSAT | 2027-03-07 | 2027-02-28 | REC | Bondada | Q4 2027 |  | 14 | BHUJ-I | 23°27′09.26″N | 69°35′32.07″E
|  |  |  | Stringing (kms) | 5 | 0 | 5 | [6 empty] | 15 | Boisar-II (GIS) → Velgaon (MH) |  |  |  |  | Yes |  | 15 | 58 | 14 | KPS-I |  | 100 | Phase - II | MLP T4 PPA - AP | A4 | PSS-02 | [25 empty] | 15 | Pune (GIS) | 18°47′39.78″N | 73°41′53.34″E
6 | Vadodara → South Olpad (GIS) | 765kV | PGCIL (KPIL) | Foundation (nos.) | 345 | 185 | 160 | Oct-26 | Oct-27 |  |  |  |  | 16 | Bhuj-I → Kps-I |  |  |  |  | Yes |  | 18 | 107 | 15 | KPS-I |  | 67 | Phase - II | MLP T4 PPA - AP | A4/A7 | PSS-02 | 13 | KPS-1 | AGEL |  | 417 | 250 | 250 | 0 | Phase II | 2026-10-31 | MLP T4 PPA - AP | AGE24L_A03_HSAT_250 MW | AGE24L | PPA | A3 | A03 | PSS-06 | China | HSAT | 2027-03-07 | 2026-12-31 | BOB/ NABARD | Hild | Q3 2027 | Phase II | 16 | Banaskantha | 24°08′15.53″N | 71°59′56.04″E
|  |  |  | Erection (nos.) | 345 | 77 | 268 | [6 empty] | 17 | Kps-III → Lakadia |  |  |  |  | Yes |  | 19 | 189 | 16 | [7 empty] | 14 | KPS-1 | AGEL |  |  | 100 | 100 | 0 | Phase II | 2026-10-31 | MLP T4 PPA - AP |  | AGE26BL | PPA | A4 |  | PSS-02 | China | HSAT | 2026-11-05 | 2024-03-31 | REC 1 (REC 2) |  | Q4 2024 | Phase II | 17 | Ramgarh | 27°28′17.25″N | 70°29′38.37″E
|  |  |  | Stringing (kms) | 140 | 0 | 140 | [6 empty] | 18 | Boisar-II (GIS) → Pune-III (GIS) |  |  |  |  | Yes |  | 20 | 227 | 17 | KPS-I | 1083 | 250 | Phase - III | MLP T3 PPA - AP | A7 | PSS-02 | 15 | KPS-1 | AGEL |  |  | 67 | 67 | 0 | Phase II | 2026-10-31 | MLP T4 PPA - AP |  | AGE26BL | PPA | A4/A7 |  | PSS-02 | China | HSAT | 2026-11-05 | 2025-02-24 | REC 1 (REC 2) |  | Q4 2025 | Phase II | 18 | Bhadla-3 | 27°40′20.32″N | 72°12′23.59″E
7 | Kps-II (HVDC) → Nagpur (HVDC) | 800kV | PGCIL (JSL / KEC / L&T / KPIL / TLL) | Foundation (nos.) | 3150 | 838 | 2312 | May-29 | May-29 |  | Yes |  |  | 19 | Narendra (NEW) → Pune (GIS) |  |  |  |  | Yes |  | 21 | 85.6 | 18 | KPS-I |  |  | Phase - III | MLP T3 PPA - AP | A7 | PSS-02 | [9 empty] | ` | [15 empty] | 19 | Fatehgarh-III | 26°21′00.24″N | 71°06′00.39″E
|  |  |  | Erection (nos.) | 3150 | 141 | 3009 | [6 empty] | 20 | Hinjewadi → Koyna |  |  |  |  | Yes |  | Charged | 10 | 19 | KPS-I |  | 250 | Phase - III | MLP T3 PPA - AP | A7 | PSS-02 | 16 | KPS-1 | AGEL |  | 1083 | 250 | 225 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | AGE25AL | PPA | A7 |  | PSS-02 | China | HSAT | 2025-11-05 | 2024-03-31 | EM 3 |  | Q4 2024 |  | 20 | Sikar-II | 27°41′43.21″N | 75°05′17.68″E
|  |  |  | Stringing (kms) | 1200 | 0 | 1200 | [6 empty] | 21 | Boisar-II (GIS) → South Olpad (GIS) |  |  |  |  | Yes |  | 3 | 232 | 20 | KPS-I |  | 250 | Phase - III | MLP T3 PPA - AP | A4 | PSS-02 | 17 | KPS-1 | AGEL |  |  |  | 25 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | AGE25AL | PPA | A7 |  | PSS-02 | China | HSAT | 2025-11-05 | 2025-02-28 | EM 3 |  | Q4 2025 | Phase III | 21 | Khetri 765 kV | 28°01′58.53″N | 75°42′33.48″E
8 | Vataman → Navsari (NEW) | 765kV | PGCIL (KPIL / KEC) | Foundation (nos.) | 689 | 676 | 13 | Dec-25 | Dec-26 |  |  |  |  | 22 | Ahmedabad → South Olpad (GIS) |  |  |  |  | Yes |  | 4 | 250 | 21 | KPS-I |  | 250 | Phase - III | MLP T3 PPA - AP | A4 | PSS-02 | 18 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | AGE25AL | PPA | A7 |  | PSS-02 | China | HSAT | 2025-11-05 | 2025-02-28 | EM 3 |  | Q4 2025 | Phase III | 22 | Narela 765 kV | 28°49′24.29″N | 76°59′01.67″E
|  |  |  | Erection (nos.) | 689 | 576 | 113 | [6 empty] | 23 | Ghandhar → Hazira |  |  |  |  | Yes |  | 5 | 5 | 22 | KPS-I |  | 83 | Phase - III | MLP PPA - AP New | A7 | PSS-02 | 19 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | AGE25BL | PPA | A4 |  | PSS-02 | China | HSAT | 2025-11-05 | 2023-12-31 | PFC 1 |  | Q3 2024 | Phase III | 23 | Jhatikara | 28°31′56.02″N | 76°56′10.47″E
|  |  |  | Stringing (kms) | 246 | 55 | 191 | [6 empty] | 24 | Vadodara → South Olpad (GIS) |  |  |  |  | Yes |  | 6 | 140 | 23 | [7 empty] | 20 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | AGE25BL | PPA | A4 |  | PSS-02 | China | HSAT | 2025-11-05 | 2023-12-31 | PFC 1 |  | Q3 2024 | Phase III | 24 | Bikaner-III | 28°22′22.54″N | 73°10′14.72″E
9 | Kps-III → Kps-II | 765kV | PGCIL (TLL) | Foundation (nos.) | 40 | 40 | 0 | Jun-25 | Jun-25 |  |  |  |  | 25 | Nagpur (HVDC) → Nagpur | [5 empty] | Yes | In Progress | 1 | 24 | KPS-I | 1000 | 250 | Phase - III | MLP T2 PPA - AP | A5 | PSS-01 | 21 | KPS-1 | AGEL |  |  | 83 | 83 | 0 | Phase III | 2027-01-31 | MLP PPA - AP New |  | AGE25BL | PPA | A7 |  | PSS-02 | China | HSAT | 2026-10-01 | 2025-03-01 | PFC 1 |  | Q4 2025 | Phase III | 25 | Mandsaur | 24°12′23.90″N | 75°10′15.02″E
|  |  |  | Erection (nos.) | 40 | 40 | 0 | [6 empty] | 26 | Kps-III (HVDC) → Kps-III | [5 empty] | Yes | In Progress | 1 | 25 | KPS-I |  | 250 | Phase - III | MLP T2 PPA - AP | A5 | PSS-01 | [25 empty] | 26 | Indore | 22°54′31.81″N | 75°53′58.87″E
|  |  |  | Stringing (kms) | 15.0 | 15.0 | 0.0 | [6 empty] | 27 | South Olpad → South Olpad (GIS) | [5 empty] | Yes | In Progress | 100 | 26 | KPS-I |  | 250 | Phase - III | MLP T2 PPA - AP | A8 | PSS-01 | 22 | KPS-1 | AGEL | 400kV | 1000 | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T2 PPA - AP |  | AGE24AL | PPA | A5 |  | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | REC 1 |  | Q3 2024 | Phase III | 27 | Jam Khambhaliya (GIS) PS | 22°08′40.92″N | 69°40′37.92″E
10 | Halvad → Vataman | 765kV | PGCIL (BAJAJ / KPIL) | Foundation (nos.) | 336 | 330 | 6 | Dec-25 | Nov-26 |  |  |  |  | 28 | Kps-III (HVDC) → South Olpad | [5 empty] | Yes | 11 | 600 | 27 | KPS-I |  | 250 | Phase - III | MLP T2 PPA - AP | A8 | PSS-01 | 23 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T2 PPA - AP |  | AGE24AL | PPA | A5 |  | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | REC 1 |  | Q3 2024 |  | 28 | Bhuj PS | 23°27′20.88″N | 69°33′44.64″E
|  |  |  | Erection (nos.) | 336 | 241 | 95 | [6 empty] | 29 | Wardha → Raipur | [5 empty] | Yes | Charged | 34 | 28 | [7 empty] | 24 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T2 PPA - AP |  | AGE24BL | PPA | A8 |  | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | EM 3 |  | Q3 2024 | Phase III | 29 | Bhuj-II PS | 23°22′19.56″N | 69°08′38.76″E
|  |  |  | Stringing (kms) | 127.2 | 11 | 116.2 | [6 empty] | 30 | Kps-II (HVDC) → Nagpur (HVDC) | [5 empty] | Yes | 7 | 1200 | 29 | KPS-I | 1000 | 600 | Phase - II | SECI H-3 PPA | A13 | PSS-05 | 25 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase III | 2027-01-31 | MLP T2 PPA - AP |  | AGE24BL | PPA | A8 |  | PSS-01 | China | HSAT | 2024-11-05 | 2024-01-31 | EM 3 |  | Q4 2024 | Phase III | 30 | Bhachau | 23°12′21.96″N | 70°11′14.28″E
11 | Kps-III (HVDC) → South Olpad | 500kV | AESL | Foundation (nos.) | 0 | 0 | 0 | Dec-29 | Dec-29 |  | Yes |  |  | 31 | Kps-II (HVDC) → Kps-II | [5 empty] | Yes | In Progress | 100 | 30 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13 | PSS-05 | [25 empty] | 31 | Khavda PS-I | 24°06′01.00″N | 69°20′13.26″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [6 empty] | 32 | Lakadia → Vadodara | Yes | [5 empty] | Charged |  | 31 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13 | PSS-05 | 26 | KPS-1 | AGEL | 400kV | 1000 | 600 | 295 | 0 | Phase II | 2026-03-08 | SECI H-3 PPA |  | AHEJ5L | PPA | A13 |  | PSS-05 | China | FT | LTA | 2025-06-30 | SBI |  | Q1 2026 | Phase III | 32 | Khavda PS-II | 24°04′56.96″N | 69°31′01.32″E
|  |  |  | Stringing (kms) | 600 | 0 | 600 | [6 empty] | 33 | Wardha → Raipur | Yes | [5 empty] | Charged |  | 32 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13 | PSS-05 | 27 | KPS-1 | AGEL |  |  |  | 50 | - | Phase II | 2026-03-08 | SECI H-3 PPA |  | AHEJ5L | PPA | A13 |  | PSS-05 | China | FT | LTA | 2025-08-31 | SBI |  | Q2 2026 | Phase III | 33 | Khavda PS-III | 24°04′01.79″N | 69°28′27.63″E
12 | Ahmedabad → Navsari (NEW) | 765kV | PGCIL (KEC / KPIL) | Foundation (nos.) | 809 | 809 | 0 | Jan-26 | Jan-26 |  |  |  |  | 34 | Hinjewadi → Koyna | Yes | [5 empty] | Charged |  | 33 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13 | PSS-05 | 28 | KPS-1 | AGEL |  |  |  | 75 | 0 | Phase II | 2026-03-08 | SECI H-3 PPA |  | AHEJ5L | PPA | A13 |  | PSS-05 | China | FT | LTA | 2025-09-01 | SBI |  | Q2 2026 |  | 34 | Banaskantha (Radhanesda) PS [GIS] | 24°20′34.80″N | 71°29′14.28″E
|  |  |  | Erection (nos.) | 809 | 809 | 0 | [6 empty] | Sr.no. | Substation | Others | Phase I | Phase II | Phase III | Phase IV | Phase V | Status | Expected Date | 34 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13, A14, A17 | PSS-05 | 29 | KPS-1 | AGEL |  |  |  | 75 | 0 | Phase II | 2026-03-08 | SECI H-3 PPA |  | AHEJ5L | PPA | A13 |  | PSS-05 | China | FT | LTA | 2025-10-16 | SBI |  | Q3 2026 | Phase II | 35 | Raghanesda | 24°27′03.60″N | 71°24′34.56″E
|  |  |  | Stringing (kms) | 294.0 | 294.0 | 0.0 | [6 empty] | 1 | Bhuj-I |  | Yes | Yes |  | Yes |  | Charged(Jun-25) | Jun-26 | 35 | KPS-I |  |  | Phase - II | SECI H-3 PPA | A13, A14, A17 | PSS-05 | 30 | KPS-1 | AGEL |  |  |  | 75 | 0 | Phase II | 2026-03-08 | SECI H-3 PPA |  | AHEJ5L | PPA | A13 |  | PSS-05 | China | FT | LTA | 2025-11-30 | SBI |  | Q3 2026 | Phase II | 36 | Rajgarh (PG) | 22°40′55.92″N | 74°55′27.84″E
13 | Banaskantha → Ahmedabad | 765kV | PGCIL (TLL / L&T) | Foundation (nos.) | 362 | 362 | 0 | Jun-25 | Jun-25 |  |  |  |  | 2 | Kps-I |  | Yes | Yes |  | Yes |  | Charged(Jun-25) | Mar-26 | 36 | KPS-I |  | 250 | Phase - II | AGEL Merchant - TTE IM2 (Solar) | A14 | PSS-05 | 31 | KPS-1 | AGEL |  |  |  | 0 | 182 | Phase II | 2026-03-08 | SECI H-3 PPA | AHEJ5L PSS-05 (39 Loc.) | AHEJ5L | PPA | A13, A14, A17 |  | PSS-05 | - | - | LTA | 2025-11-30 | SBI |  | Q3 2026 | Phase II | 37 | Indore (PG) | 22°54′31.81″N | 75°53′58.87″E
|  |  |  | Erection (nos.) | 362 | 362 | 0 | [6 empty] | 3 | Lilo Pirana (PG) | [6 empty] | Charged(Mar-25) | Feb-26 | 37 | KPS-I |  |  | Phase - II | AGEL Merchant - TTE IM2 (Solar) | A14 | PSS-05 | 32 | KPS-1 | AGEL |  |  |  | 0 | 20.8 | Phase II | 2026-03-08 | SECI H-3 PPA | AHEJ5L PSS-05 (39 Loc.) | AHEJ5L | PPA | A13, A14, A17 |  | PSS-05 | - | - | LTA | 2026-03-31 | SBI |  | Q4 2026 | Phase II | 38 | Pachora PS | 23°43′03.72″N | 76°07′23.88″E
|  |  |  | Stringing (kms) | 132.0 | 132.0 | 0.0 | [6 empty] | 4 | Pirana (T) | [6 empty] | Charged (Apr-25 & Nov-25) | Mar-25 | 38 | KPS-I |  | 150 | Phase - II | AGEL Merchant (Solar) | A14 | PSS-05 | 33 | KPS-1 | AGEL |  |  | 250 | 175 | 0 | Phase II | 2026-03-08 | AGEL Merchant - TTE IM2 (Solar) |  | ARE45L | Merchant | A14 |  | PSS-05 | ALMM | HSAT | - | 2025-06-30 | SM 2 |  | Q1 2026 | Phase II | 39 | Neemuch PS | 25°01′30.72″N | 75°13′38.64″E
14 | Babhaleswar → Padghe (M) | 400kV | STERLITE GUJARAT TBCB | Foundation (nos.) | 174 | 138 | 36 | Oct-26 | Mar-27 |  |  | Yes | Boisar-II (GIS) | 5 | Ahmedabad |  |  |  |  | Yes |  | Charged(Jul-25) | Oct-26 | 39 | KPS-I |  |  | Phase - II | AGEL Merchant (Solar) | A14 | PSS-05 | 34 | KPS-1 | AGEL |  |  |  | 75 | 0 | Phase II | 2026-03-08 | AGEL Merchant - TTE IM2 (Solar) |  | ARE45L | Merchant | A14 |  | PSS-05 | ALMM | HSAT | - | 2025-08-31 | SM 2 |  | Q2 2026 | Phase II | 40 | Khandwa S/s (PG) | 21°49′56.64″N | 76°24′14.40″E
|  |  |  | Erection (nos.) | 174 | 101 | 73 | [6 empty] | 6 | Kps-III |  |  | Yes |  | Yes | Yes | Charged | Dec-29 | 40 | [7 empty] | 35 | KPS-1 | AGEL |  |  | 150 | 75 | - | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | AGE24L | Merchant | A14 |  | PSS-05 | ALMM | HSAT | - | 2026-02-12 | NABFID |  | Q4 2026 | Phase II | 41 | Raipur S/s (PG) | 21°14′00.00″N | 81°29′00.00″E
|  |  |  | Stringing (kms) | 58 | 6 | 52 | [6 empty] | 7 | Kps-II | [5 empty] | Yes | Charged | May-29 | 41 | KPS-I | 650 | 134 | Phase - V | MSEDCL PPA Ph-4 | A17 | PSS-05 | 36 | KPS-1 | AGEL |  |  |  | 75 | - | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AGE24L_A14_HSAT_150MW_MERCHANT_Commissioned | AGE24L | Merchant | A14 |  | PSS-05 | ALMM | HSAT | - | 2026-03-31 | NABFID |  | Q4 2026 | Phase II | 42 | Kallam PS | 18°37′21.00″N | 75°52′17.04″E
15 | Boisar-II (GIS) → Velgaon (MH) | 400kV | STERLITE GUJARAT TBCB | Foundation (nos.) | 74 | 31 | 43 | Oct-26 | Mar-27 |  |  |  |  | 8 | Navsari (NEW) |  |  |  | Yes |  |  | Charged | Jun-26 | 42 | KPS-I |  | 250 | Phase - V | MLP PPA - AP New | A17 | PSS-05 | [25 empty] | 43 | Parli (PG) | 18°44′29.04″N | 76°25′41.52″E
|  |  |  | Erection (nos.) | 74 | 9 | 65 | [6 empty] | 9 | Banaskantha | [5 empty] | Yes | Charged | Dec-29 | 43 | KPS-I |  | 67 | Phase - V | MLP PPA - AP New | A17 | PSS-05 | 37 | KPS-1 | AGEL |  | 650 | 134 | 134 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-4 |  | ARE55L | PPA | A17 |  | PSS-05 | ALMM | TBD | 2027-10-29 | 2029-03-31 | Unallocated |  | Q4 2029 | Phase II | 44 | Solapur (PG) | 17°36′31.32″N | 76°03′00.00″E
|  |  |  | Stringing (kms) | 25 | 0 | 25 | [6 empty] | 10 | Lakadia |  |  |  |  | Yes |  | Charged | Jun-26 | 44 | KPS-I |  | 100 | Phase - V | MLP PPA - AP New | A17 | PSS-05 | 38 | KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE55L TBD | PPA | A17 |  | PSS-05 | ALCM | TBD | LTA+15 Days | 2029-12-31 | Unallocated |  | Q3 2030 | Phase II | 45 | Solapur PS | 17°53′09.24″N | 76°12′49.32″E
16 | Lakadia → Ahmedabad | 765kV | PGCIL (TLL / KPIL) | Foundation (nos.) | 476 | 476 | 0 | Dec-25 | Aug-26 |  |  | Yes | Halvad | 11 | Halvad | [5 empty] | Yes | Charged | Dec-29 | 45 | KPS-I |  | 99 | Phase - V | MLP PPA - AP New | A17 | PSS-05 | 39 | KPS-1 | AGEL |  |  | 67 | 67 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE55L TBD | PPA | A17 |  | PSS-05 | ALCM | TBD | LTA+15 Days | 2029-12-31 | Unallocated |  | Q3 2030 | Phase II | 46 | Dhule PS | 20°58′46.56″N | 74°09′02.88″E
|  |  |  | Erection (nos.) | 476 | 476 | 0 | [6 empty] | 12 | Vataman | [6 empty] | Charged | Dec-26 | 46 | [7 empty] | 40 | KPS-1 | AGEL |  |  | 100 | 100 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE55L TBD | PPA | A17 |  | PSS-05 | ALCM | TBD | LTA+15 Days | 2029-12-31 | Unallocated |  | Q3 2030 |  | 47 | Mandsaur PS | 24°12′23.90″N | 75°10′15.02″E
|  |  |  | Stringing (kms) | 183.3 | 183.3 | 0 | [6 empty] | 13 | Vadodara | [5 empty] | Yes | Charged | Dec-29 | 47 | KPS-I | 1000 | 225 | Phase - II | AGEL Merchant (Solar) | A2 | PSS-04 | 41 | KPS-1 | AGEL |  |  | 99 | 99 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE55L TBD | PPA | A17 |  | PSS-05 | ALCM | TBD | LTA+15 Days | 2029-12-31 | Unallocated |  | Q3 2030 | Phase V | 48 | Ishanagar | 24°51′45.72″N | 79°22′06.24″E
17 | Kps-I → Kps-II | 765kV | AESL (TPL) | Foundation (nos.) | 0 | 0 | 0 |  | Charged |  |  |  |  | 14 | Padghe (PG) |  |  |  |  | Yes |  | Charged | Aug-26 | 48 | KPS-I |  |  | Phase - II | AGEL Merchant (Solar) | A2 | PSS-04 | [25 empty] | 49 | Morena PS | 25°54′47.88″N | 77°29′56.40″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [6 empty] | 15 | Boisar-II (GIS) |  |  | Yes |  | Yes |  | Charged | Oct-26 | 49 | KPS-I |  | 50 | Phase - II | AESL PPA (C&I) - Wind - RSWM | A16, NHPC, A1,A3 | PSS-04 | 42 | KPS-1 | AGEL | 400kV | 1000 | 225 | 175 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) |  | ARE56L | Merchant | A2 |  | PSS-04 | ALMM | HSAT | - | 2025-03-29 | REC 3 |  | Q4 2025 | Phase V | 50 | Tuticorin-II | 9°03′02.16″N | 77°55′31.44″E
|  |  |  | Stringing (kms) | 20.5 | 20.5 | 0.0 | [6 empty] | 16 | Babhaleswar | [6 empty] | Charged | Mar-27 | 50 | KPS-I |  |  | Phase - II | AESL PPA (C&I) - Solar | A1 | PSS-04 | 43 | KPS-1 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) |  | ARE56L | Merchant | A2 |  | PSS-04 | ALMM | HSAT | - | 2025-05-14 | REC 3 |  | Q1 2026 | Phase V | 51 | Pugalur | 10°57′42.12″N | 77°55′22.08″E
18 | Bhuj-I → Kps-I | 765kV | AESL (Tata) | Foundation (nos.) | 285 | 285 | 0 | Aug-26 | Oct-26 |  |  |  |  | 17 | Padghe (M) | [6 empty] | Charged | Mar-27 | 51 | KPS-I |  | 50 | Phase - II | Group - Port (Hybrid - Solar) | A2 | PSS-04 | 44 | KPS-1 | AGEL |  |  | 50 | 0 | 52 | Phase II | 2026-03-08 | AESL PPA (C&I) - Wind - RSWM |  | ARE41L | PPA | A16, NHPC, A1,A3 |  | PSS-04 | - | - | - | 2025-03-31 | PFC |  | Q4 2025 | Phase V | 52 | Palakkad | 10°46′22.08″N | 76°45′36.00″E
|  |  |  | Erection (nos.) | 285 | 280 | 5 | [6 empty] | 18 | Velgaon (MH) | [6 empty] | In Progress | Aug-26 | 52 | KPS-I |  |  | Phase - II | Group - Port (Hybrid - Wind) | A1, A2, A3, A4, A5, NHPC | PSS-04 | 45 | KPS-1 | AGEL |  |  |  | 25 | 0 | Phase II | 2026-03-08 | AESL PPA (C&I) - Solar | ARE41L_A01- C_HSAT_25 MW_MERCHANT | ARE41L | PPA | A1 | A01c | PSS-04 | ALMM | HSAT |  | 2026-06-30 | REC | Bondada | Q1 2027 | Phase V | 53 | Pavagada | 14°19′06.96″N | 77°23′07.80″E
|  |  |  | Stringing (kms) | 107 | 73.1 | 33.9 | [6 empty] | 19 | Pune-III (GIS) |  |  |  |  | Yes |  | Charged | Nov-26 | 53 | KPS-I |  | 250 | Phase - II | Group - Cement (Hybrid - Solar) | A1 | PSS-04 | 46 | KPS-1 | AGEL |  |  | 50 | 25 | 0 | Phase II | 2026-03-08 | Group - Port (Hybrid - Solar) | APSEZ_A01- D_HSAT_25 MW_GROUP | APSEZ | Group | A2 | A01d | PSS-04 | ALMM | HSAT |  | 2026-06-30 |  | Bondada | Q1 2027 |  | 54 | Hiriyur | 13°57′12.24″N | 76°32′11.40″E
19 | Kps-III → Lakadia | 765kV | AESL (Jyoti Structure) | Foundation (nos.) | 514 | 440 | 74 | Aug-26 | Feb-27 |  |  |  |  | 20 | Narendra (NEW) |  |  |  |  | Yes |  | Charged | Jun-26 | 54 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Solar) | A1 | PSS-04 | 47 | KPS-1 | AGEL |  |  |  | 0 | 52 | Phase II | 2026-03-08 | Group - Port (Hybrid - Wind) |  | APSEZ | Group | A1, A2, A3, A4, A5, NHPC |  | PSS-04 | - | - |  | 2025-03-31 |  |  | Q4 2025 | Phase II | 55 | Kurnool(new) | 15°40′28.56″N | 78°10′35.40″E
|  |  |  | Erection (nos.) | 514 | 282 | 232 | [6 empty] | 21 | Pune (GIS) |  |  |  |  | Yes |  | Charged | Oct-25 | 55 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Wind) | A1, A2, A3, A4, A5, NHPC | PSS-04 | 48 | KPS-1 | AGEL |  |  | 0 | 75 | 0 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Solar) |  | ACL | Group | A1 |  | PSS-04 | ALMM | FT | - | 2025-12-31 |  |  | Q3 2026 | Phase II | 56 | Koppal | 15°21′55.44″N | 75°59′24.72″E
|  |  |  | Stringing (kms) | 189 | 28 | 161 | [6 empty] | 22 | Hinjewadi | [6 empty] | Charged | Mar-28 | 56 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Wind) | A1, A2, A3, A4, A5, NHPC | PSS-04 | 49 | KPS-1 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Solar) |  | ACL | Group | A1 |  | PSS-04 | ALMM | FT | - | 2025-09-09 |  |  | Q2 2026 | Phase II | 57 | Karur | 10°50′34.08″N | 77°39′32.76″E
20 | Boisar-II (GIS) → Pune-III (GIS) | 765kV | AESL (TLL/Jyoti Structure) | Foundation (nos.) | 629 | 102 | 527 | Nov-26 | Mar-28 |  |  |  |  | 23 | Koyna | [6 empty] | Charged | Mar-28 | 57 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Wind) | A1, A2, A3, A4, A5, NHPC | PSS-04 | 50 | KPS-1 | AGEL |  |  |  | 0 | 98.8 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Wind) |  | ACL | Group | A1, A2, A3, A4, A5, NHPC |  | PSS-04 | - | - |  | 2025-03-31 |  |  | Q4 2025 | Phase II | 58 | Gadag | 15°47′05.64″N | 75°51′28.08″E
|  |  |  | Erection (nos.) | 629 | 15 | 614 | [6 empty] | 24 | South Olpad (GIS) |  |  |  |  | Yes |  | In Progress | Mar-27 | 58 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Solar) | A1 | PSS-04 | 51 | KPS-1 | AGEL |  |  |  | 0 | 26 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Wind) |  | ACL | Group | A1, A2, A3, A4, A5, NHPC |  | PSS-04 | - | - |  | 2025-05-13 |  |  | Q1 2026 | Phase II | 59 | Koppal-II PS | 15°34′03.72″N | 76°07′02.64″E
|  |  |  | Stringing (kms) | 227 | 0 | 227 | [6 empty] | 25 | Ghandhar | [6 empty] | Charged(Nov-26) | Oct-27 | 59 | KPS-I |  |  | Phase - II | Group - Cement (Hybrid - Solar) | A1 | PSS-04 | 52 | KPS-1 | AGEL |  |  |  | 0 | 31.2 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Wind) |  | ACL | Group | A1, A2, A3, A4, A5, NHPC |  | PSS-04 | - | - |  | 2025-06-30 |  |  | Q1 2026 | Phase II | 60 | Gadag-II PS | 15°22′45.84″N | 75°49′37.20″E
21 | Narendra (NEW) → Pune (GIS) | 765kV | AESL (TPL) | Foundation (nos.) | 232 | 115 | 117 | Nov-26 | Oct-27 |  |  | Yes | Pune-III (GIS) | 26 | Hazira | [6 empty] | Charged | Nov-26 | 60 | KPS-I |  | 150 | Phase - II | MSEDCL PPA Ph-1 | A1 | PSS-04 | 53 | KPS-1 | AGEL |  |  |  | 25 | 0 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Solar) | ACL_A01- E_FT_25MW_GROUP NEW | ACL | Group | A1 | A01e | PSS-04 | ALMM | FT | - | 2026-06-30 |  | Bondada | Q1 2027 | Phase II | 61 | Kurnool-III PS | 15°01′28.20″N | 78°08′40.20″E
|  |  |  | Erection (nos.) | 222 | 50 | 172 | [6 empty] | 27 | Nagpur (HVDC) | [5 empty] | Yes | In Progress | May-29 | 61 | KPS-I |  | 0 | Phase - II | Input Solar - BESS | SE4 | PSS-04 | 54 | KPS-1 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | Group - Cement (Hybrid - Solar) | ACL_A01_HSAT_50MW_Group_NEW | ACL | Group | A1 | A01 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-06-30 | Unallocated | Amara Raja | Q1 2027 | Phase II | 62 | Ananthapuram PS | 15°09′00.72″N | 77°25′42.24″E
|  |  |  | Stringing (kms) | 85.6 | 0 | 85.6 | [6 empty] | 28 | Nagpur |  |  |  | Yes |  | Yes | Charged | May-29 | 62 | KPS-I |  | 150 | Phase - II | TPL-D PPA | A2 | PSS-04 | 55 | KPS-1 | AGEL |  |  | 150 | 150 | 0 | Phase II | 2026-03-08 | MSEDCL PPA Ph-1 | ARE55L_A01_HSAT_150MW_Group_NEW | ARE55L | PPA | A1 | A01 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-07-31 | Unallocated | Amara Raja | Q2 2027 | Phase II | 63 | Bidar PS | 18°18′48.24″N | 77°17′53.16″E
22 | Kps-II → Lakadia | 765kV | AESL (TPL) | Foundation (nos.) | 0 | 0 | 0 |  | Charged |  |  |  |  | 29 | Kps-III (HVDC) | [6 empty] | In Progress(May-29) | Nov-26 | 63 | KPS-I |  | 125 | Phase - II | MSEDCL PPA Ph-1 | A2 | PSS-04 | 56 | KPS-1 | AGEL |  |  | 0 | 250 | 0 | Phase II |  | Input Solar - BESS |  | TBD |  | SE4 |  | PSS-04 | ALCM | HSAT |  | 2030-03-31 | Unallocated |  | Q4 2030 | Phase II | 64 | Davanagere/Chitradurga PS | 14°29′02.04″N | 76°17′29.04″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [6 empty] | 30 | South Olpad | [6 empty] | In Progress | May-29 | 64 | [7 empty] | 57 | KPS-1 | AGEL |  |  | 150 | 150 | 0 | Phase II | 2026-03-08 | TPL-D PPA | ARE8L_A02_HSAT_150MW_Merc | ARE8L | PPA | A2 | A02 | PSS-04 | China | HSAT | 2026-03-31 | 2026-06-30 | Yes Bank | Amara Raja | Q1 2027 | Phase II | 65 | Bellary PS | 15°00′20.16″N | 76°01′50.88″E
|  |  |  | Stringing (kms) | 177 | 177 | 0.0 | [6 empty] | 31 | Wardha | [6 empty] | Charged | Mar-26 | 65 | KPS-I | 100 | 100 | Phase - V | PTSL PPA - AEML RTC - Wind | A16, NHPC, A1,A3 | PSS-04 | 58 | KPS-1 | AGEL |  |  | 125 | 125 | 0 | Phase II | 2026-03-08 | MSEDCL PPA Ph-1 | ARE55L_A02_HSAT_125MW | ARE55L | PPA | A2 | A02 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-07-31 | Unallocated | Amara Raja | Q2 2027 | Phase II | 66 | Bijapur PS | 16°45′22.32″N | 76°10′27.12″E
23 | Lakadia → Vadodara | 765kV | PGCIL (KPIL) | Foundation (nos.) | 82 | 82 | 0 | Dec-25 | Oct-26 |  |  | Yes | Vataman | 32 | Raipur | [6 empty] | Charged | May-29 | 66 | KPS-I |  |  | Phase - V | AGEL Merchant (Wind) | A16, NHPC, A1,A3 | PSS-04 | [25 empty] | 67 | Tumkur-II PS | 14°07′36.48″N | 77°19′39.00″E
|  |  |  | Erection (nos.) | 82 | 80 | 2 | [6 empty] | 33 | Kps-II (HVDC) | [5 empty] | Yes | In Progress | May-29 | 67 | [7 empty] | 59 | KPS-1 | AGEL | 400kV | 100 | 100 | 0 | 52 | Phase V | 2029-12-31 | PTSL PPA - AEML RTC - Wind |  | AGE24L | PPA | A16, NHPC, A1,A3 |  | PSS-04 | - | - | - | 2025-03-31 | NABFID |  | Q4 2025 | Phase II | 68 | Ananthapuram-II PS | 14°53′02.40″N | 76°58′58.44″E
|  |  |  | Stringing (kms) | 28 | 26.5 | 1.5 | [16 empty] | 68 | KPS-I | 60 | 60 | Phase - V | AGEL Merchant (Wind) | A16, NHPC, A1,A3 | PSS-04 | 60 | KPS-1 | AGEL |  |  |  | 0 | 52 | Phase V | 2029-12-31 | AGEL Merchant (Wind) |  | AGE24L | Merchant | A16, NHPC, A1,A3 |  | PSS-04 | - | - | - | 2025-04-17 | NABFID |  | Q1 2026 | Phase II | 69 | Bhadla PS | 27°25′09.84″N | 72°04′19.92″E
24 | Kps-II → Halvad | 765kV | AESL (TLL/Jyoti Structure/Om construction/Tata) | Foundation (nos.) | 792 | 742 | 50 | Dec-25 | Dec-26 | [14 empty] | 69 | [32 empty] | 70 | Bikaner | 28°14′57.12″N | 73°22′54.84″E
|  |  |  | Erection (nos.) | 792 | 710 | 82 | [16 empty] | 70 | KPS-I | 1050 | 200 | Phase - II | Group - Cement (Solar) | A9 | PSS-03 | 61 | KPS-1 | AGEL | 400kV | 60 | 60 | 0 | 62.4 | Phase V | 2029-12-31 | AGEL Merchant (Wind) |  | AHEJ5L | Merchant | A16, NHPC, A1,A3 |  | PSS-04 | - | - | - | 2025-06-30 | SBI |  | Q1 2026 |  | 71 | Fatehgarh PS | 26°51′08.64″N | 71°30′34.20″E
|  |  |  | Stringing (kms) | 259.8 | 193.3 | 66.5 | [16 empty] | 71 | KPS-I |  | 200 | Phase - II | Group - Port (Solar) | A9 | PSS-03 | [25 empty] | 72 | Bhadla-II PS | 27°30′38.16″N | 72°28′40.44″E
25 | Navsari (NEW) → Padghe (PG) | 765kV | STERLITE GUJARAT TBCB | Foundation (nos.) | 71 | 71 | 0 | Oct-26 | Oct-26 |  |  | Yes | Boisar-II (GIS) | [10 empty] | 72 | KPS-I |  | 25 | Phase - II | Group - Port (Hybrid) | A10 | PSS-03 | 62 | KPS-1 | AGEL | 400kV | 1050 | 200 | 200 | 0 | Phase II | 2026-03-08 | Group - Cement (Solar) |  | ACL | Group | A9 |  | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025 | Phase II | 73 | Fatehgarh-III PS | 26°21′00.24″N | 71°06′00.39″E
|  |  |  | Erection (nos.) | 71 | 71 | 0 | [16 empty] | 73 | KPS-I |  | 25 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 63 | KPS-1 | AGEL |  |  | 200 | 200 | 0 | Phase II | 2026-03-08 | Group - Port (Solar) |  | APSEZ | Group | A9 |  | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025 | Phase II | 74 | Bikaner-II PS | 28°09′20.16″N | 73°00′23.40″E
|  |  |  | Stringing (kms) | 26 | 22 | 4 | [16 empty] | 74 | KPS-I |  | 25 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 64 | KPS-1 | AGEL |  |  | 25 | 25 | 20.8 | Phase II | 2026-03-08 | Group - Port (Hybrid) | APSEZ_A01- D_HSAT_25 MW_GROUP | APSEZ | Group | A01 | A01b | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025 |  | 75 | Fatehgarh-IV PS | 26°15′02.52″N | 71°14′07.08″E
26 | Hinjewadi → Koyna | 400kV | AESL (TPL) | Foundation (nos.) | 29 | 5 | 24 | Nov-26 | Mar-28 |  |  | Yes | Pune-III (GIS) | [10 empty] | 75 | KPS-I |  | 25 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 65 | KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AHEJ5L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | SBI |  | Q4 2024 | Phase V | 76 | Bhadla-III PS | 27°40′20.32″N | 72°12′23.59″E
|  |  |  | Erection (nos.) | 29 | 0 | 29 | [16 empty] | 76 | KPS-I |  | 25 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 66 | KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AGE24L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | NABFID |  | Q4 2024 | Phase V | 77 | Ramgarh PS | 27°28′17.25″N | 70°29′38.37″E
|  |  |  | Stringing (kms) | 10 | 0 | 10.0 | [16 empty] | 77 | KPS-I |  | 25 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 67 | KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AGE25CL | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | REC 4 |  | Q4 2024 |  | 78 | Bikaner-III PS | 28°22′22.54″N | 73°10′14.72″E
27 | Nagpur (HVDC) → Nagpur | 800kV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | May-29 | [14 empty] | 78 | KPS-I |  | 12.5 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 68 | KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | ARE56L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | REC 3 |  | Q4 2024 | Phase V | 79 | Bikaner-IV PS | 28°26′43.08″N | 73°14′15.00″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 79 | KPS-I |  | 12.5 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 69 | KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | ASEJ6L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | Axis/NABARD |  | Q4 2024 |  | 80 | Sirohi | 25°05′01.32″N | 72°47′36.24″E
|  |  |  | Stringing (kms) | 0 | 0 | 0 | [16 empty] | 80 | KPS-I |  | 12.5 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 70 | KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AGE26AL | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | PFC -3 |  | Q4 2024 | Phase II | 81 | KPS-I | 24°06′01.00″N | 69°20′13.26″E
28 | Kps-III (HVDC) → Kps-III | 400kV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | Mar-29 | [14 empty] | 81 | KPS-I |  | 12.5 | Phase - II | PTSL PPA - AEML RTC - Solar | A9 | PSS-03 | 71 | KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | ARE57L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | EM 3.1 |  | Q4 2024 | Phase II | 82 | KPS-II | 24°04′56.96″N | 69°31′01.32″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 82 | KPS-I |  | 400 | Phase - II | PTSL PPA - AEML RTC - Solar | A10b | PSS-03 | 72 | KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | ARE55L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | Unallocated |  | Q4 2024 | Phase II | 83 | KPS-III | 24°04′01.79″N | 69°28′27.63″E
|  |  |  | Stringing (kms) | 2 | 0 | 2 | [16 empty] | 83 | KPS-I |  |  | Phase - II | PTSL PPA - AEML RTC - Solar | A10b | PSS-03 | 73 | KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | ARE41L | PPA | A9 |  | PSS-03 | ALMM | HSAT | - | 2024-03-31 | PFC- W |  | Q4 2024 | Phase II | 84 | Raipur | 21°14′00.00″N | 81°29′00.00″E
29 | South Olpad → South Olpad (GIS) | 800kV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | Dec-29 | [14 empty] | 84 | KPS-I |  | 50 | Phase - II | MLP T1 TR | A10a | PSS-03 | 74 | KPS-1 | AGEL |  |  | 400 | 112.5 | 0 | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AGE24AL | PPA | A10b |  | PSS-03 | ALMM | HSAT | - | 2024-12-28 | REC 1 |  | Q3 2025 | Phase II | 85 | Raipur 765 kV | 21°14′00.00″N | 81°29′00.00″E
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 85 | [7 empty] | 75 | KPS-1 | AGEL |  |  |  | 287.5 |  | Phase II | 2026-03-08 | PTSL PPA - AEML RTC - Solar |  | AGE24AL | PPA | A10b |  | PSS-03 | ALMM | HSAT | - | 2025-03-29 | REC 1 |  | Q4 2025 | Phase II | 86 | KPS-III (HVDC) | 24°04′01.79″N | 69°34′22.21″E
|  |  |  | Stringing (kms) | 0 | 0 | 0 | [16 empty] | 86 | KPS-I | 250 | 250 | Phase - III | PTSL PPA - AEML RTC - Wind | A5, A8, A4, A7, A9, A10 | PSS-03 | 76 | KPS-1 | AGEL |  |  | 50 | 50 | 0 | Phase II | 2026-03-08 | MLP T1 TR | AGE26AL_A10a_FT_50MW_PPA_Commissioned | AGE26AL | PPA | A10a |  | PSS-03 | SEA | FT | LTA - 23 Days | 2025-10-15 | PFC -3 |  | Q3 2026 | Phase II | 87 | KPS-II (HVDC) | 24°04′56.96″N | 69°36′55.94″E
30 | Wardha → Raipur | 765kV | PGCIL (TLL) | Foundation (nos.) | 87 | 43 | 44 | May-29 | May-29 |  |  | Yes | Nagpur | [10 empty] | 87 | KPS-I |  |  | Phase - III | PTSL PPA - AEML RTC - Wind | A5, A8, A4, A7, A9, A10 | PSS-03 | [25 empty] | 88 | South Olpad (HVDC) | 21°56′45.61″N | 73°10′57.40″E
|  |  |  | Erection (nos.) | 87 | 3 | 84 | [16 empty] | 88 |  |  | 0 |  |  |  |  | 77 | KPS-1 | AGEL |  | 250 | 250 | - | 5.2 | Phase III | 2027-01-31 | PTSL PPA - AEML RTC - Wind |  | ARE41L | PPA | A5, A8, A4, A7, A9, A10 |  | PSS-03 |  |  |  | 2026-06-30 |  |  | Q1 2027 | Phase II | 89 | Ramgarh (HVDC) | 27°28′17.25″N | 70°35′43.27″E
|  |  |  | Stringing (kms) | 34 | 0 | 34.0 | [16 empty] | 89 | KPS-III | 1050 | 250 | Phase - II | MLP T3 PPA - AP | A6c | PSS-08 | 78 | KPS-1 | AGEL | 400kV |  |  | 0 | 260 | Phase III | 2027-01-31 | PTSL PPA - AEML RTC - Wind |  | ARE41L | PPA | A5, A8, A4, A7, A9, A10 |  | PSS-03 | - | - | 2024-03-31 | 2024-07-24 | PFC Wind 260 |  | Q2 2025 | Phase II
31 | Kps-II (HVDC) → Kps-II | 800kV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | TBD | [14 empty] | 90 | KPS-III |  |  | Phase - II | MLP T3 PPA - AP | A6c | PSS-08 | [5 empty] | 0 | 0 | 0
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 91 | KPS-III |  |  | Phase - II | MLP T3 PPA - AP | A6c | PSS-08 | 79 | KPS-3 | AGEL | 400kV | 1050 | 250 | 75 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_HSAT_75 MW_PPA_Commissioned | AGE25CL | PPA | A6c |  | PSS-08 | China | HSAT | 2025-11-29 | 2025-11-30 | REC 4 |  | Q3 2026 | Phase II
|  |  |  | Stringing (kms) | 0 | 0 | 0.0 | [16 empty] | 92 | KPS-III |  | 250 | Phase - II | MLP T3 PPA - AP | A6c | PSS-08 | 80 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-02-28 | REC 4 |  | Q4 2026 | Phase II
32 | Lakadia → Vadodara | 765kV | TBD | Foundation (nos.) | 0 | 0 | 0 | - | Jan-23 | Charged | [13 empty] | 93 | KPS-III |  |  | Phase - II | MLP T3 PPA - AP | A6c | PSS-08 | 81 | KPS-3 | AGEL |  |  |  | 75 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-03-31 | REC 4 |  | Q4 2026 | Phase II
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 94 | KPS-III |  | 150 | Phase - II | AGEL Merchant (Solar) | A15a | PSS-08 | 82 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-05-31 | REC 4 |  | Q1 2027 | Phase II
|  |  |  | Stringing (kms) | 335 | 335 | 0.0 | [16 empty] | 95 | KPS-III |  |  | Phase - II | AGEL Merchant (Solar) | A15a | PSS-08 | 83 | KPS-3 | AGEL |  |  | 250 | 100 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-03-31 | REC 4 |  | Q4 2026 | Phase II
33 | Wardha → Raipur | 765KV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | TBD | Charged | [13 empty] | 96 | KPS-III |  |  | Phase - II | AGEL Merchant (Solar) | A15a | PSS-08 | 84 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-03-31 | REC 4 |  | Q4 2026 | Phase II
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 97 | KPS-III |  | 50 | Phase - II | MSEDCL PPA Ph-1 | A15b | PSS-08 | 85 | KPS-3 | AGEL |  |  |  | 100 | 0 | Phase II | 2026-03-08 | MLP T3 PPA - AP | AGE25CL_A06_FT_425MW_PPA | AGE25CL | PPA | A6c |  | PSS-08 | China | FT | 2025-11-29 | 2026-05-31 | REC 4 |  | Q1 2027
|  |  |  | Stringing (kms) | 0 | 0 | 0.0 | [16 empty] | 98 | KPS-III |  | 0 | Phase - II | Input Solar - BESS | A15a | PSS-08 | 86 | KPS-3 | AGEL |  |  | 150 | 50 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AHEJ5L_A15a_HSAT_150MW_MERCHANT_Commissioned | AHEJ5L | Merchant | A15a |  | PSS-08 | ALMM | HSAT | - | 2025-09-30 | SBI |  | Q2 2026 | Phase III
34 | Hinjewadi → Koyna | 765kV | TBD | Foundation (nos.) | 0 | 0 | 0 |  | TBD | Charged | [13 empty] | 99 | KPS-III |  | 0 | Phase - II | Input Solar - BESS | SE10 | PSS-08 | 87 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AHEJ5L_A15a_HSAT_150MW_MERCHANT_Commissioned | AHEJ5L | Merchant | A15a |  | PSS-08 | ALMM | HSAT | - | 2026-01-31 | SBI |  | Q4 2026 | Phase III
|  |  |  | Erection (nos.) | 0 | 0 | 0 | [16 empty] | 100 | KPS-III |  | 50 | Phase - II | Group - Copper (Solar) | A15a | PSS-08 | 88 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AHEJ5L_A15a_HSAT_150MW_MERCHANT_Commissioned | AHEJ5L | Merchant | A15a | A15a | PSS-08 | ALMM | HSAT | - | 2026-05-31 | SBI | KPI | Q1 2027
|  |  |  | Stringing (kms) | 0 | 0 | 0.0 | [16 empty] | 101 | KPS-III |  |  | Phase - II | Group - Copper (Solar) | A15a | PSS-08 | 89 | KPS-3 | AGEL |  |  | 50 | 50 | 0 | Phase II | 2026-03-08 | MSEDCL PPA Ph-1 | ARE41L_A15b_HSAT_50MW | ARE55L | PPA | A15b | A15b | PSS-08 | ALMM | HSAT | 2026-04-29 | 2026-06-30 | Unallocated | S&W | Q1 2027 | Phase II
[24 empty] | 102 | KPS-III |  |  | Phase - II | AGEL Merchant (Solar) | A15a | PSS-08 | 90 | KPS-3 | AGEL |  |  | 0 | 50 | 0 | Phase II |  | Input Solar - BESS |  | ARE41L |  | A15a |  | PSS-08 | ALCM | HSAT |  | 2029-03-31 |  |  | Q4 2029 | Phase II
[24 empty] | 103 | KPS-III |  | 60 | Phase - II | AGEL Hybrid Merchant (Wind) | A15, A6 | PSS-08 | 91 | KPS-3 | AGEL |  |  | 0 | 200 | 0 | Phase II |  | Input Solar - BESS |  | TBD |  | SE10 |  | PSS-08 | ALCM | HSAT |  | 2029-03-31 | Unallocated |  | Q4 2029 | Phase II
[24 empty] | 104 | KPS-III |  |  | Phase - II | AESL PPA (C&I) - Solar | A6 | PSS-08 | 92 | KPS-3 | AGEL |  |  | 50 | 12.5 | 0 | Phase II | 2026-03-08 | Group - Copper (Solar) | AGE25BL_A15a_HSAT_50 MW_MERCHANT | KCTL | Group | A15a |  | PSS-08 | ALMM | HSAT | - | 2026-03-31 |  |  | Q4 2026 | Phase II
[24 empty] | 105 | KPS-III |  | 50 | Phase - II | Adani Connex PPA - Google (Hybrid - Wind) | A18, A15. NHPC | PSS-08 | 93 | KPS-3 | AGEL |  |  |  | 12.5 | 0 | Phase II | 2026-03-08 | Group - Copper (Solar) | AGE25BL_A15a_HSAT_50 MW_MERCHANT | MCIPL | Group | A15a |  | PSS-08 | ALMM | HSAT | - | 2026-03-31 |  |  | Q4 2026 | Phase II
[24 empty] | 106 | KPS-III |  |  | Phase - II | Adani Connex PPA - Google (Hybrid - Wind) | A18, A15. NHPC | PSS-08 | 94 | KPS-3 | AGEL |  |  |  | 25 | 0 | Phase II | 2026-03-08 | AGEL Merchant (Solar) | AGE25BL_A15a_HSAT_50 MW_MERCHANT | ASEJ6L | Merchant | A15a |  | PSS-08 | ALMM | HSAT | - | 2026-03-31 | Axis |  | Q4 2026 | Phase II
[24 empty] | 107 | KPS-III |  |  | Phase - II | Adani Connex PPA - Google (Hybrid - Solar) | A6 | PSS-08 | 95 | KPS-3 | AGEL |  |  | 60 | 0 | 62.4 | Phase II | 2026-03-08 | AGEL Hybrid Merchant (Wind) | ASEJ6PL PSS-08 (12 Loc.) | ASEJ6L | Merchant | A15, A6 |  | PSS-08 |  | - | - | 2026-03-31 | TCCL |  | Q4 2026 | Phase II
[24 empty] | 108 | KPS-III |  | 65 | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 96 | KPS-3 | AGEL |  |  |  | 35 | 0 | Phase II | 2026-03-08 | AESL PPA (C&I) - Solar | ASEJ6PL_A06_HSAT_35MW_MERCHANT_Commissioned | ASEJ6L | PPA | A6 |  | PSS-08 | ALMM | HSAT | - | 2025-09-30 | TCCL |  | Q2 2026 | Phase II
[24 empty] | 109 | KPS-III |  |  | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 97 | KPS-3 | AGEL |  |  | 50 | 0 | 15.6 | Phase II | 2026-03-08 | Adani Connex PPA - Google (Hybrid - Wind) |  | ARE3L | PPA | A18, A15. NHPC |  | PSS-08 |  | - | 2025-06-30 | 2025-08-31 | TCCL |  | Q2 2026 | Phase II
[24 empty] | 110 | KPS-III |  |  | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 98 | KPS-3 | AGEL |  |  |  | 0 | 26 | Phase II | 2026-03-08 | Adani Connex PPA - Google (Hybrid - Wind) | ARE3L PSS-08 (05 Loc.) | ARE3L | PPA | A18, A15. NHPC |  | PSS-08 |  | - | 2025-06-30 | 2025-08-31 | TCCL |  | Q2 2026 | Phase II
[24 empty] | 111 | KPS-III |  | 125 | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 99 | KPS-3 | AGEL |  |  |  | 25 | 0 | Phase II | 2026-03-08 | Adani Connex PPA - Google (Hybrid - Solar) | ARE3L_A06_HSAT_25 MW_MERCHANT_Commissioned | ARE3L | PPA | A6 |  | PSS-08 | ALMM | HSAT | 2025-06-30 | 2025-07-30 | TCCL |  | Q2 2026 | Phase II
[24 empty] | 112 | KPS-III |  |  | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 100 | KPS-3 | AGEL |  |  | 65 | 0 | 31.2 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | AHEJ5L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-09-30 | SBI |  | Q2 2026
[24 empty] | 113 | KPS-III |  |  | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 101 | KPS-3 | AGEL |  |  |  | 0 | 31.2 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | AHEJ5L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-11-30 | SBI |  | Q3 2026
[24 empty] | 114 | KPS-III |  |  | Phase - II | AGEL Merchant (Wind) | NHPC, A15,A16, A6, A18 | PSS-08 | 102 | KPS-3 | AGEL |  |  |  | 0 | 5.2 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | AHEJ5L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2026-02-28 | SBI |  | Q4 2026 | Phase II
[24 empty] | 115 | [7 empty] | 103 | KPS-3 | AGEL |  |  | 125 | 0 | 52 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | ARE41L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026 | Phase II
[24 empty] | 116 | KPS-I | 1050 | 400 | Phase - III | MSEDCL PPA Ph-1 | S9 | PSS-07 | 104 | KPS-3 | AGEL |  |  |  | 0 | 26 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | ARE41L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026 | Phase II
[24 empty] | 117 | KPS-I |  |  | Phase - III | MSEDCL PPA Ph-1 | S9 | PSS-07 | 105 | KPS-3 | AGEL |  |  |  | 0 | 46.8 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | ARE41L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026 | Phase II
[24 empty] | 118 | KPS-I |  | 600 | Phase - III | MSEDCL PPA Ph-2 | A18 | PSS-07 | 106 | KPS-3 | AGEL |  |  |  | 0 | 5.2 | Phase II | 2026-03-08 | AGEL Merchant (Wind) |  | ARE41L | Merchant | NHPC, A15,A16, A6, A18 |  | PSS-08 |  | - | - | 2025-11-30 | PFC- W |  | Q3 2026 | Phase II
[24 empty] | 119 | KPS-I |  | 50 | Phase - III | MSEDCL PPA Ph-3 | S10 | PSS-07
[24 empty] | 120 | KPS-I |  | 0 | Phase - III | Input Solar - BESS | SE12, SE10 | PSS-07 | 107 | KPS-1 | AGEL |  | 1050 | 400 | 300 | - | Phase III | 2027-01-31 | MSEDCL PPA Ph-1 | AGE24AL_S09_HSAT_400MW | ARE55L | PPA | S9 | S09 | PSS-07 | ALMM | HSAT | 2026-04-29 | 2027-03-31 | Unallocated | S&W | Q4 2027 | Phase II
[24 empty] | 121 | [7 empty] | 108 | KPS-1 | AGEL |  |  |  | 100 | - | Phase III | 2027-01-31 | MSEDCL PPA Ph-1 | AGE24AL_S09_HSAT_400MW | ARE55L | PPA | S9 | S09 | PSS-07 | ALMM | HSAT | 2026-04-29 | 2027-01-31 | Unallocated | S&W | Q4 2027 | Phase II
[24 empty] | 122 | KPS-III | 1250 | 250 | Phase - V | MLP PPA - AP New | A11 | PSS-13 | 109 | KPS-1 | AGEL | 400kV |  | 600 | 600 | - | Phase III | 2027-01-31 | MSEDCL PPA Ph-2 | ARE55L_A18_HSAT_600MW | ARE55L | PPA | A18 | A18 | PSS-07 | ALMM | HSAT | 2026-10-29 | 2027-03-31 | Unallocated | S&W | Q4 2027 | Phase II
[24 empty] | 123 | KPS-III |  | 150 | Phase - V | MLP PPA - AP New | A11 | PSS-13 | 110 | KPS-1 | AGEL |  |  | 50 | 50 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-3 | ARE55L_S10_HSAT_50 MW_PPA | ARE55L | PPA | S10 | S10 | PSS-07 | ALMM | HSAT | 2027-04-29 | 2027-03-31 | Unallocated | Jakson | Q4 2027 | Phase II
[24 empty] | 124 | KPS-III |  |  | Phase - V | MLP PPA - AP New | A11 | PSS-13 | 111 | KPS-1 | AGEL |  |  | 0 | 400 | 0 | Phase II |  | Input Solar - BESS |  | TBD |  | SE12, SE10 |  | PSS-07 | ALCM | HSAT |  | 2030-03-31 | Unallocated |  | Q4 2030 | Phase II
[24 empty] | 125 | KPS-III |  | 100 | Phase - V | MLP PPA - AP New | A11 | PSS-13
[24 empty] | 126 | KPS-III |  |  | Phase - V | MLP PPA - AP New | A11 | PSS-13 | 112 | KPS-3 | AGEL | 400kV | 1250 | 250 | 250 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE57L | PPA | A11 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-28 | EM 3.1 |  | Q4 2025 | Phase II
[24 empty] | 127 | KPS-III |  | 250 | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 113 | KPS-3 | AGEL |  |  | 150 | 12.5 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE57L | PPA | A11 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-29 | EM 3.1 |  | Q4 2025 | Phase II
[24 empty] | 128 | KPS-III |  |  | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 114 | KPS-3 | AGEL |  |  |  | 137.5 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE57L | PPA | A11 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-05-21 | EM 3.1 |  | Q1 2026 | Phase II
[24 empty] | 129 | KPS-III |  | 150 | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 115 | KPS-3 | AGEL |  |  | 100 | 50 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE57L | PPA | A11 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-31 | EM 3.1 |  | Q4 2025 | Phase II
[24 empty] | 130 | KPS-III |  | 100 | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 116 | KPS-3 | AGEL |  |  |  | 50 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New |  | ARE57L | PPA | A11 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-05-01 | EM 3.1 |  | Q1 2026 | Phase II
[24 empty] | 131 | KPS-III |  |  | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 117 | KPS-3 | AGEL |  |  | 250 | 225 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-06-30 | EM 3.1 |  | Q1 2026
[24 empty] | 132 | KPS-III |  | 200 | Phase - V | MLP PPA - AP New | A12 | PSS-13 | 118 | KPS-3 | AGEL |  |  |  | 25 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026 | Phase III
[24 empty] | 133 | KPS-III |  | 50 | Phase - V | AGEL Merchant (Wind) | A11, A12, A7, A10 | PSS-13 | 119 | KPS-3 | AGEL |  |  | 150 | 150 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-05-31 | EM 3.1 |  | Q1 2027 | Phase III
[24 empty] | 134 | [7 empty] | 120 | KPS-3 | AGEL |  |  | 100 | 25 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026 | Phase III
[24 empty] | 135 | KPS-III | 75 | 75 | Phase - V | AGEL Merchant (Wind) | A11, A12, A7, A10 | PSS-13 | 121 | KPS-3 | AGEL |  |  |  | 75 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 |  | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026 | Phase III
[24 empty] | 136 | [7 empty] | 122 | KPS-3 | AGEL |  |  | 200 | 200 | 0 | Phase V | 2029-12-31 | MLP PPA - AP New | ARE57L_A12_HSAT_350MW_PPA | ARE57L | PPA | A12 | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-06-30 | EM 3.1 |  | Q1 2027
[24 empty] | 137 | KPS-III | 1530 | 287.5 | Phase - V | MSEDCL PPA Ph-3 | S10 | PSS-14 | 123 | KPS-3 | AGEL |  |  | 50 | 0 | 52 | Phase V | 2029-12-31 | AGEL Merchant (Wind) |  | ARE41L | Merchant | A11, A12, A7, A10 |  | PSS-13 |  | - | - | 2025-03-27 | PFC- W |  | Q4 2025
[24 empty] | 138 | KPS-III |  | 162.5 | Phase - V | AGEL Merchant (Solar) - TTE | S10 | PSS-14
[24 empty] | 139 | KPS-III |  | 125 | Phase - V | AGEL Merchant (Solar) - TTE | SE16 | PSS-14 | 124 | KPS-3 | AGEL | 400kV | 75 | 75 | 0 | 72.8 | Phase V | 2029-12-31 | AGEL Merchant (Wind) |  | ARE41L | Merchant | A11, A12, A7, A10 |  | PSS-13 |  | - | - | 2025-03-29 | PFC- W |  | Q4 2025 | Phase V
[24 empty] | 140 | KPS-III |  | 162.5 | Phase - V | AGEL Merchant (Solar) - TTE | SE16 | PSS-14
[24 empty] | 141 | KPS-III |  | 300 | Phase - V | MSEDCL PPA Ph-3 | SE14 | PSS-14 | 125 | KPS-3 | AGEL |  | 1530 | 287.5 | 287.5 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | S10 |  | PSS-14 | ALMM | HSAT | 2027-04-29 | 2027-05-31 | Unallocated | L&T | Q1 2028 | Phase V
[24 empty] | 142 | KPS-III |  | 200 | Phase - V | MSEDCL PPA Ph-3 | SE14 | PSS-14 | 126 | KPS-3 | AGEL |  |  | 162.5 | 162.5 | 0 | Phase V | 2029-12-31 | AGEL Merchant (Solar) - TTE |  | AE3L | Merchant | S10 |  | PSS-14 | ALCM | HSAT |  | 2027-08-31 | BOB | Jakson | Q2 2028 | Phase V
[24 empty] | 143 | KPS-III |  | 67.5 | Phase - V | MSEDCL PPA Ph-3 | SE16 | PSS-14 | 127 | KPS-3 | AGEL |  |  | 125 | 125 | 0 | Phase V | 2029-12-31 | AGEL Merchant (Solar) - TTE |  | AE3L | Merchant | SE16 |  | PSS-14 | ALCM | HSAT |  | 2027-09-30 | BOB | Jakson | Q2 2028 | Phase V
[24 empty] | 144 | KPS-III |  | 175 | Phase - V | AGEL Merchant (Solar) - TTE | SE16, SE15 | PSS-14 | 128 | KPS-3 | AGEL |  |  | 162.5 | 162.5 | 0 | Phase V | 2029-12-31 | AGEL Merchant (Solar) - TTE |  | AE2L | Merchant | SE16 |  | PSS-14 | ALCM | HSAT |  | 2027-09-30 | Unallocated | Jakson | Q2 2028 | Phase V
[24 empty] | 145 | KPS-III |  | 50 | Phase - V | MSEDCL PPA Ph-3 | SE14 | PSS-14 | 129 | KPS-3 | AGEL |  |  | 300 | 300 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 | AGEL_SE14_HSAT_500MW_HILD | ARE55L | PPA | SE14 |  | PSS-14 | ALMM | HSAT | 2027-04-29 | 2028-06-30 | Unallocated | Hild | Q1 2029 | Phase V
[24 empty] | 146 | [7 empty] | 130 | KPS-3 | AGEL |  |  | 200 | 200 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 | AGEL_SE14_HSAT_500MW_HILD | ARE55L | PPA | SE14 |  | PSS-14 | ALMM | HSAT | 2027-04-29 | 2028-09-30 | Unallocated | Hild | Q2 2029 | Phase V
[24 empty] | 147 | KPS-III | 100 | 100 | Phase - V | AGEL Merchant (Wind) | SE13, SE14, SE15, SE16 | PSS-14 | 131 | KPS-3 | AGEL |  |  | 67.5 | 67.5 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | SE16 |  | PSS-14 | ALMM | HSAT | 2027-04-29 | 2029-03-31 | Unallocated |  | Q4 2029 | Phase V
[24 empty] | 148 | [7 empty] | 132 | KPS-3 | AGEL |  |  | 175 | 175 | 0 | Phase V | 2029-12-31 | AGEL Merchant (Solar) - TTE |  | AE2L | Merchant | SE16, SE15 |  | PSS-14 | ALCM | HSAT | - | 2027-09-30 | Unallocated |  | Q2 2028 | Phase V
[24 empty] | 149 | KPS-III | 195 | 195 | Phase - V | AGEL Merchant (Wind) | SE13, SE14, SE15, SE16 | PSS-14 | 133 | KPS-3 | AGEL |  |  | 50 | 50 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 | AGEL_SE14_HSAT_500MW_HILD | ARE55L | PPA | SE14 |  | PSS-14 | ALMM | HSAT | 2027-04-29 | 2029-03-31 | Unallocated |  | Q4 2029 | Phase V
[24 empty] | 150 | KPS-III |  |  | Phase - V | AGEL Merchant (Wind) | SE13, SE14, SE15, SE16 | PSS-14
[24 empty] | 151 | KPS-III |  |  | Phase - V | AGEL Merchant (Wind) | SE13, SE14, SE15, SE16 | PSS-14 | 134 | KPS-3 | AGEL |  | 100 | 100 | 0 | 104 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | SE13, SE14, SE15, SE16 |  | PSS-14 |  | - | - | 2026-05-31 | PFC -3 |  | Q1 2027 | Phase V
152
[24 empty] | 153 | KPS-III | 65 | 65 | Phase - V | AGEL Merchant (Wind) | A18, S10 | PSS-14 | 135 | KPS-3 | AGEL |  | 195 | 195 | 0 | 98.8 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | SE13, SE14, SE15, SE16 |  | PSS-14 |  | - |  | 2026-04-30 | PFC -3 |  | Q1 2027 | Phase V
[24 empty] | 154 | KPS-III |  |  | Phase - V | AGEL Merchant (Wind) | A18, S10 | PSS-14 | 136 | KPS-3 | AGEL |  |  |  | 0 | 31.2 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | SE13, SE14, SE15, SE16 |  | PSS-14 |  | - |  | 2026-05-31 | PFC -3 |  | Q1 2027
[24 empty] | 155 | [7 empty] | 137 | KPS-3 | AGEL |  |  |  | 0 | 78 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | SE13, SE14, SE15, SE16 |  | PSS-14 |  | - |  | 2026-06-30 | PFC -3 |  | Q1 2027 | Phase V
[24 empty] | 156 | KPS-III | 75 | 75 | Phase - V | MSEDCL PPA Ph-3 | SE10, SE11, SE12, SE14 | PSS-14
[24 empty] | 157 | [7 empty] | 138 | KPS-3 | AGEL |  | 65 | 65 | 0 | 41.6 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | AGE25CL | Merchant | A18, S10 |  | PSS-14 |  | - | - | 2026-03-31 | REC 4 |  | Q4 2026
[24 empty] | 158 | KPS-III | 600 | 600 | Phase - IV | NHPC EPC 600 | NHPC | NHPC | 139 | KPS-3 | AGEL |  |  |  | 0 | 26 | Phase V | 2029-12-31 | AGEL Merchant (Wind) | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | AGE25CL | Merchant | A18, S10 |  | PSS-14 |  | - | - | 2026-03-31 | REC 4 |  | Q4 2026 | Phase V
[24 empty] | 159 | KPS-III |  |  | Phase - IV | NHPC EPC 600 | NHPC | NHPC
[24 empty] | 160 | KPS-III |  |  | Phase - IV | NHPC EPC 600 | NHPC | NHPC | 140 | KPS-3 | AGEL |  | 75 | 75 | 75 | 0 | Phase V | 2029-12-31 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | SE10, SE11, SE12, SE14 |  | PSS-14 | ALMM | TBD | 2027-04-29 | 2029-03-31 | Unallocated |  | Q4 2029 | Phase V
[24 empty] | 161 | KPS-III |  |  | Phase - IV | NHPC EPC 600 | NHPC | NHPC
[24 empty] | 162 | [7 empty] | 141 | KPS-3 | AGEL | KPS-4 | 600 | 600 | 100 | 0 | Phase IV | 2028-01-01 | NHPC EPC 600 | NHPC EPC 200 MW Khavda-Internal | NA | NHPC | NHPC | NHPC | NHPC | DCR | HSAT | 2026-12-19 | 2027-02-28 |  |  | Q4 2027 | Phase V
[24 empty] | 163 |  | 13600 | 13600 |  |  |  |  | 142 | KPS-3 | AGEL | KPS-5 |  |  | 100 | 0 | Phase IV | 2028-01-01 | NHPC EPC 600 | NHPC EPC 200 MW Khavda-Internal | NA | NHPC | NHPC | NHPC | NHPC | DCR | HSAT | 2026-12-19 | 2027-03-31 |  |  | Q4 2027 | Phase V
[24 empty] | 164 | [7 empty] | 143 | KPS-3 | AGEL | KPS-6 |  |  | 200 | 0 | Phase IV | 2028-01-01 | NHPC EPC 600 | NHPC EPC 400 MW Khavda-Internal | NA | NHPC | NHPC |  | NHPC | DCR | HSAT | 2026-12-19 | 2027-06-30 |  |  | Q1 2028 | Phase V
[24 empty] | 165 | KPS-I | 1150 | 300 | Phase - III | SECI VIII PPA | S7 | PSS-09 | 144 | KPS-3 | AGEL | 400kV |  |  | 200 | 0 | Phase IV | 2028-01-01 | NHPC EPC 600 | NHPC EPC 400 MW Khavda-Internal | NA | NHPC | NHPC |  | NHPC | DCR | HSAT | 2026-12-19 | 2027-09-30 |  |  | Q2 2028 | Phase V
[24 empty] | 166 | KPS-I |  | 300 | Phase - III | SECI VIII PPA | S7 | PSS-09
[24 empty] | 167 | KPS-I |  | 400 | Phase - III | AESL PPA (C&I) - Solar | S8 | PSS-09 |  |  |  |  | 13600 | 13350.4736 | 13235 | 1721.2
[24 empty] | 168 | KPS-I |  |  | Phase - III | AESL PPA (C&I) - Solar | S8 | PSS-09 |  | SARJAN PARK
[24 empty] | 169 | KPS-I |  |  | Phase - III | AGEL Merchant (Solar) | S8 | PSS-09 | 145 | KPS-1 | SRPL | 400kV | 1150 | 300 | 300 | 0 | Phase III | 2027-01-31 | SECI VIII PPA | ASEJ6PL_S07_FT_300MW_PPA | ASEJ6L | PPA | S7 | S07 | PSS-09 | China | FT | LTA + 30D | 2026-12-31 | Axis/NABARD | Enrich | Q3 2027 | Phase V
[24 empty] | 170 | KPS-I |  | 150 | Phase - III | AESL PPA (C&I) - Asahi, Wilmar, Airport | S8 | PSS-09 | 146 | KPS-1 | SRPL |  |  | 300 | 100 | 0 | Phase III | 2027-01-31 | SECI VIII PPA | ASEJ6PL_S07_FT_300MW | ASEJ6L | PPA | S7 | S07 | PSS-09 | China | FT | LTA + 30D | 2026-12-31 | Axis/NABARD | KPI Green | Q3 2027 | Phase V
[24 empty] | 171 | KPS-I |  |  | Phase - III | AESL PPA (C&I) - Asahi, Wilmar, Airport | S8 | PSS-09 | 147 | KPS-1 | SRPL |  |  |  | 200 | 0 | Phase III | 2027-01-31 | SECI VIII PPA | ASEJ6PL_S07_FT_300MW | ASEJ6L | PPA | S7 | S07 | PSS-09 | China | FT | LTA + 30D | 2027-01-31 | Axis/NABARD | KPI Green | Q4 2027 | Phase V
[24 empty] | 172 | KPS-I |  |  | Phase - III | AESL PPA (C&I) - Asahi, Wilmar, Airport, Shantigram | S7, S8 | PSS-09 | 148 | KPS-1 | SRPL |  |  | 400 | 150 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Solar |  | ARE56L | PPA | S8 |  | PSS-09 | ALMM | HSAT | - | 2025-03-29 | REC 3 |  | Q4 2025
[24 empty] | 173 | KPS-I |  |  | Phase - III | AESL PPA (C&I) - Asahi, Wilmar, Airport | S7, S8 | PSS-09 | 149 | KPS-1 | SRPL |  |  |  | 125 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Solar |  | ARE56L | PPA | S8 |  | PSS-09 | ALMM | HSAT | - | 2025-05-31 | REC 3 |  | Q1 2026 | Phase V
[24 empty] | 174 | KPS-I |  |  | Phase - III | AGEL Hybrid Merchant (Wind) | S7, S8 | PSS-09 | 150 | KPS-1 | SRPL |  |  |  | 125 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) |  | ARE56L | Merchant | S8 |  | PSS-09 | ALMM | HSAT | - | 2025-08-01 | REC 3 |  | Q2 2026
[24 empty] | 175 | [7 empty] | 151 | KPS-1 | SRPL |  |  | 150 | 50 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Nestle |  | AGE25BL | PPA | S8 |  | PSS-09 | ALMM | HSAT | - | 2025-09-30 | PFC 1 |  | Q2 2026 | Phase V
[24 empty] | 176 | KPS-III | 1250 | 234 | Phase - III | MLP T1 PPA - BEST | S6-A | PSS-10 | 152 | KPS-1 | SRPL |  |  |  | 50 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Nestle |  | AGE25BL | PPA | S8 |  | PSS-09 | ALMM | HSAT | - | 2025-09-30 | PFC 1 |  | Q2 2026 | Phase V
[24 empty] | 177 | KPS-III |  |  | Phase - III | MLP T1 PPA - BEST | S6-A | PSS-10 | 153 | KPS-1 | SRPL |  |  |  | 0 | 67.6 | Phase III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar,Nestle |  | AGE25BL | PPA | S7, S8 |  | PSS-09 |  | - | - | 2025-01-14 | PFC 1 |  | Q4 2025 | Phase V
[24 empty] | 178 | KPS-III |  | 250 | Phase - III | MLP T3 PPA - AP | S6-B | PSS-10 | 154 | KPS-1 | SRPL |  |  |  | 0 | 52 | Phase III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Airport, Shantigram |  | AGE25BL | PPA | S7, S8 |  | PSS-09 |  | - | - | 2025-01-14 | PFC 1 |  | Q4 2025
[24 empty] | 179 | KPS-III |  |  | Phase - III | MLP T3 PPA - AP | S6-B | PSS-10 | 155 | KPS-1 | SRPL |  |  |  | 0 | 10.4 | Phase III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Airport |  | AGE25BL | PPA | S7, S8 |  | PSS-09 |  | - | - | 2026-02-28 | PFC |  | Q4 2026 | Phase V
[24 empty] | 180 | KPS-III |  | 250 | Phase - III | MLP T3 PPA - AP | S6-B | PSS-10 | 156 | KPS-1 | SRPL |  |  |  | 0 | 20.8 | Phase III | 2027-01-31 | AGEL Hybrid Merchant (Wind) |  | AGE25BL | Merchant | S7, S8 |  | PSS-09 |  | - | - | 2028-12-31 | Unallocated |  | Q3 2029 | Phase V
[24 empty] | 181 | KPS-III |  |  | Phase - III | MLP T3 PPA - AP | S6-B | PSS-10
[24 empty] | 182 | KPS-III |  | 150 | Phase - III | AGEL Merchant (Solar) | S5 | PSS-10 | 157 | KPS-3 | SRPL | 400kV | 1250 | 234 | 100 | 0 | Phase III | 2027-01-31 | MLP T1 PPA - BEST | AGE26AL_S06A_FT_234MW | AGE26AL | PPA | S6-A | S06a | PSS-10 | SEA | FT | LTA + 56D | 2027-02-28 | Canara/ BOB | KPI Green | Q4 2027
[24 empty] | 183 | KPS-III |  |  | Phase - III | AGEL Merchant (Solar) | S5 | PSS-10 | 158 | KPS-3 | SRPL |  |  |  | 134 | 0 | Phase III | 2027-01-31 | MLP T1 PPA - BEST | AGE26AL_S06A_FT_234MW | AGE26AL | PPA | S6-A | S06a | PSS-10 | SEA | FT | LTA + 56D | 2027-01-31 | Canara/ BOB | KPI Green | Q4 2027 | Phase V
[24 empty] | 184 | KPS-III |  | 216 | Phase - III | AESL PPA (C&I) - Solar | S5 | PSS-10 | 159 | KPS-3 | SRPL |  |  | 250 | 237.5 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | ARE56L | PPA | S6-B |  | PSS-10 | China | HSAT | 2025-11-05 | 2025-06-30 | REC 3 |  | Q1 2026
[24 empty] | 185 | KPS-III |  |  | Phase - III | AESL PPA (C&I) - Solar | S5 | PSS-10 | 160 | KPS-3 | SRPL |  |  |  | 12.5 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | ARE56L | PPA | S6-B |  | PSS-10 | China | HSAT | 2025-11-05 | 2025-08-31 | REC 3 |  | Q2 2026 | Phase IV
[24 empty] | 186 | KPS-III |  |  | Phase - III | AGEL Hybrid Merchant (Wind) | S5, S6, A10, S4 | PSS-10 | 161 | KPS-3 | SRPL |  |  | 250 | 175 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | ARE56L | PPA | S6-B |  | PSS-10 | China | HSAT | 2025-11-05 | 2025-08-31 | REC 3 |  | Q2 2026 | Phase IV
[24 empty] | 187 | KPS-III |  |  | Phase - III | AGEL Hybrid Merchant (Wind) | S5, S6, A10, S4 | PSS-10 | 162 | KPS-3 | SRPL |  |  |  | 75 | 0 | Phase III | 2027-01-31 | MLP T3 PPA - AP |  | ARE56L | PPA | S6-B |  | PSS-10 | China | HSAT | 2025-11-05 | 2025-12-31 | REC 3 |  | Q3 2026 | Phase IV
[24 empty] | 188 | KPS-III |  |  | Phase - III | AGEL Hybrid Merchant (Wind) | S5, S6, A10, S4 | PSS-10 | 163 | KPS-3 | SRPL |  |  | 150 | 75 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | AGE26BL | Merchant | S5 | S5b | PSS-10 | ALMM | HSAT | - | 2026-03-31 | REC 2 |  | Q4 2026 | Phase IV
[24 empty] | 189 | KPS-III |  | 150 | Phase - III | AGEL Merchant (Solar) | S5 | PSS-10 | 164 | KPS-3 | SRPL |  |  |  | 75 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | AGE26BL | Merchant | S5 | S5b | PSS-10 | ALMM | HSAT | - | 2026-01-31 | REC 2 |  | Q4 2026
[24 empty] | 190 | KPS-III |  |  | Phase - III | AGEL Merchant (Solar) | S5 | PSS-10 | 165 | KPS-3 | SRPL |  |  | 216 | 50 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Solar | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | AGE26BL | PPA | S5 | S5b | PSS-10 | ALMM | HSAT | - | 2025-09-30 | REC 2 |  | Q2 2026
[24 empty] | 191 | [7 empty] | 166 | KPS-3 | SRPL |  |  |  | 92 | 0 | Phase III | 2027-01-31 | AESL PPA (C&I) - Solar | AGE26BL_S05_HSAT_292MW_MERCHANT_HYBRID_Commissioned | AGE26BL | PPA | S5 | S5b | PSS-10 | ALMM | HSAT | - | 2026-03-31 | REC 2 |  | Q4 2026 | Phase III
[24 empty] | 192 | KPS-III | 1250 | 150 | Phase - IV | MSEDCL PPA Ph-3 | S3 | PSS-11 | 167 | KPS-3 | SRPL |  |  |  | 0 | 119.6 | Phase III | 2027-01-31 | AGEL Hybrid Merchant (Wind) |  | AGE26BL | Merchant | S5, S6, A10, S4 |  | PSS-10 |  | - | - | 2025-06-30 | REC 2 |  | Q1 2026 | Phase III
[24 empty] | 193 | KPS-III |  | 150 | Phase - IV | MSEDCL PPA Ph-3 | S3 | PSS-11 | 168 | KPS-3 | SRPL |  |  |  | 0 | 26 | Phase III | 2027-01-31 | AGEL Hybrid Merchant (Wind) |  | AGE26BL | Merchant | S5, S6, A10, S4 |  | PSS-10 |  | - | - | 2025-07-31 | REC 2 |  | Q2 2026 | Phase III
[24 empty] | 194 | KPS-III |  | 200 | Phase - IV | MSEDCL PPA Ph-3 | S3 | PSS-11 | 169 | KPS-3 | SRPL |  |  |  | 0 | 10.4 | Phase III | 2027-01-31 | AGEL Hybrid Merchant (Wind) |  | AGE26BL | Merchant | S5, S6, A10, S4 |  | PSS-10 |  | - | - | 2026-03-31 | REC 2 |  | Q4 2026 | Phase III
[24 empty] | 195 | KPS-III |  | 150 | Phase - IV | AGEL Merchant (Solar) - TTE | S3 | PSS-11 | 170 | KPS-3 | SRPL |  |  | 150 | 50 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L_S05_HSAT_150MW_MERCHANT | AGE24L | Merchant | S5 | S5a | PSS-10 | ALMM | HSAT | - | 2026-01-31 | NABFID |  | Q4 2026 | Phase III
[24 empty] | 196 | KPS-III |  | 185 | Phase - IV | AGEL Merchant (Wind) | S2, S3, S4, A11, A12 | PSS-11 | 171 | KPS-3 | SRPL |  |  |  | 50 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L_S05_HSAT_150MW_MERCHANT | AGE24L | Merchant | S5 | S5a | PSS-10 | ALMM | HSAT | - | 2026-03-31 | NABFID |  | Q4 2026 | Phase III
[24 empty] | 197 | KPS-III |  |  | Phase - IV | AGEL Merchant (Wind) | S2, S3, S4, A11, A12 | PSS-11 | 172 | KPS-3 | SRPL |  |  |  | 50 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L_S05_HSAT_150MW_MERCHANT | AGE24L | Merchant | S5 | S5a | PSS-10 | ALMM | HSAT | - | 2026-04-30 | NABFID |  | Q1 2027 | Phase III
[24 empty] | 198 | KPS-III |  |  | Phase - IV | AGEL Merchant (Wind) | S2, S3, S4, A11, A12 | PSS-11
[24 empty] | 199 | KPS-III |  | 300 | Phase - IV | AGEL Merchant (Solar) | S4 | PSS-11 | 173 | KPS-3 | SRPL | 400kV | 1250 | 150 | 150 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 | ARE55L_S03_HSAT_500MW_MERCHANT | ARE55L | PPA | S3 |  | PSS-11 | ALMM | HSAT | 2027-04-29 | 2027-05-31 | Unallocated | Bondada | Q1 2028 | Phase III
[24 empty] | 200 | KPS-III |  |  | Phase - IV | AGEL Merchant (Solar) | S4 | PSS-11 | 174 | KPS-3 | SRPL |  |  | 150 | 150 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 | ARE55L_S03_HSAT_500MW_MERCHANT | ARE55L | PPA | S3 |  | PSS-11 | ALMM | HSAT | 2027-04-29 | 2027-04-30 | Unallocated | Bondada | Q1 2028 | Phase III
[24 empty] | 201 | KPS-III |  |  | Phase - IV | AGEL Merchant (Solar) | S4 | PSS-11 | 175 | KPS-3 | SRPL |  |  | 200 | 200 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 | ARE55L_S03_HSAT_500MW_MERCHANT | ARE55L | PPA | S3 |  | PSS-11 | ALMM | HSAT | 2027-04-29 | 2027-05-31 | Unallocated | Bondada | Q1 2028 | Phase III
[24 empty] | 202 | KPS-III |  | 115 | Phase - IV | AGEL Merchant (Solar) - TTE | S4a | PSS-11 | 176 | KPS-3 | SRPL |  |  | 150 | 150 | 0 | Phase IV | 2028-01-01 | AGEL Merchant (Solar) - TTE | AE2L_S03_HSAT_150MW_MERCHANT | AE2L | Merchant | S3 | S03 | PSS-11 | ALCM | HSAT |  | 2027-09-30 | BOB | Bondada | Q2 2028 | Phase III
[24 empty] | 203 | [7 empty] | 177 | KPS-3 | SRPL |  |  | 185 | 0 | 104 | Phase IV | 2028-01-01 | AGEL Merchant (Wind) | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | AGE25CL | Merchant | S2, S3, S4, A11, A12 |  | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026
[24 empty] | 204 | KPS-III | 1100 | 300 | Phase - III | MSEDCL PPA Ph-1 | S1 | PSS-12 | 178 | KPS-3 | SRPL |  |  |  | 0 | 52 | Phase IV | 2028-01-01 | AGEL Merchant (Wind) | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | AGE25CL | Merchant | S2, S3, S4, A11, A12 |  | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026 | Phase III
[24 empty] | 205 | KPS-III |  |  | Phase - III | MSEDCL PPA Ph-2 | S1 | PSS-12 | 179 | KPS-3 | SRPL |  |  |  | 0 | 31.2 | Phase IV | 2028-01-01 | AGEL Merchant (Wind) | AGE25CL PSS-11 (36 Loc.) & PSS-14 (13 Loc.) | AGE25CL | Merchant | S2, S3, S4, A11, A12 |  | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026 | Phase III
[24 empty] | 206 | KPS-III |  | 75 | Phase - III | AGEL Merchant (Solar) - TTE | S1 | PSS-12 | 180 | KPS-3 | SRPL |  |  | 300 | 100 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | S4 |  | PSS-11 | ALMM | HSAT | - | 2027-10-31 | SBI | KPI Green | Q3 2028 | Phase III
[24 empty] | 207 | KPS-III |  | 112.5 | Phase - III | MSEDCL PPA Ph-3 | S2b | PSS-12 | 181 | KPS-3 | SRPL |  |  |  | 150 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | S4 |  | PSS-11 | ALMM | HSAT | - | 2027-11-30 | SBI | KPI Green | Q3 2028 | Phase III
[24 empty] | 208 | KPS-III |  | 175 | Phase - III | MSEDCL PPA Ph-1 | S2a | PSS-12 | 182 | KPS-3 | SRPL |  |  |  | 50 | 0 | Phase IV | 2028-01-01 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | S4 |  | PSS-11 | ALMM | HSAT | - | 2027-10-31 | SBI | KPI Green | Q3 2028 | Phase III
[24 empty] | 209 | KPS-III |  | 50 | Phase - III | MSEDCL PPA Ph-2 | S2a | PSS-12 | 183 | KPS-3 | SRPL |  |  | 115 | 115 | 0 | Phase IV | 2028-01-01 | AGEL Merchant (Solar) - TTE |  | AE3L | Merchant | S4a |  | PSS-11 | ALCM | HSAT |  | 2027-09-30 | BOB | KPI Green | Q2 2028 | Phase III
[24 empty] | 210 | KPS-III |  | 150 | Phase - III | MSEDCL PPA Ph-2 | S2a | PSS-12
[24 empty] | 211 | KPS-III |  | 100 | Phase - III | MSEDCL PPA Ph-3 | S2a | PSS-12 | 184 | KPS-3 | SRPL | 400kV | 1100 | 300 | 100 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-1 | AGEL_S1_100_MW_HSAT | ARE55L | PPA | S1 | S01 | PSS-12 | ALMM | HSAT | 2026-04-29 | 2027-01-31 | Unallocated | L&T | Q4 2027 | Phase III
[24 empty] | 212 | KPS-III |  | 137.5 | Phase - III | AGEL Merchant (Wind) | S1, S2, S9, S10 | PSS-12 | 185 | KPS-3 | SRPL |  |  |  | 200 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-2 | AGEL_S1_200_MW_HSAT | ARE55L | PPA | S1 | S01 | PSS-12 | ALMM | HSAT | 2026-10-29 | 2027-02-28 | Unallocated | L&T | Q4 2027 | Phase III
[24 empty] | 213 | KPS-III |  |  | Phase - III | AGEL Merchant (Wind) | S1, S2, S9, S10 | PSS-12 | 186 | KPS-3 | SRPL |  |  | 75 | 75 | 0 | Phase III | 2027-01-31 | AGEL Merchant (Solar) - TTE | AGEL_S1_75_MW_HSAT | AE3L | PPA | S1 | S01 | PSS-12 | ALCM | HSAT |  | 2027-03-31 | BOB | L&T | Q4 2027 | Phase III
[32 empty] | 187 | KPS-3 | SRPL |  |  | 112.5 | 112.5 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-3 | AGEL_S2B_112.5_MW_HSAT | ARE55L | PPA | S2b | S02b | PSS-12 | ALMM | HSAT | 2027-04-29 | 2026-12-31 | Unallocated | L&T | Q3 2027 | Phase III
[26 empty] | 4750 | 4750 |  |  |  |  | 188 | KPS-3 | SRPL |  |  | 175 | 75 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-1 | AGEL_S2A_175_MW_HSAT | ARE55L | PPA | S2a | S02a | PSS-12 | ALMM | HSAT | 2026-04-29 | 2026-12-31 | Unallocated | L&T | Q3 2027 | Phase III
[32 empty] | 189 | KPS-3 | SRPL |  |  |  | 100 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-1 | AGEL_S2A_175_MW_HSAT | ARE55L | PPA | S2a | S02a | PSS-12 | ALMM | HSAT | 2026-04-29 | 2027-02-28 | Unallocated | L&T | Q4 2027 | Phase III
[32 empty] | 190 | KPS-3 | SRPL |  |  | 50 | 50 | 0 | Phase III | 2027-01-31 | MSEDCL PPA Ph-2 | AGEL_S2A_50_MW_HSAT | ARE55L | PPA | S2a | S02a | PSS-12 | ALMM | HSAT | 2026-10-29 | 2026-12-31 | Unallocated | L&T | Q3 2027 | Phase III
[32 empty] | 191 | KPS-3 | SRPL |  |  | 150 | 150 |  | Phase III | 2027-01-31 | MSEDCL PPA Ph-2 |  | ARE55L | PPA | S2a |  | PSS-12 | ALMM | HSAT | 2026-10-29 | 2027-04-30 | Unallocated | KPI Green | Q1 2028 | Phase III
[32 empty] | 192 | KPS-3 | SRPL |  |  | 100 | 100 |  | Phase III | 2027-01-31 | MSEDCL PPA Ph-3 |  | ARE55L | PPA | S2a |  | PSS-12 | ALMM | HSAT | 2027-04-29 | 2027-04-30 | Unallocated | KPI Green | Q1 2028 | Phase III
[32 empty] | 193 | KPS-3 | SRPL |  |  | 138 | 0 | 52 | Phase III | 2027-01-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | S1, S2, S9, S10 |  | PSS-12 | - | - | - | 2026-03-31 | PFC -3 |  | Q4 2026 | Phase III
[32 empty] | 194 | KPS-3 | SRPL |  |  |  | 0 | 88.4 | Phase III | 2027-01-31 | AGEL Merchant (Wind) | AGE26AL PSS-12 (27 Loc.) & PSS-14 (60 Loc.) | AGE26AL | Merchant | S1, S2, S9, S10 |  | PSS-12 | - | - | - | 2026-03-31 | PFC -3 |  | Q4 2026
[36 empty] | 4750 | 4750 | 4303.5 | 634.4
APL PARK
[32 empty] | 195 | KPS-4 | APL |  | 1875 | 250 | 0 | 119.6 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) | AGE25CL PSS-18 (49 Loc.) - Phase-4 | AGE25CL | Merchant |  |  | PSS-18 | - | - | - | 2027-01-31 | REC |  | Q4 2027 | Phase IV
[32 empty] | 196 | KPS-4 | APL |  |  |  | 0 | 135.2 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) | AGE25CL PSS-18 (49 Loc.) - Phase-4 | AGE25CL | Merchant |  |  | PSS-18 | - | - | - | 2027-03-31 | REC |  | Q4 2027 | Phase IV
[32 empty] | 197 | KPS-4 | APL |  |  |  | 112.5 | 0 | Phase VI | 2029-09-30 | Group - Copper (Solar) |  | KCL | Group |  |  | PSS-18 | ALCM | TBD |  | 2028-03-31 |  |  | Q4 2028 | Phase IV
[32 empty] | 198 | KPS-4 | APL |  | 1250 | 1250 | 0 | 130 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) |  | TBD | Merchant |  |  | PSS-20 | - | - |  | 2028-03-31 | Unallocated |  | Q4 2028 | Phase IV
[32 empty] | 199 | KPS-4 | APL |  |  |  | 0 | 260 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) |  | TBD | Merchant |  |  | PSS-20 | - | - |  | 2028-03-31 | Unallocated |  | Q4 2028 | Phase IV
[32 empty] | 200 | KPS-5 | APL |  | 1250 | 1250 | 0 | 130 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) |  | TBD | Merchant |  |  | PSS-15 | TBD | TBD |  | 2027-12-31 | Unallocated |  | Q3 2028 | Phase IV
[32 empty] | 201 | KPS-5 | APL |  |  |  |  | 182 | Phase VI | 2029-09-30 | AGEL Merchant (Wind) |  | TBD | Merchant |  |  | PSS-15 | TBD | TBD |  | 2028-03-31 | Unallocated |  | Q4 2028 | Phase IV
[36 empty] | 4375 | 2750 | 112.5 | 956.8
[32 empty] | 202 | KPS-2 |  |  |  | 1000 |  |  | Phase IV |  | Gujrat State Electricity Corporate Ltd. | [13 empty] | Phase IV
[32 empty] | 203 | KPS-2 |  |  |  | 600 |  |  | Phase IV |  | Gujrat State Electricity Corporate Ltd. | [13 empty] | Phase IV
[32 empty] | 204 | KPS-2 |  |  |  | 364 |  |  | Phase IV |  | Gujrat State Electricity Corporate Ltd. | [13 empty] | Phase IV
[32 empty] | 205 | KPS-2 |  |  |  | 600 |  |  | Phase IV |  | Gujrat Industries Power Company Ltd. | [13 empty] | Phase IV
[32 empty] | 206 | KPS-2 |  |  |  | 600 |  |  |  |  | Gujrat Industries Power Company Ltd.
[32 empty] | 207 | KPS-2 |  |  |  | 1995 |  |  | Phase III |  | NTPC REL | [13 empty] | Phase III
[32 empty] | 208 | KPS-2 |  |  |  | 365 |  |  | Phase III |  | NTPC REL | [13 empty] | Phase III
[32 empty] | 209 | KPS-2 |  |  |  | 890 |  |  | Phase III |  | NTPC REL | [13 empty] | Phase III
[32 empty] | 210 | KPS-2 |  |  |  | 300 |  |  | Phase III |  | NTPC REL | [13 empty] | Phase III
[32 empty] | 211 | KPS-2 |  |  |  | 1361 |  |  | Phase III |  | Gujrat State Electricity Corporate Ltd. | [13 empty] | Phase III
[32 empty] | 212 | KPS-2 |  |  |  | 1175 |  |  | Phase III |  | Gujrat Industries Power Corporation Ltd. | [13 empty] | Phase III
[36 empty] | 0 | 9250 | 0 | 0

## _agel_meta (hidden)
{"schema":1,"banner_rows":0,"sheet":"Sheet1","tables":[{"name":"Name of Work","name_col":2,"row_labels":{"6":"Bhuj-I \u2192 Kps-I","7":"Bhuj-I \u2192 Kps-I","8":"Bhuj-I \u2192 Kps-I","9":"Lilo Pirana (PG) \u2192 Pirana (T)","10":"Lilo Pirana (PG) \u2192 Pirana (T)","11":"Lilo Pirana (PG) \u2192 Pirana (T)","12":"Boisar-II (GIS) \u2192 South Olpad (GIS)","13":"Boisar-II (GIS) \u2192 South Olpad (GIS)","14":"Boisar-II (GIS) \u2192 South Olpad (GIS)","15":"Ahmedabad \u2192 South Olpad (GIS)","16":"Ahmedabad \u2192 South Olpad (GIS)","17":"Ahmedabad \u2192 South Olpad (GIS)","18":"Ghandhar \u2192 Hazira","19":"Ghandhar \u2192 Hazira","20":"Ghandhar \u2192 Hazira","21":"Vadodara \u2192 South Olpad (GIS)","22":"Vadodara \u2192 South Olpad (GIS)","23":"Vadodara \u2192 South Olpad (GIS)","24":"Kps-II (HVDC) \u2192 Nagpur (HVDC)","25":"Kps-II (HVDC) \u2192 Nagpur (HVDC)","26":"Kps-II (HVDC) \u2192 Nagpur (HVDC)","27":"Vataman \u2192 Navsari (NEW)","28":"Vataman \u2192 Navsari (NEW)","29":"Vataman \u2192 Navsari (NEW)","30":"Kps-III \u2192 Kps-II","31":"Kps-III \u2192 Kps-II","32":"Kps-III \u2192 Kps-II","33":"Halvad \u2192 Vataman","34":"Halvad \u2192 Vataman","35":"Halvad \u2192 Vataman","36":"Kps-III (HVDC) \u2192 South Olpad","37":"Kps-III (HVDC) \u2192 South Olpad","38":"Kps-III (HVDC) \u2192 South Olpad","39":"Ahmedabad \u2192 Navsari (NEW)","40":"Ahmedabad \u2192 Navsari (NEW)","41":"Ahmedabad \u2192 Navsari (NEW)","42":"Banaskantha \u2192 Ahmedabad","43":"Banaskantha \u2192 Ahmedabad","44":"Banaskantha \u2192 Ahmedabad","45":"Babhaleswar \u2192 Padghe (M)","46":"Babhaleswar \u2192 Padghe (M)","47":"Babhaleswar \u2192 Padghe (M)","48":"Boisar-II (GIS) \u2192 Velgaon (MH)","49":"Boisar-II (GIS) \u2192 Velgaon (MH)","50":"Boisar-II (GIS) \u2192 Velgaon (MH)","51":"Lakadia \u2192 Ahmedabad","52":"Lakadia \u2192 Ahmedabad","53":"Lakadia \u2192 Ahmedabad","54":"Kps-I \u2192 Kps-II","55":"Kps-I \u2192 Kps-II","56":"Kps-I \u2192 Kps-II","57":"Bhuj-I \u2192 Kps-I","58":"Bhuj-I \u2192 Kps-I","59":"Bhuj-I \u2192 Kps-I","60":"Kps-III \u2192 Lakadia","61":"Kps-III \u2192 Lakadia","62":"Kps-III \u2192 Lakadia","63":"Boisar-II (GIS) \u2192 Pune-III (GIS)","64":"Boisar-II (GIS) \u2192 Pune-III (GIS)","65":"Boisar-II (GIS) \u2192 Pune-III (GIS)","66":"Narendra (NEW) \u2192 Pune (GIS)","67":"Narendra (NEW) \u2192 Pune (GIS)","68":"Narendra (NEW) \u2192 Pune (GIS)","69":"Kps-II \u2192 Lakadia","70":"Kps-II \u2192 Lakadia","71":"Kps-II \u2192 Lakadia","72":"Lakadia \u2192 Vadodara","73":"Lakadia \u2192 Vadodara","74":"Lakadia \u2192 Vadodara","75":"Kps-II \u2192 Halvad","76":"Kps-II \u2192 Halvad","77":"Kps-II \u2192 Halvad","78":"Navsari (NEW) \u2192 Padghe (PG)","79":"Navsari (NEW) \u2192 Padghe (PG)","80":"Navsari (NEW) \u2192 Padghe (PG)","81":"Hinjewadi \u2192 Koyna","82":"Hinjewadi \u2192 Koyna","83":"Hinjewadi \u2192 Koyna","84":"Nagpur (HVDC) \u2192 Nagpur","85":"Nagpur (HVDC) \u2192 Nagpur","86":"Nagpur (HVDC) \u2192 Nagpur","87":"Kps-III (HVDC) \u2192 Kps-III","88":"Kps-III (HVDC) \u2192 Kps-III","89":"Kps-III (HVDC) \u2192 Kps-III","90":"South Olpad \u2192 South Olpad (GIS)","91":"South Olpad \u2192 South Olpad (GIS)","92":"South Olpad \u2192 South Olpad (GIS)","93":"Wardha \u2192 Raipur","94":"Wardha \u2192 Raipur","95":"Wardha \u2192 Raipur","96":"Kps-II (HVDC) \u2192 Kps-II","97":"Kps-II (HVDC) \u2192 Kps-II","98":"Kps-II (HVDC) \u2192 Kps-II","99":"Lakadia \u2192 Vadodara","100":"Lakadia \u2192 Vadodara","101":"Lakadia \u2192 Vadodara","102":"Wardha \u2192 Raipur","103":"Wardha \u2192 Raipur","104":"Wardha \u2192 Raipur","105":"Hinjewadi \u2192 Koyna","106":"Hinjewadi \u2192 Koyna","107":"Hinjewadi \u2192 Koyna"},"header_row":5,"first_data_row":6,"last_data_row":107,"appended":null,"injected":[{"label":"Voltage","col":3},{"label":"HVDC Lines","col":12},{"label":"LILO Lines","col":13},{"label":"LILO Line Substation","col":14}]},{"name":"Transmission Line","name_col":17,"row_labels":{"6":"Bhuj-I \u2192 Kps-I","7":"Lilo Pirana (PG) \u2192 Pirana (T)","8":"Kps-III \u2192 Kps-II","9":"Ahmedabad \u2192 Navsari (NEW)","10":"Banaskantha \u2192 Ahmedabad","11":"Lakadia \u2192 Ahmedabad","12":"Kps-I \u2192 Kps-II","13":"Kps-II \u2192 Lakadia","14":"Vataman \u2192 Navsari (NEW)","15":"Lakadia \u2192 Vadodara","16":"Halvad \u2192 Vataman","17":"Kps-II \u2192 Halvad","18":"Navsari (NEW) \u2192 Padghe (PG)","19":"Babhaleswar \u2192 Padghe (M)","20":"Boisar-II (GIS) \u2192 Velgaon (MH)","21":"Bhuj-I \u2192 Kps-I","22":"Kps-III \u2192 Lakadia","23":"Boisar-II (GIS) \u2192 Pune-III (GIS)","24":"Narendra (NEW) \u2192 Pune (GIS)","25":"Hinjewadi \u2192 Koyna","26":"Boisar-II (GIS) \u2192 South Olpad (GIS)","27":"Ahmedabad \u2192 South Olpad (GIS)","28":"Ghandhar \u2192 Hazira","29":"Vadodara \u2192 South Olpad (GIS)","30":"Nagpur (HVDC) \u2192 Nagpur","31":"Kps-III (HVDC) \u2192 Kps-III","32":"South Olpad \u2192 South Olpad (GIS)","33":"Kps-III (HVDC) \u2192 South Olpad","34":"Wardha \u2192 Raipur","35":"Kps-II (HVDC) \u2192 Nagpur (HVDC)","36":"Kps-II (HVDC) \u2192 Kps-II","37":"Lakadia \u2192 Vadodara","38":"Wardha \u2192 Raipur","39":"Hinjewadi \u2192 Koyna"},"header_row":5,"first_data_row":6,"last_data_row":39,"appended":null,"injected":[{"label":"Others","col":18}]},{"name":"Substations","name_col":17,"row_labels":{"41":"Bhuj-I","42":"Kps-I","43":"Lilo Pirana (PG)","44":"Pirana (T)","45":"Ahmedabad","46":"Kps-III","47":"Kps-II","48":"Navsari (NEW)","49":"Banaskantha","50":"Lakadia","51":"Halvad","52":"Vataman","53":"Vadodara","54":"Padghe (PG)","55":"Boisar-II (GIS)","56":"Babhaleswar","57":"Padghe (M)","58":"Velgaon (MH)","59":"Pune-III (GIS)","60":"Narendra (NEW)","61":"Pune (GIS)","62":"Hinjewadi","63":"Koyna","64":"South Olpad (GIS)","65":"Ghandhar","66":"Hazira","67":"Nagpur (HVDC)","68":"Nagpur","69":"Kps-III (HVDC)","70":"South Olpad","71":"Wardha","72":"Raipur","73":"Kps-II (HVDC)"},"header_row":40,"first_data_row":41,"last_data_row":73,"appended":null,"injected":[{"label":"Others","col":18},{"label":"Expected Date","col":25}]},{"name":"Project Blocks","name_col":null,"row_labels":{},"header_row":6,"first_data_row":8,"last_data_row":253,"appended":null,"injected":[]},{"name":"Substation Coordinates","name_col":69,"row_labels":{"6":"Padghe (GIS)","7":"Padghe (PG)","8":"Pirana (PG)","9":"Pirana (T)","10":"Pirana PGCIL","11":"South Olpad (GIS)","12":"Lakadia","13":"Halvad","14":"Boisar-II (Sec-II)","15":"Boisar-II - Pune-III","16":"KHAVDA-I PS","17":"KHAVDA-II PS","18":"KHAVDA-III PS","19":"BHUJ-I","20":"Pune (GIS)","21":"Banaskantha","22":"Ramgarh","23":"Bhadla-3","24":"Fatehgarh-III","25":"Sikar-II","26":"Khetri 765 kV","27":"Narela 765 kV","28":"Jhatikara","29":"Bikaner-III","30":"Mandsaur","31":"Indore","32":"Jam Khambhaliya (GIS) PS","33":"Bhuj PS","34":"Bhuj-II PS","35":"Bhachau","36":"Khavda PS-I","37":"Khavda PS-II","38":"Khavda PS-III","39":"Banaskantha (Radhanesda) PS [GIS]","40":"Raghanesda","41":"Rajgarh (PG)","42":"Indore (PG)","43":"Pachora PS","44":"Neemuch PS","45":"Khandwa S/s (PG)","46":"Raipur S/s (PG)","47":"Kallam PS","48":"Parli (PG)","49":"Solapur (PG)","50":"Solapur PS","51":"Dhule PS","52":"Mandsaur PS","53":"Ishanagar","54":"Morena PS","55":"Tuticorin-II","56":"Pugalur","57":"Palakkad","58":"Pavagada","59":"Hiriyur","60":"Kurnool(new)","61":"Koppal","62":"Karur","63":"Gadag","64":"Koppal-II PS","65":"Gadag-II PS","66":"Kurnool-III PS","67":"Ananthapuram PS","68":"Bidar PS","69":"Davanagere/Chitradurga PS","70":"Bellary PS","71":"Bijapur PS","72":"Tumkur-II PS","73":"Ananthapuram-II PS","74":"Bhadla PS","75":"Bikaner","76":"Fatehgarh PS","77":"Bhadla-II PS","78":"Fatehgarh-III PS","79":"Bikaner-II PS","80":"Fatehgarh-IV PS","81":"Bhadla-III PS","82":"Ramgarh PS","83":"Bikaner-III PS","84":"Bikaner-IV PS","85":"Sirohi","86":"KPS-I","87":"KPS-II","88":"KPS-III","89":"Raipur","90":"Raipur 765 kV","91":"KPS-III (HVDC)","92":"KPS-II (HVDC)","93":"South Olpad (HVDC)","94":"Ramgarh (HVDC)"},"header_row":5,"first_data_row":6,"last_data_row":94,"appended":null,"injected":[]}]}