## Khavda
Khavda Park - Project Allocation (04 Sep 2026)
# | KPS
|  |  | Voltage | Connectivity MW | Connectivity Breakup | Solar | Wind | Connectivity Phase | Likey start date of connectivity | Project | SPV | Block | PSS | Module | MMS | SCOD | ECOD | Financing | EPC Partner | Qtr
AGEL PARK
1 | KPS-1 | AGEL | 400kV | 1000 | 50 | 50 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - J&K | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-01-21 | 2026-01-31 | PFC -3 |  | Q4 2026
| KPS-1 | AGEL |  |  | 200 | 50 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026
| KPS-1 | AGEL |  |  |  | 100 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026
| KPS-1 | AGEL |  |  |  | 50 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - CG | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027
| KPS-1 | AGEL | 400kV |  | 167 | 100 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - TN | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026
| KPS-1 | AGEL |  |  |  | 67 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - TN | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027
| KPS-1 | AGEL |  |  | 333 | 158 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - OR | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-03-31 | PFC -3 |  | Q4 2026
| KPS-1 | AGEL |  |  |  | 175 | 0 | Phase - I | 2024-02-18 | MLP T1 PPA - OR | AGE26AL | A16 | PSS-06 | SEA | FT | 2026-04-20 | 2026-04-30 | PFC -3 |  | Q1 2027
| KPS-1 | AGEL |  |  | 250 | 125 | 0 | Phase - I | 2024-02-18 | MLP T4 PPA - AP | AGE26BL | A3 | PSS-06 | China | HSAT | 2027-03-07 | 2027-01-31 | REC | Bondada | Q4 2027
| KPS-1 | AGEL |  |  |  | 125 | 0 | Phase - I | 2024-02-18 | MLP T4 PPA - AP | AGE26BL | A3 | PSS-06 | China | HSAT | 2027-03-07 | 2027-02-28 | REC | Bondada | Q4 2027
2 | KPS-1 | AGEL |  | 417 | 250 | 125 | 0 | Phase - II | 2026-10-31 | MLP T4 PPA - AP | AGE24L | A3 | PSS-06 | China | HSAT | 2027-03-07 | 2026-12-31 | Canara | Hild | Q3 2027
| KPS-1 | AGEL |  |  |  | 125 | 0 | Phase - II | 2026-10-31 | MLP T4 PPA - AP | AGE24L | A3 | PSS-06 | China | HSAT | 2027-03-07 | 2027-01-31 | Canara | Hild | Q4 2027
| KPS-1 | AGEL |  |  | 100 | 100 | 0 | Phase - II | 2026-10-31 | MLP T4 PPA - AP | AGE26BL | A4 | PSS-02 | China | HSAT | 2026-11-05 | 2024-03-31 | REC 1 (REC 2) |  | Q4 2024
| KPS-1 | AGEL |  |  | 67 | 67 | 0 | Phase - II | 2026-10-31 | MLP T4 PPA - AP | AGE26BL | A4/A7 | PSS-02 | China | HSAT | 2026-11-05 | 2025-02-24 | REC 1 (REC 2) |  | Q4 2025
3 | KPS-1 | AGEL |  | 1083 | 250 | 225 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | AGE25AL | A7 | PSS-02 | China | HSAT | 2025-11-05 | 2024-03-31 | EM 3 |  | Q4 2024
| KPS-1 | AGEL |  |  |  | 25 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | AGE25AL | A7 | PSS-02 | China | HSAT | 2025-11-05 | 2025-02-28 | EM 3 |  | Q4 2025
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | AGE25AL | A7 | PSS-02 | China | HSAT | 2025-11-05 | 2025-02-28 | EM 3 |  | Q4 2025
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | AGE25BL | A4 | PSS-02 | China | HSAT | 2025-11-05 | 2023-12-31 | PFC 1 |  | Q3 2024
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | AGE25BL | A4 | PSS-02 | China | HSAT | 2025-11-05 | 2023-12-31 | PFC 1 |  | Q3 2024
| KPS-1 | AGEL |  |  | 83 | 83 | 0 | Phase - III | 2027-01-31 | MLP PPA - AP New | AGE25BL | A7 | PSS-02 | China | HSAT | 2026-10-01 | 2025-03-01 | PFC 1 |  | Q4 2025
4 | KPS-1 | AGEL | 400kV | 1000 | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T2 PPA - AP | AGE24AL | A5 | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | REC 1 |  | Q3 2024
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T2 PPA - AP | AGE24AL | A5 | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | REC 1 |  | Q3 2024
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T2 PPA - AP | AGE24BL | A8 | PSS-01 | China | HSAT | 2024-11-05 | 2023-12-31 | EM 3 |  | Q3 2024
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - III | 2027-01-31 | MLP T2 PPA - AP | AGE24BL | A8 | PSS-01 | China | HSAT | 2024-11-05 | 2024-01-31 | EM 3 |  | Q4 2024
5 | KPS-1 | AGEL | 400kV | 1000 | 600 | 295 | 0 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13 | PSS-05 | China | FT | LTA | 2025-06-30 | SBI |  | Q1 2026
| KPS-1 | AGEL |  |  |  | 50 | - | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13 | PSS-05 | China | FT | LTA | 2025-08-31 | SBI |  | Q2 2026
| KPS-1 | AGEL |  |  |  | 75 | 0 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13 | PSS-05 | China | FT | LTA | 2025-09-01 | SBI |  | Q2 2026
| KPS-1 | AGEL |  |  |  | 75 | 0 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13 | PSS-05 | China | FT | LTA | 2025-10-16 | SBI |  | Q3 2026
| KPS-1 | AGEL |  |  |  | 75 | 0 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13 | PSS-05 | China | FT | LTA | 2025-11-30 | SBI |  | Q3 2026
| KPS-1 | AGEL |  |  |  | 0 | 182 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13, A14, A17 | PSS-05 | - | - | LTA | 2025-11-30 | SBI |  | Q3 2026
| KPS-1 | AGEL |  |  |  | 0 | 20.8 | Phase - II | 2026-02-28 | SECI H-3 PPA | AHEJ5L | A13, A14, A17 | PSS-05 | - | - | LTA | 2026-03-31 | SBI |  | Q4 2026
| KPS-1 | AGEL |  |  | 250 | 175 | 0 | Phase - II | 2026-02-28 | AGEL Merchant - TTE IM2 (Solar) | ARE45L | A14 | PSS-05 | ALMM | HSAT | - | 2025-06-30 | SM 2 |  | Q1 2026
| KPS-1 | AGEL |  |  |  | 75 | 0 | Phase - II | 2026-02-28 | AGEL Merchant - TTE IM2 (Solar) | ARE45L | A14 | PSS-05 | ALMM | HSAT | - | 2025-08-31 | SM 2 |  | Q2 2026
| KPS-1 | AGEL |  |  | 150 | 75 | - | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | AGE24L | A14 | PSS-05 | ALMM | HSAT | - | 2026-02-12 | NABFID |  | Q4 2026
| KPS-1 | AGEL |  |  |  | 75 | - | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | AGE24L | A14 | PSS-05 | ALMM | HSAT | - | 2026-03-31 | NABFID |  | Q4 2026
6 | KPS-1 | AGEL |  | 650 | 134 | 134 | 0 | Phase - V | 2029-12-31 | AGEL Merchant (Solar) - TTE | ARE64LS2REL | A17 | PSS-05 | ALCM | TBD | - | 2027-06-30 | Unallocated |  | Q1 2028
| KPS-1 | AGEL |  |  | 250 | 250 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE55L TBD | A17 | PSS-05 | China | TBD | LTA+15 Days | 2027-06-30 | Unallocated |  | Q1 2028
| KPS-1 | AGEL |  |  | 67 | 67 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE55L TBD | A17 | PSS-05 | China | TBD | LTA+15 Days | 2027-06-30 | Unallocated |  | Q1 2028
| KPS-1 | AGEL |  |  | 100 | 100 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE55L TBD | A17 | PSS-05 | China | TBD | LTA+15 Days | 2027-06-30 | Unallocated |  | Q1 2028
| KPS-1 | AGEL |  |  | 99 | 99 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE55L TBD | A17 | PSS-05 | China | TBD | LTA+15 Days | 2027-06-30 | Unallocated |  | Q1 2028
7 | KPS-1 | AGEL | 400kV | 1000 | 225 | 175 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | ARE56L | A2 | PSS-04 | ALMM | HSAT | - | 2025-03-29 | REC 3 |  | Q4 2025
| KPS-1 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | ARE56L | A2 | PSS-04 | ALMM | HSAT | - | 2025-05-14 | REC 3 |  | Q1 2026
| KPS-1 | AGEL |  |  | 50 | 0 | 52 | Phase - II | 2026-02-28 | AESL PPA (C&I) - Wind - RSWM | ARE41L | A16, NHPC, A1,A3 | PSS-04 | - | - | - | 2025-03-31 | PFC |  | Q4 2025
| KPS-1 | AGEL |  |  |  | 25 | 0 | Phase - II | 2026-02-28 | AESL PPA (C&I) - Solar | ARE41L | A1 | PSS-04 | ALMM | HSAT |  | 2026-05-31 | REC | Bondada | Q1 2027
| KPS-1 | AGEL |  |  | 50 | 25 | 0 | Phase - II | 2026-02-28 | Group - Port (Hybrid - Solar) | APSEZ | A2 | PSS-04 | ALMM | HSAT |  | 2026-05-31 |  | Bondada | Q1 2027
| KPS-1 | AGEL |  |  |  | 0 | 52 | Phase - II | 2026-02-28 | Group - Port (Hybrid - Wind) | APSEZ | A1, A2, A3, A4, A5, NHPC | PSS-04 | - | - |  | 2025-03-31 |  |  | Q4 2025
| KPS-1 | AGEL |  |  | 250 | 75 | 0 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Solar) | ACL | A1 | PSS-04 | ALMM | FT | - | 2025-12-31 |  |  | Q3 2026
| KPS-1 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Solar) | ACL | A1 | PSS-04 | ALMM | FT | - | 2025-09-09 |  |  | Q2 2026
| KPS-1 | AGEL |  |  |  | 0 | 98.8 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Wind) | ACL | A1, A2, A3, A4, A5, NHPC | PSS-04 | - | - |  | 2025-03-31 |  |  | Q4 2025
| KPS-1 | AGEL |  |  |  | 0 | 26 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Wind) | ACL | A1, A2, A3, A4, A5, NHPC | PSS-04 | - | - |  | 2025-05-13 |  |  | Q1 2026
| KPS-1 | AGEL |  |  |  | 0 | 31.2 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Wind) | ACL | A1, A2, A3, A4, A5, NHPC | PSS-04 | - | - |  | 2025-06-30 |  |  | Q1 2026
| KPS-1 | AGEL |  |  |  | 25 | 0 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Solar) | ACL | A1 | PSS-04 | ALMM | FT | - | 2026-05-31 |  | Bondada | Q1 2027
| KPS-1 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | Group - Cement (Hybrid - Solar) | ACL | A1 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-05-31 |  | Amara Raja | Q1 2027
| KPS-1 | AGEL |  |  | 150 | 150 | 0 | Phase - II | 2026-02-28 | MSEDCL PPA Ph-1 | ARE55L | A1 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-09-30 | SBI | Amara Raja | Q2 2027
| KPS-1 | AGEL |  |  | 150 | 150 | 0 | Phase - II | 2026-02-28 | TPL-D PPA | ARE8L | A2 | PSS-04 | China | HSAT | 2026-03-31 | 2026-06-30 | Yes Bank | Amara Raja | Q1 2027
| KPS-1 | AGEL |  |  | 125 | 125 | 0 | Phase - II | 2026-02-28 | MSEDCL PPA Ph-1 | ARE55L | A2 | PSS-04 | ALMM | HSAT | 2026-04-29 | 2026-09-30 | SBI | Amara Raja | Q2 2027
8 | KPS-1 | AGEL | 400kV | 100 | 100 | 0 | 52 | Phase - V | 2029-12-31 | PTSL PPA - AEML RTC - Wind | AGE24L | A16, NHPC, A1,A3 | PSS-04 | - | - | - | 2025-03-31 | NABFID |  | Q4 2025
| KPS-1 | AGEL |  |  |  | 0 | 52 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE24L | A16, NHPC, A1,A3 | PSS-04 | - | - | - | 2025-04-17 | NABFID |  | Q1 2026
9 | KPS-1 | AGEL | 400kV | 60 | 60 | 0 | 62.4 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AHEJ5L | A16, NHPC, A1,A3 | PSS-04 | - | - | - | 2025-06-30 | SBI |  | Q1 2026
10 | KPS-1 | AGEL | 400kV | 1050 | 200 | 200 | 0 | Phase - II | 2026-02-28 | Group - Cement (Solar) | ACL | A9 | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025
| KPS-1 | AGEL |  |  | 200 | 200 | 0 | Phase - II | 2026-02-28 | Group - Port (Solar) | APSEZ | A9 | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025
| KPS-1 | AGEL |  |  | 25 | 25 | 20.8 | Phase - II | 2026-02-28 | Group - Port (Hybrid) | APSEZ | A10 | PSS-03 | ALMM | HSAT | - | 2025-03-31 |  |  | Q4 2025
| KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AHEJ5L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | SBI |  | Q4 2024
| KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AGE24L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | NABFID |  | Q4 2024
| KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AGE25CL | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | REC 4 |  | Q4 2024
| KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | ARE56L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | REC 3 |  | Q4 2024
| KPS-1 | AGEL |  |  | 25 | 25 | 0 | Phase - II | 2026-02-28 | AESL PPA (C&I) - Solar- RSWM | ASEJ6L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | Axis/NABARD |  | Q4 2024
| KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AGE26AL | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | PFC -3 |  | Q4 2024
| KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | ARE57L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | EM 3.1 |  | Q4 2024
| KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | ARE55L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | Unallocated |  | Q4 2024
| KPS-1 | AGEL |  |  | 12.5 | 12.5 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | ARE41L | A9 | PSS-03 | ALMM | HSAT | - | 2024-03-31 | PFC- W |  | Q4 2024
| KPS-1 | AGEL |  |  | 400 | 112.5 | 0 | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AGE24AL | A10b | PSS-03 | ALMM | HSAT | - | 2024-12-28 | REC 1 |  | Q3 2025
| KPS-1 | AGEL |  |  |  | 287.5 |  | Phase - II | 2026-02-28 | PTSL PPA - AEML RTC - Solar | AGE24AL | A10b | PSS-03 | ALMM | HSAT | - | 2025-03-29 | REC 1 |  | Q4 2025
| KPS-1 | AGEL |  |  | 50 | 50 | 0 | Phase - II | 2026-02-28 | MLP T1 TR | AGE26AL | A10a | PSS-03 | SEA | FT | LTA - 23 Days | 2025-10-15 | PFC -3 |  | Q3 2026
11 | KPS-1 | AGEL |  | 250 | 250 | - | 5.2 | Phase - III | 2027-01-31 | PTSL PPA - AEML RTC - Wind | ARE41L | A5, A8, A4, A7, A9, A10 | PSS-03 |  |  |  | 2026-08-31 |  |  | Q2 2027
| KPS-1 | AGEL | 400kV |  |  | 0 | 260 | Phase - III | 2027-01-31 | PTSL PPA - AEML RTC - Wind | ARE41L | A5, A8, A4, A7, A9, A10 | PSS-03 | - | - | 2024-03-31 | 2024-07-24 | PFC Wind 260 |  | Q2 2025
[5 empty] | 0 | 0 | 0
12 | KPS-3 | AGEL | 400kV | 1050 | 250 | 75 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | HSAT | 2026-03-23 | 2025-11-30 | REC 4 |  | Q3 2026
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-02-28 | REC 4 |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 75 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-03-31 | REC 4 |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-05-31 | REC 4 |  | Q1 2027
| KPS-3 | AGEL |  |  | 250 | 100 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-03-31 | REC 4 |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-03-31 | REC 4 |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 100 | 0 | Phase - II | 2026-02-28 | MLP T3 PPA - AP | AGE25CL | A6c | PSS-08 | China | FT | 2026-03-23 | 2026-05-31 | REC 4 |  | Q1 2027
| KPS-3 | AGEL |  |  | 150 | 50 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | AHEJ5L | A15a | PSS-08 | ALMM | HSAT | - | 2025-09-30 | SBI |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | AHEJ5L | A15a | PSS-08 | ALMM | HSAT | - | 2026-01-31 | SBI |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | AHEJ5L | A15a | PSS-08 | ALMM | HSAT | - | 2026-05-31 | SBI | KPI | Q1 2027
| KPS-3 | AGEL |  |  | 50 | 50 | 0 | Phase - II | 2026-02-28 | MSEDCL PPA Ph-1 | ARE55L | A15b | PSS-08 | ALMM | HSAT | 2026-04-29 | 2026-09-30 | SBI | S&W | Q2 2027
| KPS-3 | AGEL |  |  | 50 | 12.5 | 0 | Phase - II | 2026-02-28 | Group - Copper (Solar) | KCTL | A15a | PSS-08 | ALMM | HSAT | - | 2026-03-31 |  |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 12.5 | 0 | Phase - II | 2026-02-28 | Group - Copper (Solar) | MCIPL | A15a | PSS-08 | ALMM | HSAT | - | 2026-03-31 |  |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 25 | 0 | Phase - II | 2026-02-28 | AGEL Merchant (Solar) | ASEJ6L | A15a | PSS-08 | ALMM | HSAT | - | 2026-03-31 | Axis |  | Q4 2026
| KPS-3 | AGEL |  |  | 60 | 0 | 62.4 | Phase - II | 2026-02-28 | AGEL Hybrid Merchant (Wind) | ASEJ6L | A15, A6 | PSS-08 |  | - | - | 2026-03-31 | TCCL |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 25 | 0 | Phase - II | 2026-02-28 | AESL PPA (C&I) - Solar- RSWM | ASEJ6L | A6 | PSS-08 | ALMM | HSAT | - | 2025-09-30 | TCCL |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 10 | 0 | Phase - II | 2026-02-28 | AESL PPA (C&I) - Solar | ASEJ6L | A6 | PSS-08 | ALMM | HSAT | - | 2025-09-30 | TCCL |  | Q2 2026
| KPS-3 | AGEL |  |  | 50 | 0 | 15.6 | Phase - II | 2026-02-28 | Adani Connex PPA - Google (Hybrid - Wind) | ARE3L | A18, A15. NHPC | PSS-08 |  | - | 2025-06-30 | 2025-08-31 | TCCL |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 0 | 26 | Phase - II | 2026-02-28 | Adani Connex PPA - Google (Hybrid - Wind) | ARE3L | A18, A15. NHPC | PSS-08 |  | - | 2025-06-30 | 2025-08-31 | TCCL |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 25 | 0 | Phase - II | 2026-02-28 | Adani Connex PPA - Google (Hybrid - Solar) | ARE3L | A6 | PSS-08 | ALMM | HSAT | 2025-06-30 | 2025-07-30 | TCCL |  | Q2 2026
| KPS-3 | AGEL |  |  | 65 | 0 | 31.2 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | AHEJ5L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-09-30 | SBI |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 0 | 31.2 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | AHEJ5L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-11-30 | SBI |  | Q3 2026
| KPS-3 | AGEL |  |  |  | 0 | 5.2 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | AHEJ5L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2026-02-28 | SBI |  | Q4 2026
| KPS-3 | AGEL |  |  | 125 | 0 | 52 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | ARE41L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 0 | 26 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | ARE41L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 0 | 46.8 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | ARE41L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-09-30 | PFC- W |  | Q2 2026
| KPS-3 | AGEL |  |  |  | 0 | 5.2 | Phase - II | 2026-02-28 | AGEL Merchant (Wind) | ARE41L | NHPC, A15,A16, A6, A18 | PSS-08 |  | - | - | 2025-11-30 | PFC- W |  | Q3 2026
13 | KPS-1 | AGEL |  | 1050 | 400 | 300 | - | Phase - III | 2027-01-31 | MSEDCL PPA Ph-1 | ARE55L | S9 | PSS-07 | ALMM | HSAT | 2026-04-29 | 2027-03-31 | SBI | S&W | Q4 2027
| KPS-1 | AGEL |  |  |  | 100 | - | Phase - III | 2027-01-31 | MSEDCL PPA Ph-1 | ARE55L | S9 | PSS-07 | ALMM | HSAT | 2026-04-29 | 2027-01-31 | SBI | S&W | Q4 2027
| KPS-1 | AGEL | 400kV |  | 600 | 600 | - | Phase - III | 2027-01-31 | MSEDCL PPA Ph-2 | ARE55L | A18 | PSS-07 | ALMM | HSAT | 2026-10-29 | 2027-03-31 | SBI | S&W | Q4 2027
| KPS-1 | AGEL |  |  | 50 | 50 | 0 | Phase - III | 2027-01-31 | MSEDCL PPA Ph-3 | ARE55L | S10 | PSS-07 | ALMM | HSAT | 2027-04-29 | 2027-03-31 | ECB | Jakson | Q4 2027
14 | KPS-3 | AGEL | 400kV | 1250 | 250 | 250 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A11 | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-28 | EM 3.1 |  | Q4 2025
| KPS-3 | AGEL |  |  | 150 | 12.5 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A11 | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-29 | EM 3.1 |  | Q4 2025
| KPS-3 | AGEL |  |  |  | 137.5 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A11 | PSS-13 | China | HSAT | LTA+15 Days | 2025-05-21 | EM 3.1 |  | Q1 2026
| KPS-3 | AGEL |  |  | 100 | 50 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A11 | PSS-13 | China | HSAT | LTA+15 Days | 2025-03-31 | EM 3.1 |  | Q4 2025
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A11 | PSS-13 | China | HSAT | LTA+15 Days | 2025-05-01 | EM 3.1 |  | Q1 2026
| KPS-3 | AGEL |  |  | 250 | 225 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2025-06-30 | EM 3.1 |  | Q1 2026
| KPS-3 | AGEL |  |  |  | 25 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026
| KPS-3 | AGEL |  |  | 150 | 100 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-10-31 | EM 3.1 |  | Q3 2027
| KPS-3 | AGEL |  |  |  | 50 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-11-30 | EM 3.1 |  | Q3 2027
| KPS-3 | AGEL |  |  | 100 | 25 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026
| KPS-3 | AGEL |  |  |  | 75 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2025-11-30 | EM 3.1 |  | Q3 2026
| KPS-3 | AGEL |  |  | 200 | 100 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-08-30 | EM 3.1 |  | Q2 2027
| KPS-3 | AGEL |  |  |  | 100 | 0 | Phase - V | 2029-12-31 | MLP PPA - AP New | ARE57L | A12 | PSS-13 | China | HSAT | LTA+15 Days | 2026-09-30 | EM 3.1 |  | Q2 2027
| KPS-3 | AGEL |  |  | 50 | 0 | 52 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | ARE41L | A11, A12, A7, A10 | PSS-13 |  | - | - | 2025-03-27 | PFC- W |  | Q4 2025
15 | KPS-3 | AGEL | 400kV | 75 | 75 | 0 | 72.8 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | ARE41L | A11, A12, A7, A10 | PSS-13 |  | - | - | 2025-03-29 | PFC- W |  | Q4 2025
16 | KPS-3 | AGEL |  | 1530 | 287.5 | 287.5 | 0 | Phase - V | 2029-12-31 | MSEDCL PPA Ph-3 | ARE55L | S10 | PSS-14 | ALMM | HSAT | 2027-04-29 | 2027-05-31 | ECB | L&T | Q1 2028
| KPS-3 | AGEL |  |  | 162.5 | 162.5 | 0 | Phase - V | 2029-12-31 | AGEL Merchant (Solar) - TTE | ARE64LS1REL | S10 | PSS-14 | ALCM | HSAT | - | 2027-05-31 | Unallocated | Jakson | Q1 2028
| KPS-3 | AGEL |  |  | 227.5 | 227.5 | 0 | Phase - V | 2029-12-31 | AGEL Merchant (Solar) - TTE | ARE64LS1REL | SE16 | PSS-14 | ALCM | HSAT | - | 2027-07-31 | Unallocated | Jakson | Q2 2028
| KPS-3 | AGEL |  |  | 366 | 366 | 0 | Phase - V | 2029-12-31 | AGEL Merchant (Solar) - TTE | ARE64LS2REL | SE14 | PSS-14 | ALCM | HSAT | - | 2027-05-31 | Unallocated | Hild | Q1 2028
| KPS-3 | AGEL |  |  | 134 | 134 | 0 | Phase - V | 2029-12-31 | MSEDCL PPA Ph-3 | ARE55L | SE14 | PSS-14 | ALCM | HSAT | - | 2027-12-31 | Unallocated | Hild | Q3 2028
17 | KPS-3 | AGEL |  | 100 | 100 | 0 | 26 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - | - | 2026-07-31 | PFC -3 |  | Q2 2027
| KPS-3 | AGEL |  |  |  | 0 | 78 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - | - | 2026-08-31 | PFC -3 |  | Q2 2027
18 | KPS-3 | AGEL |  | 195 | 195 | 0 | 98.8 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - |  | 2026-04-30 | PFC -3 |  | Q1 2027
| KPS-3 | AGEL |  |  |  | 0 | 31.2 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - |  | 2026-05-31 | PFC -3 |  | Q1 2027
| KPS-3 | AGEL |  |  |  | 0 | 26 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - |  | 2026-06-30 | PFC -3 |  | Q1 2027
| KPS-3 | AGEL |  |  |  | 0 | 52 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE26AL | SE13, SE14, SE15, SE16 | PSS-14 |  | - |  | 2026-07-31 | PFC -3 |  | Q2 2027
19 | KPS-3 | AGEL |  | 65 | 65 | 0 | 41.6 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE25CL | A18, S10 | PSS-14 |  | - | - | 2026-03-31 | REC 4 |  | Q4 2026
| KPS-3 | AGEL |  |  |  | 0 | 26 | Phase - V | 2029-12-31 | AGEL Merchant (Wind) | AGE25CL | A18, S10 | PSS-14 |  | - | - | 2026-03-31 | REC 4 |  | Q4 2026
20 | KPS-3 | AGEL |  | 75 | 75 | 75 | 0 | Phase - V | 2029-12-31 | MSEDCL PPA Ph-3 | ARE55L | SE10, SE11, SE12, SE14 | PSS-14 | ALMM | HSAT | 2027-04-29 | 2028-03-31 | ECB |  | Q4 2028
21 | KPS-3 | AGEL | KPS-4 | 600 | 600 | 50 | 0 | Phase - IV | 2028-06-30 | NHPC EPC 600 | NA | NHPC | NHPC | DCR | HSAT | 2026-12-19 | 2026-09-30 |  |  | Q2 2027
| KPS-3 | AGEL |  |  |  | 250 | 0 | Phase - IV | 2028-06-30 | NHPC EPC 600 | NA | NHPC | NHPC | DCR | HSAT | 2026-12-19 | 2027-12-31 |  |  | Q3 2028
| KPS-3 | AGEL | KPS-6 |  |  | 300 | 0 | Phase - IV | 2028-06-30 | NHPC EPC 600 | NA | NHPC | NHPC | DCR | HSAT | 2026-12-19 | 2028-03-31 |  |  | Q4 2028
|  |  |  | 13600 | 13247.5 | 11982.5 | 1721.2
SARJAN PARK
1 | KPS-1 | SRPL | 400kV | 1150 | 300 | 300 | 0 | Phase - III | 2027-01-31 | SECI VIII PPA | ASEJ6L | S7 | PSS-09 | China | FT | LTA + 30D | 2027-01-31 | Axis | Enrich | Q4 2027
| KPS-1 | SRPL |  |  | 300 | 50 | 0 | Phase - III | 2027-01-31 | SECI VIII PPA | ASEJ6L | S7 | PSS-09 | China | FT | LTA + 30D | 2027-01-31 | Axis | KPI Green | Q4 2027
| KPS-1 | SRPL |  |  |  | 250 | 0 | Phase - III | 2027-01-31 | SECI VIII PPA | ASEJ6L | S7 | PSS-09 | China | FT | LTA + 30D | 2027-02-28 | Axis | KPI Green | Q4 2027
| KPS-1 | SRPL |  |  | 400 | 150 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Solar | ARE56L | S8 | PSS-09 | ALMM | HSAT | - | 2025-03-29 | REC 3 |  | Q4 2025
| KPS-1 | SRPL |  |  |  | 125 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Solar | ARE56L | S8 | PSS-09 | ALMM | HSAT | - | 2025-05-31 | REC 3 |  | Q1 2026
| KPS-1 | SRPL |  |  |  | 125 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | ARE56L | S8 | PSS-09 | ALMM | HSAT | - | 2025-08-01 | REC 3 |  | Q2 2026
| KPS-1 | SRPL |  |  | 150 | 50 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Nestle | AGE25BL | S8 | PSS-09 | ALMM | HSAT | - | 2025-09-30 | PFC 1 |  | Q2 2026
| KPS-1 | SRPL |  |  |  | 50 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Nestle | AGE25BL | S8 | PSS-09 | ALMM | HSAT | - | 2025-09-30 | PFC 1 |  | Q2 2026
| KPS-1 | SRPL |  |  |  | 0 | 67.6 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Nestle | AGE25BL | S7, S8 | PSS-09 |  | - | - | 2025-01-14 | PFC 1 |  | Q4 2025
| KPS-1 | SRPL |  |  |  | 0 | 52 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Airport, Shantigram | AGE25BL | S7, S8 | PSS-09 |  | - | - | 2025-01-14 | PFC 1 |  | Q4 2025
| KPS-1 | SRPL |  |  |  | 0 | 10.4 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Asahi, Wilmar, Airport | AGE25BL | S7, S8 | PSS-09 |  | - | - | 2026-02-28 | PFC |  | Q4 2026
2 | KPS-3 | SRPL | 400kV | 1250 | 234 | 150 | 0 | Phase - III | 2027-01-31 | MLP T1 PPA - BEST | AGE26AL | S6-A | PSS-10 | SEA | FT | LTA + 56D | 2027-01-31 | PFC | KPI Green | Q4 2027
| KPS-3 | SRPL |  |  |  | 84 | 0 | Phase - III | 2027-01-31 | MLP T1 PPA - BEST | AGE26AL | S6-A | PSS-10 | SEA | FT | LTA + 56D | 2027-02-28 | PFC | KPI Green | Q4 2027
| KPS-3 | SRPL |  |  | 250 | 237.5 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | ARE56L | S6-B | PSS-10 | China | HSAT | 2025-11-05 | 2025-06-30 | REC 3 |  | Q1 2026
| KPS-3 | SRPL |  |  |  | 12.5 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | ARE56L | S6-B | PSS-10 | China | HSAT | 2025-11-05 | 2025-08-31 | REC 3 |  | Q2 2026
| KPS-3 | SRPL |  |  | 250 | 175 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | ARE56L | S6-B | PSS-10 | China | HSAT | 2025-11-05 | 2025-08-31 | REC 3 |  | Q2 2026
| KPS-3 | SRPL |  |  |  | 75 | 0 | Phase - III | 2027-01-31 | MLP T3 PPA - AP | ARE56L | S6-B | PSS-10 | China | HSAT | 2025-11-05 | 2025-12-31 | REC 3 |  | Q3 2026
| KPS-3 | SRPL |  |  | 150 | 75 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | AGE26BL | S5 | PSS-10 | ALMM | HSAT | - | 2026-03-31 | REC 2 |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 75 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | AGE26BL | S5 | PSS-10 | ALMM | HSAT | - | 2026-01-31 | REC 2 |  | Q4 2026
| KPS-3 | SRPL |  |  | 216 | 50 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Solar | AGE26BL | S5 | PSS-10 | ALMM | HSAT | - | 2025-09-30 | REC 2 |  | Q2 2026
| KPS-3 | SRPL |  |  |  | 92 | 0 | Phase - III | 2027-01-31 | AESL PPA (C&I) - Solar | AGE26BL | S5 | PSS-10 | ALMM | HSAT | - | 2026-03-31 | REC 2 |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 0 | 119.6 | Phase - III | 2027-01-31 | AGEL Hybrid Merchant (Wind) | AGE26BL | S5, S6, A10, S4 | PSS-10 |  | - | - | 2025-06-30 | REC 2 |  | Q1 2026
| KPS-3 | SRPL |  |  |  | 0 | 26 | Phase - III | 2027-01-31 | AGEL Hybrid Merchant (Wind) | AGE26BL | S5, S6, A10, S4 | PSS-10 |  | - | - | 2025-07-31 | REC 2 |  | Q2 2026
| KPS-3 | SRPL |  |  |  | 0 | 10.4 | Phase - III | 2027-01-31 | AGEL Hybrid Merchant (Wind) | AGE26BL | S5, S6, A10, S4 | PSS-10 |  | - | - | 2026-03-31 | REC 2 |  | Q4 2026
| KPS-3 | SRPL |  |  | 150 | 50 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L | S5 | PSS-10 | ALMM | HSAT | - | 2026-01-31 | NABFID |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 50 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L | S5 | PSS-10 | ALMM | HSAT | - | 2026-03-31 | NABFID |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 50 | 0 | Phase - III | 2027-01-31 | AGEL Merchant (Solar) | AGE24L | S5 | PSS-10 | ALMM | HSAT | - | 2026-04-30 | NABFID |  | Q1 2027
3 | KPS-3 | SRPL | 400kV | 1250 | 200 | 200 | 0 | Phase - IV | 2028-06-30 | MSEDCL PPA Ph-3 | ARE55L | S3 | PSS-11 | ALMM | HSAT | 2027-04-29 | 2027-12-31 | ECB | Bondada | Q3 2028
| KPS-3 | SRPL |  |  | 100 | 100 | 0 | Phase - IV | 2028-06-30 | Group - PVC (Solar) | MPL | S3 | PSS-11 | ALCM | HSAT | - | 2028-03-31 |  | Bondada | Q4 2028
| KPS-3 | SRPL |  |  | 200 | 200 | 0 | Phase - IV | 2028-06-30 | Group - PVC (Solar) | MPL | S3 | PSS-11 | ALCM | HSAT | - | 2028-03-31 |  | Bondada | Q4 2028
| KPS-3 | SRPL |  |  | 150 | 150 | 0 | Phase - IV | 2028-06-30 | Group - PVC (Solar) | MPL | S3 | PSS-11 | ALCM | HSAT | - | 2028-03-31 |  | Bondada | Q4 2028
| KPS-3 | SRPL |  |  | 185 | 0 | 104 | Phase - IV | 2028-06-30 | AGEL Merchant (Wind) | AGE25CL | S2, S3, S4, A11, A12 | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 0 | 52 | Phase - IV | 2028-06-30 | AGEL Merchant (Wind) | AGE25CL | S2, S3, S4, A11, A12 | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 0 | 31.2 | Phase - IV | 2028-06-30 | AGEL Merchant (Wind) | AGE25CL | S2, S3, S4, A11, A12 | PSS-11 | - | - | - | 2026-02-28 | REC 4 |  | Q4 2026
| KPS-3 | SRPL |  |  | 100 | 100 | 0 | Phase - IV | 2028-06-30 | MSEDCL PPA Ph-3 | ARE55L | S4 | PSS-11 | ALCM | HSAT | - | 2028-03-31 |  | KPI Green | Q4 2028
| KPS-3 | SRPL |  |  | 68.5 | 68.5 | 0 | Phase - IV | 2028-06-30 | MSEDCL PPA Ph-3 | ARE55L | S4 | PSS-11 | ALMM | HSAT | 2027-04-29 | 2028-03-31 | ECB | KPI Green | Q4 2028
| KPS-3 | SRPL |  |  | 112.5 | 112.5 | 0 | Phase - IV | 2028-06-30 | Group - Copper (Solar) | KCL | S4a | PSS-11 | ALCM | HSAT | - | 2028-03-31 |  | KPI Green | Q4 2028
4 | KPS-3 | SRPL | 400kV | 1100 | 300 | 100 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-1 | ARE55L | S1 | PSS-12 | ALMM | HSAT | 2026-04-29 | 2027-01-31 | SBI | L&T | Q4 2027
| KPS-3 | SRPL |  |  |  | 200 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-2 | ARE55L | S1 | PSS-12 | ALMM | HSAT | 2026-10-29 | 2027-02-28 | SBI | L&T | Q4 2027
| KPS-3 | SRPL |  |  | 75 | 75 | 0 | Phase - III | 2027-11-04 | AGEL Merchant (Solar) - TTE | ARE64LS1REL | S1 | PSS-12 | ALCM | HSAT | - | 2027-03-31 | ECB | L&T | Q4 2027
| KPS-3 | SRPL |  |  | 112.5 | 112.5 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-3 | ARE55L | S2b | PSS-12 | ALMM | HSAT | 2027-04-29 | 2027-02-28 | ECB | L&T | Q4 2027
| KPS-3 | SRPL |  |  | 175 | 75 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-1 | ARE55L | S2a | PSS-12 | ALMM | HSAT | 2026-04-29 | 2027-01-31 | SBI | L&T | Q4 2027
| KPS-3 | SRPL |  |  |  | 100 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-1 | ARE55L | S2a | PSS-12 | ALMM | HSAT | 2026-04-29 | 2027-02-28 | SBI | L&T | Q4 2027
| KPS-3 | SRPL |  |  | 50 | 50 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-2 | ARE55L | S2a | PSS-12 | ALMM | HSAT | 2026-10-29 | 2027-01-31 | SBI | L&T | Q4 2027
| KPS-3 | SRPL |  |  | 150 | 150 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-2 | ARE55L | S2 | PSS-12 | ALMM | HSAT | 2026-10-29 | 2027-04-30 | SBI | KPI Green | Q1 2028
| KPS-3 | SRPL |  |  | 100 | 100 | 0 | Phase - III | 2027-11-04 | MSEDCL PPA Ph-3 | ARE55L | S2 | PSS-12 | ALMM | HSAT | 2027-04-29 | 2027-04-30 | ECB | KPI Green | Q1 2028
| KPS-3 | SRPL |  |  | 137.5 | 0 | 52 | Phase - III | 2027-11-04 | AGEL Merchant (Wind) | AGE26AL | S1, S2, S9, S10 | PSS-12 | - | - | - | 2026-03-31 | PFC -3 |  | Q4 2026
| KPS-3 | SRPL |  |  |  | 0 | 88.4 | Phase - III | 2027-11-04 | AGEL Merchant (Wind) | AGE26AL | S1, S2, S9, S10 | PSS-12 | - | - | - | 2026-03-31 | PFC -3 |  | Q4 2026
|  |  |  | 4750 | 4616 | 4169.5 | 613.6
APL PARK
1 | KPS-4 | APL |  | 1875 | 250 | 0 | 100 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | ASEJ2L |  | PSS-18 | - | - | - | 2027-03-31 | REC |  | Q4 2027
| KPS-4 | APL |  |  |  | 0 | 150 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | ASEJ2L |  | PSS-18 | - | - | - | 2027-06-30 | REC |  | Q1 2028
| KPS-4 | APL |  |  | 400 | 400 | 0 | Phase - VI | 2029-09-30 | MLP LOA | TBD | SE13, SE15 | PSS-18 | China | TBD | - | 2027-12-31 | Unallocated |  | Q3 2028
| KPS-4 | APL |  |  | 270 | 270 | 0 | Phase - VI | 2029-09-30 | MLP LOA | TBD | SE13, SE15 | PSS-18 | China | TBD | - | 2028-03-31 | Unallocated |  | Q4 2028
3 | KPS-5 | APL |  | 1250 | 375 | 0 | 150 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | TBD |  | PSS-20 | - | - |  | 2027-12-31 | Unallocated |  | Q3 2028
| KPS-5 | APL |  |  |  | 0 | 225 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | TBD |  | PSS-20 | - | - |  | 2028-03-31 | Unallocated |  | Q4 2028
8 | KPS-5 | APL |  | 1250 | 275 | 0 | 100 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | TBD |  | PSS-15 | TBD | TBD |  | 2028-01-31 | Unallocated |  | Q4 2028
| KPS-5 | APL |  |  |  |  | 175 | Phase - VI | 2029-09-30 | AGEL Merchant (Wind) | TBD |  | PSS-15 | TBD | TBD |  | 2028-03-31 | Unallocated |  | Q4 2028
|  |  |  | 4375 | 1570 | 670 | 900
Note: Planning for projects from Mar'27 onwards is fluid and likely to go through multiple iterations
Projects commissioned till date
Projects to be executed in Year 2026-2027
Projects to be executed in Year 2027-2028
Projects to be executed in Year 2028-2029 and beyond
EPC as service contract

## Non Khavda
RJ+other sites - Project Allocation (04 Sep 2026)
# | CTUIL S/s for connectivity | Location | Connectivity status (Applied/To Be Applied) | Project Capacity | Solar | Wind | Project | SPV | SCOD | ECOD | Financing | Period
1 | Bhadla - I | Essel Park | Granted | 150 | 150 | 0 | SECI V Solar PPA | ASERJ2PL | 2024-03-31 | 2024-03-31 |  | Q4 2024
2 | Bhadla - I | Essel Park | Granted | 300 | 150 | 0 | Group - Cement | ACL | NA | 2025-08-31 |  | Q2 2026
3 | Bhadla - I | Essel Park | Granted |  | 150 | 0 | Group - Cement | ACL | NA | 2025-12-31 |  | Q3 2026
4 | Bhadla - II | Badi Sid & Kalyan Singh ki sid | Granted | 250 | 250 | 0 | MLP T2 PPA - AP | AGE25L | 2024-11-05 | 2024-12-31 | SM 2 | Q3 2025
5 | Bhadla - II | Badi Sid & Kalyan Singh ki sid | Granted | 250 | 250 | 0 | MLP T2 PPA - AP | AGE25L | 2024-11-05 | 2025-03-31 | SM 2 | Q4 2025
6 | Bhadla - II | Baap, Ultratech | Granted | 50 | 25 | 0 | PTSL PPA - AEML RTC - Solar | ASEJ6L | NA | 2025-06-30 | TCCL | Q1 2026
|  |  | Granted |  | 25 | 0 | AESL PPA (C&I) | ASEJ6L | NA | 2025-06-30 | TCCL | Q1 2026
7 | Fatehgarh - II | Devikot | Granted | 180 | 180 | 0 | SECI V Solar PPA | ASERJ2PL | 2024-03-31 | 2024-03-31 |  | Q4 2024
8 | Fatehgarh - II | Bhimsar (AREPRL) | Granted | 250 | 250 | 0 | MLP T2 PPA - AP | AGE24L | 2024-11-05 | 2025-02-28 | NABFID | Q4 2025
9 | Fatehgarh - II | Bhimsar (AREPRL) | Granted | 250 | 250 | 0 | MLP T2 PPA - AP | AGE24L | 2024-11-05 | 2025-03-31 | NABFID | Q4 2025
10 | Fatehgarh - III | Baiya | Granted | 320 | 251 | 0 | NHPC BOO - PPA | ASEB1PL | NA | 2026-03-31 | SBI 2 | Q4 2026
11 | Fatehgarh - III |  | Granted |  | 69 | 0 | NHPC BOO - PPA | ASEB1PL | NA | 2026-10-31 | SBI 2 | Q3 2027
12 | Fatehgarh - III |  | Granted | 280 | 70 | 0 | NHPC BOO - PPA | ASEB1PL | NA | 2026-10-31 | SBI 2 | Q3 2027
13 | Fatehgarh - III |  | Granted |  | 90 | 0 | NHPC BOO - PPA | ASEB1PL | NA | 2026-12-31 | SBI 2 | Q3 2027
14 | Fatehgarh - III |  | Granted |  | 120 | 0 | NHPC BOO - PPA | ASEB1PL | NA | 2027-01-31 | SBI 2 | Q4 2027
15 | Ramgarh I | Bandha | Granted | 250 | 100 | 0 | MLP PPA - AP New | AGE26BL | 2025-10-01 | 2027-12-31 | REC 2 | Q3 2028
16 | Ramgarh I |  | Granted |  | 150 | 0 | MLP PPA - AP New | AGE26BL | 2025-10-01 | 2027-12-31 | REC 2 | Q3 2028
17 | Ramgarh I |  | Granted | 100 | 100 | 0 | MLP PPA - AP New | AGE26BL | 2026-10-01 | 2028-01-31 | REC 2 | Q4 2028
18 | Ramgarh I |  | Granted | 184 | 54 | 0 | MLP PPA - AP New | AGE26BL | 2026-10-01 | 2028-02-28 | REC 2 | Q4 2028
19 | Ramgarh I |  | Granted |  | 130 | 0 | MLP PPA - AP New | AGE26BL | 2026-10-01 | 2028-02-28 | REC 2 | Q4 2028
20 | Ramgarh I | Bandha | Granted | 250 | 137.5 | 0 | MLP T1 PPA - TN | AGE25BL | LTA + 60 Days | 2026-03-31 | PFC 1 | Q4 2026
21 | Ramgarh I |  | Granted |  | 112.5 | 0 | MLP T1 PPA - TN | AGE25BL | LTA + 60 Days | 2026-12-31 | PFC 1 | Q3 2027
22 | Ramgarh I |  | Granted | 250 | 100 | 0 | MLP T1 PPA - TN | AGE25BL | LTA + 60 Days | 2026-12-31 | PFC 1 | Q3 2027
23 | Ramgarh I |  | Granted |  | 150 | 0 | MLP T1 PPA - TN | AGE25BL | LTA + 60 Days | 2027-01-31 | PFC 1 | Q4 2027
24 | Ramgarh I | Bandha | Granted | 150 | 150 | 0 | PSPCL PPA | ASEAP3L | 2026-09-30 | 2027-04-30 | IndusInd/HDFC/ABFL | Q1 2028
25 | APTransco - Talamanchipalli | Kadappa | Granted | 250 | 250 | 0 | SECI PPA Kadappa | ASEAP8PL | 2026-02-28 | 2025-03-31 | REC 3 | Q4 2025
26 | Navinal | Mundra North | Granted | 300 | 0 | 99 | AGEL Merchant (Wind) | AWEK3L | NA | 2026-07-31 | PFC | Q2 2027
27 | Navinal |  | Granted |  | 0 | 26.4 | AGEL Merchant (Wind) | AWEK3L | NA | 2026-09-30 | PFC | Q2 2027
28 | Navinal |  | Granted |  | 0 | 13.2 | AGEL Merchant (Wind) | AWEK3L | NA | 2026-09-30 | PFC | Q2 2027
29 | Navinal |  | Granted |  | 0 | 46.2 | AGEL Merchant (Wind) | AWEK3L | NA | 2026-12-31 | PFC | Q3 2027
30 | Navinal |  | Granted |  | 0 | 72.6 | AGEL Merchant (Wind) | AWEK3L | NA | 2027-03-31 | PFC | Q4 2027
31 | Navinal |  | Granted |  | 0 | 66 | AGEL Merchant (Wind) | AWEK3L | NA | 2027-03-31 | PFC | Q4 2027
32 | Navinal | APSEZ | Applied | 225 | 0 | 100 | AGEL Merchant (Wind) | AREKAL | NA | 2027-06-30 | Unallocated | Q1 2028
33 | Navinal |  | Applied |  | 0 | 125 | AGEL Merchant (Wind) | AREKAL | NA | 2027-09-30 | Unallocated | Q2 2028
34 | Bhuj II | Mandvi | Granted | 225.5 | 0 | 33 | AGEL Merchant (Wind) | AGE32L | NA | 2027-07-31 | REC | Q2 2028
35 | Bhuj II |  | Granted |  | 0 | 112.2 | AGEL Merchant (Wind) | AGE32L | NA | 2027-11-30 | REC | Q3 2028
36 | Bhuj II |  | Granted |  | 0 | 99 | AGEL Merchant (Wind) | AGE32L | NA | 2028-01-30 | REC | Q4 2028
37 | Bhuj II | Ludbay | Granted | 150 | 150 | 0 | AEML RTC - Solar | TBD | NA | 2027-11-30 | Unallocated | Q3 2028
38 | Navinal | Adipur | TBA | 300 | 0 | 150 | AGEL Merchant (Wind) | TBD | NA | 2027-09-30 |  | Q2 2028
39 | Navinal |  | TBA |  | 0 | 150 | AGEL Merchant (Wind) | TBD | NA | 2027-12-31 |  | Q3 2028
40 | Bikaner I | Hapasar | Granted | 150 | 150 |  | PTSL PPA - AEML RTC - Solar | ASEJa2PL | 2024-03-31 | 2024-03-31 |  | Q4 2024
41 | Bhadla I | Rawra | Granted | 50 | 50 |  | PTSL PPA - AEML RTC - Solar | ASEJo2L | 2024-03-31 | 2024-03-31 |  | Q4 2024
42 | Bhuj II | Mandvi | Granted | 300 |  | 300 | PTSL PPA - C&I | AWEK4L | 2024-03-31 | 2024-03-31 |  | Q4 2024
43 |  | Kutch | Granted | 50 |  | 50 | AGEL Merchant (Wind) | WFRL | 2024-03-31 | 2024-03-31 |  | Q4 2024
44 |  | Non Khavda | Granted | 4165 | 3300 | 865 |  |  | 2024-03-31 | 2024-03-31 |  | Q4 2024
45 |  | Non Khavda | Granted | 4594 | 3543 | 1051 |  |  | 2024-03-31 | 2024-03-31 |  | Q4 2024