## BOCW
Sr.No | EPC Partner | Project | PPA/Merchant | SPV | Plot | Capacity (MW) | FTC Date | Work Commencement Date | Liscense Validity Date | License Taken in name of Entity
1 | Amaraja | TPL-D PPA | PPA | ARE8L | A02 | 150 | 2026-06-16 | 2025-11-20 | 2026-11-20 | Adani Green Energy Limited
2 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 125 | 2026-07-17
3 | Amaraja | Group - Cement (Hybrid - Solar) | Group | ACL | A01 | 50 | 2026-05-17
4 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 150 | 2026-07-17
5 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-03-17 | 2025-11-30 | 2026-10-31 | Adani Green Energy Six Ltd
6 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-05-17 | Project Deffered | Shall be taken after Oct-26 | Project Deffered
7 | Bondada | AGEL Merchant (Solar) - TTE | Merchant | AE2L | S03 | 150 | 2027-05-17
8 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 200 | 2027-05-17
9 | HILD | MSEDCL PPA Ph-3 | PPA | ARE55L | SE14 | 300 | 2027-09-16 | Not Obtained | Not Obtained | Not Obtained
10 |  | MSEDCL PPA Ph-3 | PPA | ARE55L |  | 200 | 2027-08-17 | Not Obtained | Not Obtained | Not Obtained
11 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S02a | 175 | 2027-02-14 | 2025-11-01 | 2026-12-15 | Adani Green Energy Six Ltd
12 | L&T | MSEDCL PPA Ph-2 | PPA | ARE55L | S02a | 50 | 2027-01-17
13 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S02b | 112.5 | 2027-02-14
14 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S01 | 100 | 2027-01-17
15 |  | MSEDCL PPA Ph-2 | PPA | ARE55L |  | 200 | 2027-02-14
16 | L&T | AGEL Merchant (Solar) - TTE | Merchant | AE3L | S01 | 75 | 2027-03-17
17 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S10 | 287.5 | 2027-05-15
18 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | S09 | 400 | 2027-03-17 | 2025-11-30 | 2027-01-31 | Adani Renewable Enrgy 41 Limited
19 | S&W | MSEDCL PPA Ph-2 | PPA | ARE55L | A18 | 600 | 2027-03-17
20 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | A15b | 50 | 2026-06-16
21 | Enrich | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | 2026-01-28 | 2026-10-15 | Adani Green Energy Six Ltd
22 | KPI Green | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | 2025-12-23 | 2027-03-31 | Adani Green Energy Six Ltd
23 | KPI Green | MLP T1 PPA - BEST | PPA | AGE26AL | S06a | 234 | 2027-02-14

## Sheet3 (hidden)
EPC Partner | ABG/CG | Checklist Barcode | Amount
Bondada | ABG | 8O1621005#5001478175 | 51556010.94
Bondada | ABG | 8O1511005#5001478158 | 155258932.61
|  | Total Amount | 206814943.55

## GST Certificate
Sr.No | EPC Partner | Project | PPA/Merchant | SPV | Plot | Capacity (MW) | FTC Date | Obtained or Not on Gujarat State
1 | Amaraja | TPL-D PPA | PPA | ARE8L | A02 | 150 | 2026-06-16 | Obtained
2 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 125 | 2026-07-17 | Obtained
3 | Amaraja | Group - Cement (Hybrid - Solar) | Group | ACL | A01 | 50 | 2026-05-17 | Obtained
4 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 150 | 2026-07-17 | Obtained
5 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-03-17 | Obtained
6 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-05-17 | Obtained
7 | Bondada | AGEL Merchant (Solar) - TTE | Merchant | AE2L | S03 | 150 | 2027-05-17 | Obtained
8 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 200 | 2027-05-17 | Obtained
9 | HILD | MSEDCL PPA Ph-3 | PPA | ARE55L | SE14 | 300 | 2027-09-16 | Obtained
10 |  | MSEDCL PPA Ph-3 | PPA | ARE55L |  | 200 | 2027-08-17 | Obtained
11 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S02a | 175 | 2027-02-14 | Obtained
12 | L&T | MSEDCL PPA Ph-2 | PPA | ARE55L | S02a | 50 | 2027-01-17 | Obtained
13 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S02b | 112.5 | 2027-02-14 | Obtained
14 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S01 | 100 | 2027-01-17 | Obtained
15 |  | MSEDCL PPA Ph-2 | PPA | ARE55L |  | 200 | 2027-02-14 | Obtained
16 | L&T | AGEL Merchant (Solar) - TTE | Merchant | AE3L | S01 | 75 | 2027-03-17 | Obtained
17 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S10 | 287.5 | 2027-05-15 | Obtained
18 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | S09 | 400 | 2027-03-17 | Obtained
19 | S&W | MSEDCL PPA Ph-2 | PPA | ARE55L | A18 | 600 | 2027-03-17 | Obtained
20 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | A15b | 50 | 2026-06-16 | Obtained
21 | Enrich | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | Obtained
22 | KPI Green | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | Obtained
23 | KPI Green | MLP T1 PPA - BEST | PPA | AGE26AL | S06a | 234 | 2027-02-14 | Obtained

## CLRA
Sr.No | EPC Partner | Project | PPA/Merchant | SPV | Plot | Capacity (MW) | FTC Date | Liscense Obtaine on
1 | Amaraja | TPL-D PPA | PPA | ARE8L | A02 | 150 | 2026-06-16 | Offline Letter to ALC
2 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 125 | 2026-07-17 | Offline Letter to ALC
3 | Amaraja | Group - Cement (Hybrid - Solar) | Group | ACL | A01 | 50 | 2026-05-17 | Offline Letter to ALC
4 |  | MSEDCL PPA Ph-1 | PPA | ARE55L |  | 150 | 2026-07-17 | Offline Letter to ALC
5 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-03-17 | Offline Letter to ALC
6 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 150 | 2027-05-17 | Project Deffered
7 | Bondada | AGEL Merchant (Solar) - TTE | Merchant | AE2L | S03 | 150 | 2027-05-17 | Project Deffered
8 | Bondada | MSEDCL PPA Ph-3 | PPA | ARE55L | S03 | 200 | 2027-05-17 | Project Deffered
9 | HILD | MSEDCL PPA Ph-3 | PPA | ARE55L | SE14 | 300 | 2027-09-16 | Offline Letter to ALC
10 |  | MSEDCL PPA Ph-3 | PPA | ARE55L |  | 200 | 2027-08-17 | Offline Letter to ALC
11 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S02a | 175 | 2027-02-14 | Offline Letter to ALC
12 | L&T | MSEDCL PPA Ph-2 | PPA | ARE55L | S02a | 50 | 2027-01-17 | Offline Letter to ALC
13 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S02b | 112.5 | 2027-02-14 | Offline Letter to ALC
14 | L&T | MSEDCL PPA Ph-1 | PPA | ARE55L | S01 | 100 | 2027-01-17 | Offline Letter to ALC
15 |  | MSEDCL PPA Ph-2 | PPA | ARE55L |  | 200 | 2027-02-14 | Offline Letter to ALC
16 | L&T | AGEL Merchant (Solar) - TTE | Merchant | AE3L | S01 | 75 | 2027-03-17 | Offline Letter to ALC
17 | L&T | MSEDCL PPA Ph-3 | PPA | ARE55L | S10 | 287.5 | 2027-05-15 | Offline Letter to ALC
18 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | S09 | 400 | 2027-03-17 | Offline Letter to ALC
19 | S&W | MSEDCL PPA Ph-2 | PPA | ARE55L | A18 | 600 | 2027-03-17 | Offline Letter to ALC
20 | S&W | MSEDCL PPA Ph-1 | PPA | ARE55L | A15b | 50 | 2026-06-16 | Offline Letter to ALC
21 | Enrich | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | Offline Letter to ALC
22 | KPI Green | SECI VIII PPA | PPA | ASEJ6PL | S07 | 300 | 2027-01-17 | Offline Letter to ALC
23 | KPI Green | MLP T1 PPA - BEST | PPA | AGE26AL | S06a | 234 | 2027-02-14 | Offline Letter to ALC
Note - As, per discussion with Site HR Team Portal is expected to commence from 15-July-26